## Data
Project ID | Cycle | Stage | Name | Commercial Name | Developer | State | County | Status | Project Type | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Fuel | Submitted Date | Requested In-Service Date | Revised In-Service Date | Actual In-Service Date | Commercial Operation Milestone | Backfeed Date | Test Energy Date | Last Updated | Withdrawn Date | Withdrawn Remarks | Phase 1 SIS Report | Phase 1 SIS Report Status | Phase 2 SIS Report | Phase 2 SIS Report Status | Phase 3 SIS Report | Phase 3 SIS Report Status | GIA/WMPA Report | GIA/WMPA Report Status | CSA/USCA Report | CSA/USCA Report Status | Transmission Type | Rights (MW) | Long-Term Firm Service Start Date | Long-Term Firm Service End Date
AE1-070 | TC1 | PHASE 2 | Elwood 345 kV |  | Elwood Energy, LLC | IL | Will | Withdrawn | Generation Interconnection | ComEd | 1610.0 | 0.0 | 135.0 |  | Capacity | Natural Gas | 7/31/2018 | 12/31/2020 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-070/AE1-070_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-070/AE1-070_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE1-092 | TC1 | PHASE 3 | Blue Jacket-Kirby 138 kV |  | Fountain Point Solar Energy LLC | OH | Union | Active | Generation Interconnection | Dayton | 206.55 | 206.6 | 96.4 |  | Capacity | Solar | 8/31/2018 | 12/31/2021 | [5 empty] | 3/26/2025 |  |  |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-092/AE1-092_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE1-114 | TC1 | PHASE 3 | Maryland-Lancaster 138 kV |  | Leaf River Wind, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 34.0 |  | Capacity | Wind | 9/13/2018 | 12/31/2021 | [5 empty] | 4/1/2025 |  | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-114/AE1-114_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-114/AE1-114_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE1-148 | TC1 | PHASE 3 | Kerr Dam-Ridge Rd 115 kV |  | RWE Solar Development, LLC | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 90.0 | 90.0 | 54.0 |  | Capacity | Solar | 9/24/2018 | 12/1/2021 | [5 empty] | 1/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-148/AE1-148_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-148/AE1-148_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE1-172 | TC1 | PHASE 3 | Loretto-Wilton Center | Livingston Wind | EDF Renewables Development, Inc. | IL | Livingston | Active | Generation Interconnection | ComEd | 255.0 | 255.0 | 44.88 |  | Capacity | Wind | 9/25/2018 | 10/1/2021 | [5 empty] | 4/29/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE1-172/AE1-172_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE1-172/AE1-172_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-053 | TC1 | PHASE 1 | Kerr Dam-Ridge Road 115 kV |  | RWE Solar Development, LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 110.0 | 20.0 | 20.0 |  | Capacity | Storage | 2/1/2019 | 9/15/2021 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-053/AE2-053_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-107 | TC1 | PHASE 1 | Haumesser Road 138 kV |  | DK Solar LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 90.0 | 90.0 | 54.0 |  | Capacity | Solar | 2/28/2019 | 12/31/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-107/AE2-107_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-123 | TC1 | PHASE 1 | Birdneck-Landstown 230 kV |  | Avangrid Renewables, LLC | VA | City of Virginia Beach | Withdrawn | Generation Interconnection | Dominion | 800.1 | 800.1 | 163.3 |  | Capacity | Offshore Wind | 2/28/2019 | 12/31/2027 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-123/AE2-123_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-124 | TC1 | PHASE 1 | Landstown 230 kV |  | Avangrid Renewables, LLC | VA | City of Virginia Beach | Withdrawn | Generation Interconnection | Dominion | 800.1 | 800.1 | 148.5 |  | Capacity | Offshore Wind | 2/28/2019 | 12/31/2029 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-124/AE2-124_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-130 | TC1 | PHASE 1 | Rockport 765 kV |  | Sand Ridge Solar Project LLC | IN | Spencer | Withdrawn | Generation Interconnection | AEP | 800.0 | 800.0 | 480.0 |  | Capacity | Solar,Storage,Hybrid | 2/28/2019 | 12/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-130/AE2-130_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-138 | TC1 | PHASE 1 | Avon-North Clark 345 kV |  | Geenex Solar, LLC | KY | Clark | Withdrawn | Generation Interconnection | EKPC | 260.0 | 260.0 | 20.8 |  | Capacity | Solar | 3/8/2019 | 6/1/2022 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-138/AE2-138_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-138/AE2-138_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-147 | TC1 | PHASE 1 | Swamp 230 kV |  | Aurora Solar LLC | NC | Perquimans | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 3/13/2019 | 12/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-147/AE2-147_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-147/AE2-147_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-156 | TC1 | PHASE 3 | Yadkin 115 kV |  | Yadkins Energy Center, LLC | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 3/15/2019 | 12/1/2021 | [5 empty] | 2/13/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-156/AE2-156_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-156/AE2-156_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-173 | TC1 | PHASE 3 | McLean 345 kV |  | Blooming Grove Solar Energy Center LLC | IL | McLean | Active | Generation Interconnection | ComEd | 250.0 | 50.0 | 50.0 |  | Capacity | Storage | 3/18/2019 | 12/31/2022 | [5 empty] | 1/31/2025 |  |  |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-173/AE2-173_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-185 | TC1 | PHASE 3 | Gladys DP-Stonemill Switching Station 69 kV | Gladys II Solar Farm | Pigeon Run Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 60.0 | 60.0 | 36.0 |  | Capacity | Solar | 3/18/2019 | 9/1/2020 | [5 empty] | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-185/AE2-185_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-185/AE2-185_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-187 | TC1 | PHASE 3 | Shockoe DP-Chatham 69 kV |  | Zenith Solar, LLC | VA | Pittsylvania | Active | Generation Interconnection | Dominion | 60.0 | 60.0 | 36.0 |  | Capacity | Solar | 3/18/2019 | 9/1/2020 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-187/AE2-187_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-187/AE2-187_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-210 | TC1 | PHASE 1 | Avon-North Clark 345 kV |  | Geenex Solar, LLC | KY | Clark | Withdrawn | Generation Interconnection | EKPC | 90.0 | 90.0 | 7.2 |  | Capacity | Solar | 3/20/2019 | 6/1/2022 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-210/AE2-210_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-210/AE2-210_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-223 | TC1 | PHASE 3 | McLean 345 kV |  | Lexington Chenoa Wind Farm II LLC | IL | McLean | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 19.5 |  | Capacity | Wind | 3/22/2019 | 10/31/2022 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-223/AE2-223_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-223/AE2-223_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-250 | TC1 | PHASE 2 | Purdy Sw.-Reams 115 kV |  | Wyatt Mill Solar, LLC | VA | Greensville | Withdrawn | Generation Interconnection | Dominion | 82.5 | 82.5 | 54.0 |  | Capacity | Solar | 3/26/2019 | 9/30/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-250/AE2-250_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-250/AE2-250_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-261 | TC1 | PHASE 3 | Kincaid-Pana 345 kV |  | Black Diamond Solar Power, LLC | IL | Christian | Active | Generation Interconnection | ComEd | 299.0 | 299.0 | 179.4 |  | Capacity | Solar | 3/28/2019 | 6/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-261/AE2-261_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-261/AE2-261_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-270 | TC1 | PHASE 1 | Hopewell-Surry 230 kV |  | Violet Wood Solar LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 150.0 |  | Capacity | Solar,Storage,Hybrid | 3/28/2019 | 9/29/2021 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-270/AE2-270_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-275 | TC1 | PHASE 1 | J.K. Smith-Fawkes 138 kV |  | Geenex Solar, LLC | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 90.0 | 90.0 | 7.2 |  | Capacity | Solar | 3/28/2019 | 6/1/2022 | [5 empty] | 1/25/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-275/AE2-275_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-275/AE2-275_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-283 | TC1 | PHASE 3 | Gladys-Stone Mill 69 kV |  | Gladys Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 53.0 | 53.0 | 28.0 |  | Capacity | Solar | 3/29/2019 | 9/30/2021 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-283/AE2-283_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-283/AE2-283_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-291 | TC1 | PHASE 3 | Grit DP-Perth 115 kV |  | Hillandale Solar, LLC | VA | Pittsylvania | Active | Generation Interconnection | Dominion | 102.0 | 102.0 | 61.2 |  | Capacity | Solar | 3/29/2019 | 4/1/2021 | [5 empty] | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-291/AE2-291_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-291/AE2-291_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-292 | TC1 | PHASE 1 | Grit DP-Perth 115 kV |  | Eno Solar, LLC | VA | Campbell | Withdrawn | Generation Interconnection | Dominion | 127.0 | 127.0 | 76.2 |  | Capacity | Solar | 3/29/2019 | 4/1/2021 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-292/AE2-292_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AE2-308 | TC1 | PHASE 3 | Three Forks-Dale 138 kV | Madison Solar 1 | AEUG Madison Solar, LLC | KY | Madison | Active | Generation Interconnection | EKPC | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/29/2019 | 5/31/2021 |  |  |  |  | 1/31/2026 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-308/AE2-308_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-308/AE2-308_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-313 | TC1 | PHASE 2 | Carson-Rawlings 500 kV |  | RWE Solar Development, LLC | VA | Dinwiddie | Withdrawn | Generation Interconnection | Dominion | 314.0 | 314.0 | 188.4 |  | Capacity | Solar | 3/29/2019 | 9/15/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-313/AE2-313_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-313/AE2-313_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AE2-321 | TC1 | PHASE 3 | Belvidere-Marengo 138 kV |  | McHenry County Solar Project, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 100.0 | 100.0 | 67.0 |  | Capacity | Solar | 3/30/2019 | 12/1/2021 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-321/AE2-321_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-321/AE2-321_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-325 | TC1 | PHASE 3 | Valley 138 kV |  | Southwest Michigan Solar Project, LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Storage | 3/30/2019 | 12/1/2022 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-325/AE2-325_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-325/AE2-325_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AE2-341 | TC1 | PHASE 3 | Sandwich-Plano 138 kV |  | Plano Skies Energy Center, LLC | IL | Kendall | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 100.6 |  | Capacity | Solar | 3/31/2019 | 12/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AE2-341/AE2-341_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AE2-341/AE2-341_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-030 | TC1 | PHASE 3 | Sandwich-Plano 138 kV |  | Plano Skies Energy Center, LLC | IL | Kendall | Active | Generation Interconnection | ComEd | 250.0 | 100.0 | 66.9 |  | Capacity | Solar | 5/17/2019 | 12/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-030/AF1-030_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-030/AF1-030_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-048 | TC1 | PHASE 2 | Belvidere-Marengo |  | McHenry County Solar Project, LLC | IL | McHenry | Withdrawn | Generation Interconnection | ComEd | 152.2 | 52.2 | 31.32 |  | Capacity | Storage | 6/28/2019 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-048/AF1-048_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-048/AF1-048_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-099 | TC1 | PHASE 1 | Moshannon-Milesburg 230 kV III |  | Moonlight Flats Solar Power, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 126.5 | 126.5 | 75.9 |  | Capacity | Solar,Storage,Hybrid | 9/4/2019 | 4/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-099/AF1-099_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-099/AF1-099_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-100 | TC1 | PHASE 1 | Shawville-Moshannon 230 kV |  | Mineral Basin Solar Power, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | PENELEC | 250.0 | 250.0 | 150.0 |  | Capacity | Solar,Storage,Hybrid | 9/4/2019 | 4/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-100/AF1-100_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-116 | TC1 | PHASE 2 | Marion County 161 kV |  | Logan Branch Solar, LLC | KY | Washington | Withdrawn | Generation Interconnection | EKPC | 120.0 | 120.0 | 72.0 |  | Capacity | Solar | 9/12/2019 | 12/29/2023 | [5 empty] | 4/1/2025 | 2/28/2025 | Customer Milestone Not Met |  | Not Applicable |  | Not Applicable |  | Not Started |  | Not Started |  | Not Started
AF1-123 | TC1 | PHASE 3 | Oceana 230 kV |  | Virginia Electric and Power Company | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 833.0 | 833.0 | 253.2 |  | Capacity | Offshore Wind | 9/17/2019 | 12/31/2025 |  |  |  |  | 12/31/2025 | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-123/AF1-123_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-123/AF1-123_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_123_csa.pdf | Posted
AF1-124 | TC1 | PHASE 3 | Oceana 230 kV |  | Virginia Electric and Power Company | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 836.0 | 836.0 | 254.1 |  | Capacity | Offshore Wind | 9/17/2019 | 12/31/2026 | [5 empty] | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-124/AF1-124_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-124/AF1-124_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_124_csa.pdf | Posted
AF1-125 | TC1 | PHASE 3 | Oceana 230 kV |  | Virginia Electric and Power Company | VA | City of Chesapeake | Active | Generation Interconnection | Dominion | 820.0 | 820.0 | 249.3 |  | Capacity | Offshore Wind | 9/17/2019 | 12/31/2024 | [5 empty] | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-125/AF1-125_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-125/AF1-125_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_125_csa.pdf | Posted
AF1-128 | TC1 | PHASE 3 | Chesterfield 230 kV |  | Virginia Electric and Power Company | VA | Chesterfield | Active | Generation Interconnection | Dominion | 569.0 | 569.0 | 569.0 |  | Capacity | Natural Gas | 9/18/2019 | 6/1/2023 |  |  |  | 3/31/2028 | 6/30/2028 | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-128/AF1-128_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-128/AF1-128_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af1_128_csa.pdf | Posted
AF1-142 | TC1 | PHASE 1 | Moshannon-Milesburg 230 kV IV |  | Moonlight Flats Solar Power, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 328.9 | 202.4 | 121.44 |  | Capacity | Solar,Storage,Hybrid | 9/4/2019 | 4/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-142/AF1-142_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-142/AF1-142_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-152 | TC1 | PHASE 1 | Swamp 230 kV |  | Aurora Solar LLC | NC | Pasquotank | Withdrawn | Generation Interconnection | Dominion | 50.0 | 50.0 | 30.0 |  | Capacity | Solar | 9/19/2019 | 10/2/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-152/AF1-152_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-152/AF1-152_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-161 | TC1 | PHASE 3 | Valley 138 kV |  | Decatur Storage LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 25.0 |  | Capacity | Storage | 9/20/2019 | 3/1/2022 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-161/AF1-161_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-161/AF1-161_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-176 | TC1 | PHASE 3 | Corey 138 kV |  | Three Lakes Solar LLC | MI | St. Joseph | Active | Generation Interconnection | AEP | 300.0 | 300.0 | 155.684 |  | Capacity | Solar,Storage,Hybrid | 9/25/2019 | 10/31/2022 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-176/AF1-176_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-176/AF1-176_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-201 | TC1 | PHASE 1 | Hayes-White Marsh 115 kV |  | TGE Virginia 195, LLC | VA | Gloucester | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar,Storage,Hybrid | 9/24/2019 | 12/31/2021 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-201/AF1-201_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-204 | TC1 | PHASE 3 | Eugene 345 kV |  | Vermilion Grove Wind, LLC | IN | Vermillion | Active | Generation Interconnection | AEP | 255.0 | 255.0 | 63.75 |  | Capacity | Wind | 9/25/2019 | 12/31/2022 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-204/AF1-204_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-204/AF1-204_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-221 | TC1 | PHASE 2 | College Corner-Drewersburg 138 kV |  | Yellow Perch Solar LLC | IN | Franklin | Withdrawn | Generation Interconnection | AEP | 180.0 | 180.0 | 25.2 |  | Capacity | Solar | 9/27/2019 | 6/1/2022 | [5 empty] | 1/28/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-221/AF1-221_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-221/AF1-221_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-233 | TC1 | PHASE 3 | Flemingsburg – Spurlock 138kV | AEUG Fleming Solar | AEUG Fleming Solar, LLC | KY | Fleming | Active | Generation Interconnection | EKPC | 188.5 | 188.5 | 113.1 |  | Capacity | Solar | 9/27/2019 | 5/31/2022 | [5 empty] | 2/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-233/AF1-233_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-233/AF1-233_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-238 | TC1 | PHASE 3 | Sherman Ave - West Vineland 69 kV |  | Garden Reserve Energy, LLC | NJ | Cumberland | Active | Generation Interconnection | AEC | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 9/28/2019 | 5/31/2023 | [5 empty] | 1/30/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-238/AF1-238_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-238/AF1-238_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-240 | TC1 | PHASE 3 | Timblin 34.5 kV |  | AR-Pierce LLC | PA | Armstrong | Active | Generation Interconnection | PENELEC | 15.75 | 15.75 | 11.0 |  | Capacity | Solar | 9/30/2019 | 7/1/2022 | [5 empty] | 2/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-240/AF1-240_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-240/AF1-240_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-252 | TC1 | PHASE 1 | Kincaid-Pana |  | Rolling Farms Wind Project, LLC | IL | Christian | Withdrawn | Generation Interconnection | ComEd | 262.4 | 62.4 | 62.4 |  | Capacity | Storage | 9/30/2019 | 9/1/2022 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-252/AF1-252_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-253 | TC1 | PHASE 1 | Kincaid-Pana |  | Rolling Farms Wind Project, LLC | IL | Christian | Withdrawn | Generation Interconnection | ComEd | 305.6 | 43.2 | 43.2 |  | Capacity | Storage | 9/30/2019 | 9/1/2022 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-253/AF1-253_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-266 | TC1 | PHASE 1 | Clubhouse-Sapony 230 kV |  | Invenergy Solar Project Development LLC | VA | Dinwiddie | Withdrawn | Generation Interconnection | Dominion | 223.5 | 74.5 | 74.5 |  | Capacity | Storage | 9/30/2019 | 12/31/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-266/AF1-266_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-270 | TC1 | PHASE 2 | Blue Jacket-Kirby 138 kV |  | Fountain Point Solar Energy LLC | OH | Logan | Withdrawn | Generation Interconnection | Dayton | 279.5 | 50.0 | 50.0 |  | Capacity | Solar | 9/30/2019 | 12/31/2022 | [5 empty] | 12/20/2024 | 6/21/2024 | Customer Milestone Not Met |  | Not Applicable |  | Not Specified |  | Not Started |  | Not Started |  | Not Started
AF1-276 | TC1 | PHASE 1 | Lewis Run-Pierce Brook 230 kV |  | McKean Solar, LLC | PA | McKean | Withdrawn | Generation Interconnection | PENELEC | 100.0 | 100.0 | 67.0 |  | Capacity | Solar | 9/30/2019 | 6/29/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-276/AF1-276_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-277 | TC1 | PHASE 1 | Lewis Run-Pierce Brook 2 230 kV |  | McKean Solar, LLC | PA | McKean | Withdrawn | Generation Interconnection | PENELEC | 200.0 | 100.0 | 67.0 |  | Capacity | Solar | 9/30/2019 | 6/29/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-277/AF1-277_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-278 | TC1 | PHASE 1 | Lewis Run-Pierce Brook 3 230 kV |  | McKean Solar, LLC | PA | Mc Kean | Withdrawn | Generation Interconnection | PENELEC | 280.0 | 80.0 | 53.44 |  | Capacity | Solar | 9/30/2019 | 6/29/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-278/AF1-278_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-280 | TC1 | PHASE 3 | Nelson-Lee County |  | Deriva Energy Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 200.0 | 200.0 | 0.0 |  | Energy | Solar | 9/10/2019 | 12/1/2022 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-280/AF1-280_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-280/AF1-280_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-281 | TC1 | PHASE 1 | Nelson-Lee County |  | Deriva Energy Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 220.0 | 20.0 | 3.0 |  | Capacity | Storage | 9/10/2019 | 12/1/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-281/AF1-281_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-293 | TC1 | PHASE 1 | Kidds Store-Fort Union 115 kV |  | Kidds Store, LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 127.86 | 127.86 | 108.37 |  | Capacity | Solar,Storage,Hybrid | 9/30/2019 | 6/30/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-293/AF1-293_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-294 | TC1 | PHASE 3 | Jetersville-Ponton 115 kV |  | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 41.0 | 41.0 | 22.2 |  | Capacity | Solar | 9/30/2019 | 12/1/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-294/AF1-294_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-294/AF1-294_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-296 | TC1 | PHASE 3 | Garden Plain 138 kV |  | Gipper Wind Farm, LLC | IL | Whiteside | Active | Generation Interconnection | ComEd | 190.89 | 190.89 | 33.6 |  | Capacity | Wind | 9/30/2019 | 9/15/2022 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-296/AF1-296_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-296/AF1-296_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF1-301 | TC1 | PHASE 1 | Louisa-South Anna 230 kV |  | Invenergy Solar Project Development LLC | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 117.0 | 117.0 | 70.0 |  | Capacity | Solar | 9/30/2019 | 12/31/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-301/AF1-301_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-306 | TC1 | PHASE 1 | Squab Hollow 230 kV |  | Seven Creek Energy, LLC | PA | Elk | Withdrawn | Generation Interconnection | APS | 197.2 | 197.2 | 49.3 |  | Capacity | Storage | 9/30/2019 | 5/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-306/AF1-306_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-314 | TC1 | PHASE 2 | Lena - Lancaster 138 kV |  | High Point Wind Farm, LLC | IL | Stephenson | Withdrawn | Generation Interconnection | ComEd | 212.0 | 212.0 | 37.2 |  | Capacity | Wind | 9/30/2019 | 9/15/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-314/AF1-314_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-314/AF1-314_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF1-318 | TC1 | PHASE 1 | Crescent Ridge-Corbin |  | SkyYield Wind Farm, LLC | IL | Putnam | Withdrawn | Generation Interconnection | ComEd | 299.97 | 299.97 | 52.7947 |  | Capacity | Wind | 9/30/2019 | 9/15/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-318/AF1-318_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF1-323 | TC1 | PHASE 2 | Scottsville-Colleen 138 kV |  | Vista Energy Facility, LLC | VA | Albemarle | Withdrawn | Generation Interconnection | AEP | 55.0 | 55.0 | 33.0 |  | Capacity | Solar | 9/30/2019 | 12/12/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF1-323/AF1-323_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF1-323/AF1-323_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-010 | TC1 | PHASE 3 | Union City-Titusville 115 kV |  | RWE Solar Development, LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 77.0 | 77.0 | 46.0 |  | Capacity | Solar | 10/11/2019 | 12/15/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-010/AF2-010_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-010/AF2-010_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-016 | TC1 | PHASE 1 | Lewis 138 kV |  | Garden Reserve Energy, LLC | NJ | Atlantic | Withdrawn | Generation Interconnection | AEC | 240.0 | 240.0 | 96.0 |  | Capacity | Storage | 10/1/2019 | 5/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-016/AF2-016_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-021 | TC1 | PHASE 1 | Cedar 69 kV |  | Calpine Mid-Atlantic Development, LLC | NJ | Ocean | Withdrawn | Generation Interconnection | AEC | 20.0 | 20.0 | 8.0 |  | Capacity | Storage | 11/15/2019 | 6/1/2021 | [5 empty] | 7/2/2024 | 5/31/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-021/AF2-021_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-025 | TC1 | FINAL AGREEMENT | Ontario 69 kV | Missouri Avenue Battery Storage Project | Calpine Mid-Atlantic Development, LLC | NJ | Atlantic | EP | Generation Interconnection | AEC | 20.0 | 20.0 | 8.0 |  | Capacity | Storage | 11/15/2019 | 6/1/2021 | 4/30/2028 |  |  | 2/1/2028 | 2/15/2028 | 4/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-025/AF2-025_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-025/AF2-025_imp_PHASE_2.htm | Posted |  | Not Required |  | Not Started |  | Not Started
AF2-034 | TC1 | PHASE 2 | Kendall 345kV |  | Kendall Solar BESS LLC | IL | Kendall | Withdrawn | Generation Interconnection | ComEd | 1238.8 | 20.0 | 10.8 |  | Capacity | Solar,Storage,Hybrid | 10/28/2019 | 6/1/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-034/AF2-034_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-034/AF2-034_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-035 | TC1 | PHASE 3 | St. Johns 115 kV |  | Anna River Solar, LLC | VA | Hanover | Active | Generation Interconnection | Dominion | 72.0 | 72.0 | 48.0 |  | Capacity | Solar | 11/27/2019 | 10/27/2023 | [5 empty] | 2/20/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-035/AF2-035_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-035/AF2-035_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-037 | TC1 | PHASE 2 | Louisa-North Anna 230 kV |  | AURA POWER DEVELOPMENTS (USA), LLC | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 94.0 | 94.0 | 56.4 |  | Capacity | Solar | 11/29/2019 | 7/1/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-037/AF2-037_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-037/AF2-037_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-041 | TC1 | PHASE 3 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 12/9/2019 | 11/1/2023 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-041/AF2-041_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-041/AF2-041_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-042 | TC1 | PHASE 3 | Clover-Rawlings 500 kV |  | Virginia Electric and Power Company | VA | Halifax | Active | Generation Interconnection | Dominion | 500.0 | 500.0 | 300.0 |  | Capacity | Solar | 12/9/2019 | 12/31/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-042/AF2-042_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-042/AF2-042_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-046 | TC1 | PHASE 3 | Tunis-Mapleton 115 kV |  | Murphy Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 126.0 | 126.0 | 83.7 |  | Capacity | Solar | 12/19/2019 | 6/1/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-046/AF2-046_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-046/AF2-046_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-047 | TC1 | PHASE 1 | Creswell-Riders Creek 115 kV |  | Creswell HWY 64 Solar, LLC | NC | Washington | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 99.8 |  | Capacity | Solar | 12/19/2019 | 6/1/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-047/AF2-047_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-050 | TC1 | PHASE 3 | Bearrock-Johnstown 230 kV |  | CPV Maple Hill Solar II, LLC | PA | Cambria | Active | Generation Interconnection | PENELEC | 150.0 | 50.0 | 30.0 |  | Capacity | Solar | 12/23/2019 | 9/1/2021 | [5 empty] | 3/14/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-050/AF2-050_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-050/AF2-050_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-056 | TC1 | PHASE 1 | Shenandoah Tap 1– Mahanoy Tap 2 69 kV |  | Locust Ridge Solar LLC | PA | Schuylkill | Withdrawn | Generation Interconnection | PPL | 50.0 | 50.0 | 33.0 |  | Capacity | Solar | 1/16/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-056/AF2-056_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-056/AF2-056_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-063 | TC1 | PHASE 2 | Louisa-North Anna 230 kV |  | AURA POWER DEVELOPMENTS (USA), LLC | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 1/29/2020 | 2/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-063/AF2-063_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-063/AF2-063_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-065 | TC1 | PHASE 1 | Surry-Hopewell 230 kV |  | Violet Wood Solar LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 300.0 | 150.0 | 76.5 |  | Capacity | Solar | 1/30/2020 | 10/21/2021 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-065/AF2-065_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-068 | TC1 | PHASE 3 | Jay 138 kV |  | Leeward Renewable Energy Development, LLC | IN | Blackford | Active | Generation Interconnection | AEP | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 1/30/2020 | 10/3/2022 | [5 empty] | 2/3/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-068/AF2-068_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-068/AF2-068_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-069 | TC1 | PHASE 3 | Crescent Ridge 138 kV |  | Lone Tree Wind, LLC | IL | Bureau | Active | Generation Interconnection | ComEd | 87.8 | 8.4 | 1.98 |  | Capacity | Wind | 1/31/2020 | 10/4/2021 | [5 empty] | 3/3/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-069/AF2-069_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-069/AF2-069_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-070 | TC1 | PHASE 2 | Crescent Ridge 138 kV |  | Crescent Ridge LLC | IL | Bureau | Withdrawn | Generation Interconnection | ComEd | 72.6 | 18.15 | 3.1 |  | Capacity | Wind | 1/31/2020 | 10/4/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-070/AF2-070_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-070/AF2-070_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-080 | TC1 | PHASE 3 | Chinquapin-Everetts 230 kV |  | Pitt Solar, LLC | NC | Pitt | Active | Generation Interconnection | Dominion | 150.0 | 70.0 | 48.5 |  | Capacity | Solar | 1/31/2020 | 6/30/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-080/AF2-080_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-080/AF2-080_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-081 | TC1 | PHASE 3 | Moyock 230 kV |  | Currituck Solar, LLC | NC | Currituck | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 56.0 |  | Capacity | Solar | 1/31/2020 | 12/1/2023 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-081/AF2-081_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-081/AF2-081_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-095 | TC1 | PHASE 3 | Davis Creek 138 kV |  | AEUG Kankakee Solar, LLC | IL | Kankakee | Active | Generation Interconnection | ComEd | 144.0 | 144.0 | 86.4 |  | Capacity | Solar | 2/13/2020 | 5/31/2021 | [5 empty] | 2/26/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-095/AF2-095_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-095/AF2-095_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-096 | TC1 | PHASE 2 | Braidwood-East Frankfort 345 kV |  | AEUG Will Solar, LLC | IL | Will | Withdrawn | Generation Interconnection | ComEd | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 2/12/2020 | 5/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-096/AF2-096_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-096/AF2-096_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-111 | TC1 | PHASE 3 | North Clark-Spurlock 345 kV |  | Goldfinch Solar, LLC | KY | Mason | Active | Generation Interconnection | EKPC | 250.0 | 250.0 | 150.0 |  | Capacity | Solar | 2/28/2020 | 12/31/2023 | [5 empty] | 3/3/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-111/AF2-111_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-111/AF2-111_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-115 | TC1 | PHASE 3 | Jetersville-Ponton 115 kV |  | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 66.0 | 25.0 | 13.5 |  | Capacity | Solar | 2/28/2020 | 12/1/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-115/AF2-115_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-115/AF2-115_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-120 | TC1 | PHASE 3 | Garner-Northern Neck 115 kV |  | Virginia Electric and Power Company | VA | Richmond | Active | Generation Interconnection | Dominion | 62.0 | 62.0 | 37.2 |  | Capacity | Solar | 2/28/2020 | 12/1/2023 |  |  |  | 12/1/2025 | 2/6/2026 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-120/AF2-120_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-120/AF2-120_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af2_120_csa.pdf | Posted
AF2-126 | TC1 | PHASE 3 | Weston 69 kV II |  | Juliet Energy Project, LLC | OH | Wood | Active | Generation Interconnection | ATSI | 62.0 | 12.0 | 8.0 |  | Capacity | Solar | 2/28/2020 | 12/31/2021 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-126/AF2-126_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-126/AF2-126_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-128 | TC1 | DP1 | Crescent Ridge-Corbin 138 kV |  | UKA Green Power LLC | IL | Lasalle | Withdrawn | Generation Interconnection | ComEd | 79.5 | 79.5 | 13.992 |  | Capacity | Wind | 2/28/2020 | 8/26/2024 | [5 empty] | 7/15/2024 | 6/25/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-128/AF2-128_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-142 | TC1 | PHASE 3 | Nevada 345 kV |  | Aurora Solar LLC | IL | Lasalle | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 3/12/2020 | 12/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-142/AF2-142_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-142/AF2-142_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-143 | TC1 | PHASE 3 | Powerton-Nevada 345 kV |  | Aurora Solar LLC | IL | Lasalle | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 3/12/2020 | 12/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-143/AF2-143_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-143/AF2-143_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-164 | TC1 | PHASE 1 | Handsome Lake 345 kV |  | Heartland Solar LLC | PA | Venango | Withdrawn | Generation Interconnection | PENELEC | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/17/2020 | 9/15/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-164/AF2-164_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-171 | TC1 | PHASE 1 | Madisonville 115 kV |  | CPV County Line Solar, LLC | VA | Prince Edward | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 3/19/2020 | 3/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-171/AF2-171_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-171/AF2-171_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-173 | TC1 | PHASE 3 | Desoto 345 kV |  | Esker Solar Park LLC | IN | Delaware | Active | Generation Interconnection | AEP | 140.0 | 140.0 | 84.0 |  | Capacity | Solar | 3/19/2020 | 10/31/2023 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-173/AF2-173_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-173/AF2-173_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-176 | TC1 | PHASE 1 | Masury-Maysville 138 kV |  | Sanderson Solar LLC | PA | Mercer | Withdrawn | Generation Interconnection | ATSI | 60.0 | 60.0 | 36.0 |  | Capacity | Solar | 3/19/2020 | 9/15/2022 | [5 empty] | 6/25/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-176/AF2-176_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-177 | TC1 | PHASE 3 | Sorenson-DeSoto #2 345 kV |  | Blackford County Wind Farm LLC | IN | Blackford | Active | Generation Interconnection | AEP | 200.0 | 200.0 | 26.0 |  | Capacity | Wind | 3/20/2020 | 10/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-177/AF2-177_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-177/AF2-177_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-182 | TC1 | PHASE 3 | Nelson-Lee County 345 kV II |  | Deriva Energy Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 500.0 | 300.0 | 0.0 |  | Energy | Solar | 3/21/2020 | 12/1/2022 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-182/AF2-182_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-182/AF2-182_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-183 | TC1 | PHASE 1 | Nelson-Lee County 345 kV |  | Deriva Energy Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 600.0 | 80.0 | 32.0 |  | Capacity | Storage | 3/20/2020 | 12/1/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-183/AF2-183_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-193 | TC1 | PHASE 1 | Indian River 230 kV I |  | GSOE I, LLC | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 440.0 | 440.0 | 119.0 |  | Capacity | Offshore Wind | 3/23/2020 | 10/31/2026 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-193/AF2-193_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-194 | TC1 | PHASE 1 | Indian River 230 kV II |  | GSOE I, LLC | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 880.0 | 440.0 | 119.0 |  | Capacity | Offshore Wind | 3/23/2020 | 10/31/2026 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-194/AF2-194_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-199 | TC1 | PHASE 3 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 400.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/24/2020 | 11/1/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-199/AF2-199_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-199/AF2-199_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-200 | TC1 | PHASE 3 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 600.0 | 200.0 | 120.0 |  | Capacity | Solar | 3/24/2020 | 11/1/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-200/AF2-200_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-200/AF2-200_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-201 | TC1 | PHASE 2 | Lena - Lancaster 138 kV |  | Blue Violet Energy, LLC | IL | Stephenson | Withdrawn | Generation Interconnection | ComEd | 199.0 | 199.0 | 51.4 |  | Capacity | Wind,Solar,Hybrid | 3/24/2020 | 5/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-201/AF2-201_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-201/AF2-201_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-209 | TC1 | DP2 | South Hicksville-Sowers 138 kV |  | Mink Solar LLC | OH | Defiance | Withdrawn | Generation Interconnection | AEP | 140.0 | 140.0 | 19.6 |  | Capacity | Solar | 3/25/2020 | 6/2/2023 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-209/AF2-209_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-209/AF2-209_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-222 | TC1 | PHASE 3 | Madisonville DP-Twitty's Creek 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 167.0 | 167.0 | 100.0 |  | Capacity | Solar | 3/25/2020 | 5/31/2023 |  |  |  | 12/31/2025 | 3/31/2027 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-222/AF2-222_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-222/AF2-222_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/af2_222_csa.pdf | Posted
AF2-225 | TC1 | PHASE 3 | McLean 345 kV |  | Bright Stalk Solar Park LLC | IL | McLean | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 63.0 |  | Capacity | Solar | 3/26/2020 | 10/31/2022 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-225/AF2-225_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-225/AF2-225_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-226 | TC1 | PHASE 3 | Katydid Road 345 kV |  | Blackstone Wind Farm, LLC | IL | Lasalle | Active | Generation Interconnection | ComEd | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/26/2020 | 10/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-226/AF2-226_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-226/AF2-226_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-263 | TC1 | PHASE 1 | Shelby 138 kV |  | AEUG Shelby Solar, LLC | OH | Shelby | Withdrawn | Generation Interconnection | Dayton | 98.0 | 98.0 | 58.8 |  | Capacity | Solar | 3/27/2020 | 7/1/2022 | [5 empty] | 8/1/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-263/AF2-263_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-296 | TC1 | PHASE 3 | Madera 34.5 kV |  | CL-Belsena LLC | PA | Clearfield | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/28/2020 | 10/1/2021 | [5 empty] | 2/18/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-296/AF2-296_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-296/AF2-296_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-297 | TC1 | PHASE 3 | Sedge Hill 115 kV |  | Sedge Hill Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/28/2020 | 3/12/2022 | [5 empty] | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-297/AF2-297_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-297/AF2-297_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-299 | TC1 | PHASE 3 | Fields 34.5 kV | Jarratt Energy Facility 2 | Jarratt Energy Facility, LLC | VA | Greensville | Active | Generation Interconnection | Dominion | 18.0 | 18.0 | 10.8 |  | Capacity | Solar | 3/30/2020 | 12/12/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-299/AF2-299_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-299/AF2-299_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-302 | TC1 | PHASE 2 | Scottsville-Colleen 138 kV |  | Vista Energy Facility, LLC | VA | Albemarle | Withdrawn | Generation Interconnection | AEP | 75.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/30/2020 | 12/12/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-302/AF2-302_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-302/AF2-302_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-307 | TC1 | PHASE 3 | Hope-Belvins Valley Tap 69 kV |  | Flat Top Solar Project, LLC | KY | Bath | Active | Generation Interconnection | EKPC | 64.2 | 64.2 | 39.6 |  | Capacity | Solar | 3/30/2020 | 9/1/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-307/AF2-307_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-307/AF2-307_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-319 | TC1 | PHASE 3 | Katydid Road 345 kV |  | Blackstone Wind Farm II LLC | IL | Lasalle | Active | Generation Interconnection | ComEd | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/30/2020 | 10/31/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-319/AF2-319_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-319/AF2-319_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-321 | TC1 | PHASE 1 | Stryker-Ridgeville 138 kV |  | Williams County Solar, LLC | OH | Williams | Withdrawn | Generation Interconnection | ATSI | 148.0 | 148.0 | 88.8 |  | Capacity | Solar | 3/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-321/AF2-321_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-321/AF2-321_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-324 | TC1 | PHASE 2 | Edgecombe 230 kV |  | Bridge Solar, LLC | NC | Edgecombe | Withdrawn | Generation Interconnection | Dominion | 75.0 | 75.0 | 45.0 |  | Capacity | Solar | 3/30/2020 | 11/30/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-324/AF2-324_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-324/AF2-324_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-329 | TC1 | PHASE 2 | Sandwich-Plano 138 kV |  | Plano Skies Energy Center, LLC | IL | Kendall | Withdrawn | Generation Interconnection | ComEd | 292.2 | 42.2 | 42.2 |  | Capacity | Storage | 3/30/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-329/AF2-329_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-329/AF2-329_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-335 | TC1 | PHASE 3 | Delaware-Royerton 138 kV |  | Royerton Solar, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/31/2020 | 12/31/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-335/AF2-335_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-335/AF2-335_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-348 | TC1 | DP2 | North Clark-Spurlock 345 kV |  | AEUG Covered Bridge Solar, LLC | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 250.0 | 250.0 | 150.0 |  | Capacity | Solar | 3/31/2020 | 7/1/2022 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-348/AF2-348_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-348/AF2-348_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-349 | TC1 | PHASE 3 | SILVER LAKE- CHERRY VALLEY 345 KV |  | Deriva Energy Solar, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 300.0 | 300.0 | 0.0 |  | Energy | Solar | 3/31/2020 | 12/1/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-349/AF2-349_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-349/AF2-349_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-350 | TC1 | PHASE 3 | Kensington 138 kV |  | Deriva Energy Solar, LLC | IL | Kankakee | Active | Generation Interconnection | ComEd | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/31/2020 | 12/1/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-350/AF2-350_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-350/AF2-350_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-351 | TC1 | PHASE 1 | Kensington 138 kV |  | Deriva Energy Solar, LLC | IL | Kankakee | Withdrawn | Generation Interconnection | ComEd | 120.0 | 20.0 | 8.0 |  | Capacity | Storage | 3/31/2020 | 12/1/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-351/AF2-351_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-355 | TC1 | DP2 | West Gerrard-J.K. Smith 345 kV |  | AEUG Richmond Solar, LLC | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 225.0 | 225.0 | 135.0 |  | Capacity | Solar | 3/31/2020 | 7/1/2022 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-355/AF2-355_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-355/AF2-355_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-358 | TC1 | PHASE 3 | Airey-Vienna 69 kV |  | RWE Solar Development, LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/31/2020 | 12/15/2023 | [5 empty] | 1/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-358/AF2-358_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-358/AF2-358_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-365 | TC1 | PHASE 3 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | Thoroughbred Solar, LLC | KY | Hart | Active | Generation Interconnection | EKPC | 50.0 | 50.0 | 30.0 |  | Capacity | Solar | 3/31/2020 | 12/31/2022 | [5 empty] | 3/3/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AF2-370 | TC1 | PHASE 3 | Delaware-Royerton 138 kV |  | Royerton Solar, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 100.0 | 0.0 | 20.0 |  | Capacity | Storage | 3/31/2020 | 12/31/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-370/AF2-370_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-370/AF2-370_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-376 | TC1 | PHASE 3 | Timber Switch 138 kV |  | Paulding Wind Farm II LLC | OH | Paulding | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/31/2020 | 10/31/2023 | [5 empty] | 3/12/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AF2-381 | TC1 | PHASE 1 | Bedford North-Central City West 115 kV |  | Panther Run Solar, LLC | PA | Somerset | Withdrawn | Generation Interconnection | PENELEC | 60.0 | 60.0 | 40.2 |  | Capacity | Solar | 4/1/2020 | 6/30/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-381/AF2-381_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-388 | TC1 | PHASE 3 | Keystone-Desoto 345 kV |  | RWE Renewables Development, LLC | IN | Blackford | Active | Generation Interconnection | AEP | 200.0 | 200.0 | 35.2 |  | Capacity | Wind | 3/31/2020 | 12/15/2023 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-388/AF2-388_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-388/AF2-388_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-391 | TC1 | PHASE 2 | Central Hardin 69 kV |  | Naturgy Candela DevCo LLC | KY | Hardin | Withdrawn | Generation Interconnection | EKPC | 120.0 | 120.0 | 72.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2020 | 6/15/2023 | [5 empty] | 1/14/2025 | 1/14/2025 | Customer Initiated Withdrawal |  | Not Applicable |  | Not Specified |  | Not Started |  | Not Started |  | Not Started
AF2-392 | TC1 | PHASE 3 | Nelson-Dixon 138 kV |  | Bison Meadows Wind Project, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 199.0 | 199.0 | 35.2 |  | Capacity | Wind | 3/31/2020 | 9/1/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-392/AF2-392_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-392/AF2-392_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-393 | TC1 | PHASE 2 | Nelson-Dixon 138 kV |  | Bison Meadows Wind Project, LLC | IL | Adams | Withdrawn | Generation Interconnection | ComEd | 259.0 | 60.0 | 55.0 |  | Capacity | Storage | 3/31/2020 | 9/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-393/AF2-393_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-393/AF2-393_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-394 | TC1 | PHASE 2 | Nelson-Dixon 138 kV |  | Bison Meadows Wind Project, LLC | IL | Adams | Withdrawn | Generation Interconnection | ComEd | 299.0 | 40.0 | 40.0 |  | Capacity | Storage | 3/31/2020 | 9/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-394/AF2-394_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-394/AF2-394_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-396 | TC1 | PHASE 3 | Stinger 138 kV |  | Steelhead Solar, LLC | MI | Cass | Active | Generation Interconnection | AEP | 200.0 | 200.0 | 200.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2020 | 12/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-396/AF2-396_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-396/AF2-396_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-397 | TC1 | PHASE 1 | Fork Union-Mt. Eagle 230 kV |  | Kidds Store II, LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 130.0 | 130.0 | 78.0 |  | Capacity | Solar,Storage,Hybrid | 4/1/2020 | 12/15/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-397/AF2-397_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-403 | TC1 | PHASE 1 | Shockoe DP-Chatham 69 kV | Shockoe Storage / Shockoe DP-Chatham 69 kV | Zenith Solar, LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 60.0 | 0.0 | 8.0 |  | Capacity | Storage | 3/31/2020 | 12/15/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-403/AF2-403_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-403/AF2-403_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-404 | TC1 | PHASE 3 | Gladys DP-Stonemill 69 kV |  | Pigeon Run Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 60.0 | 0.0 | 0.0 |  | Energy | Storage | 3/31/2020 | 12/15/2022 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-404/AF2-404_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-404/AF2-404_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-406 | TC1 | PHASE 1 | Sayre 115 kV |  | Juno Power Management LLC | PA | Bradford | Withdrawn | Generation Interconnection | PENELEC | 75.0 | 75.0 | 75.0 |  | Capacity | Storage | 3/31/2020 | 6/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-406/AF2-406_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AF2-407 | TC1 | PHASE 3 | Fall Creek 345 kV |  | Liberty Madison Storage LLC | IN | Madison | Active | Generation Interconnection | AEP | 300.0 | 300.0 | 300.0 |  | Capacity | Storage | 3/31/2020 | 6/1/2022 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-407/AF2-407_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-407/AF2-407_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AF2-412 | TC1 | PHASE 1 | Mainesburg 115 kV |  | Elk Run LLC | PA | Tioga | Withdrawn | Generation Interconnection | PENELEC | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 3/31/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-412/AF2-412_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-412/AF2-412_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AF2-441 | TC1 | PHASE 3 | Burnham 138kV |  | Lincoln Reserve Energy, LLC | IL | Cook | Active | Generation Interconnection | ComEd | 200.0 | 200.0 | 80.0 |  | Capacity | Storage | 3/31/2020 | 5/31/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AF2-441/AF2-441_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AF2-441/AF2-441_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-005 | TC1 | PHASE 2 | Corbin-Crescent Ridge 138 kV |  | Sky Yield Solar Farm, LLC | IL | Stephenson | Withdrawn | Generation Interconnection | ComEd | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 4/29/2020 | 10/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-005/AG1-005_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-005/AG1-005_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-008 | TC1 | PHASE 3 | Tunis-Mapleton 115 kV |  | Bells Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 126.0 | 126.0 | 83.7 |  | Capacity | Solar | 5/1/2020 | 12/15/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-008/AG1-008_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-008/AG1-008_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-011 | TC1 | PHASE 1 | Colonial Trail 230 kV |  | Urban Grid Solar Projects, LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 160.0 | 160.0 | 160.0 |  | Capacity | Storage | 5/8/2020 | 6/30/2022 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-011/AG1-011_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-019 | TC1 | PHASE 1 | Arnold's Corner-Dahlgren 230 kV |  | Harwood Power, LLC | VA | King George | Withdrawn | Generation Interconnection | Dominion | 200.0 | 100.0 | 100.0 |  | Capacity | Storage | 5/20/2020 | 10/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-019/AG1-019_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-021 | TC1 | PHASE 3 | Jetersville-Ponton 115 kV |  | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 86.0 | 20.0 | 10.8 |  | Capacity | Solar | 5/26/2020 | 12/12/2023 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-021/AG1-021_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-021/AG1-021_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-022 | TC1 | PHASE 2 | Scottsville-Colleen 138 kV |  | Vista Energy Facility, LLC | VA | Albemarle | Withdrawn | Generation Interconnection | AEP | 95.0 | 20.0 | 12.0 |  | Capacity | Solar | 5/26/2020 | 12/12/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-022/AG1-022_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-022/AG1-022_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-030 | TC1 | PHASE 1 | Victoria DP-Martin DP 115 kV |  | Dickerson Creek Solar LLC | VA | Nottoway | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 6/9/2020 | 1/1/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-030/AG1-030_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-051 | TC1 | DP1 | Maysville 69 kV III |  | MC Solar, LLC | PA | Mercer | Withdrawn | Generation Interconnection | ATSI | 70.0 | 20.0 | 20.0 |  | Capacity | Storage | 7/18/2020 | 6/30/2022 | [5 empty] | 1/29/2025 | 7/18/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-051/AG1-051_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-060 | TC1 | PHASE 1 | Eldred 69 kV |  | ANTHRACITE RIDGE LLC | PA | Schuylkill | Withdrawn | Generation Interconnection | PPL | 174.8 | 174.8 | 25.7 |  | Capacity | Solar | 7/29/2020 | 5/31/2022 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-060/AG1-060_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-061 | TC1 | PHASE 1 | Laurel-Sharptown 69 kV |  | Deere Acres Solar LLC | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 109.3 | 109.3 | 65.58 |  | Capacity | Solar | 7/29/2020 | 12/31/2021 | [5 empty] | 6/27/2024 | 6/25/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-061/AG1-061_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-070 | TC1 | PHASE 3 | Bon Ayr 69 kV |  | Wood Duck Solar LLC | KY | Barren | Active | Generation Interconnection | EKPC | 45.0 | 45.0 | 32.7 |  | Capacity | Solar | 7/30/2020 | 6/1/2024 | [5 empty] | 2/25/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-071 | TC1 | PHASE 3 | Bon Ayr 69 kV |  | Wood Duck Solar LLC | KY | Barren | Active | Generation Interconnection | EKPC | 55.0 | 55.0 | 37.5 |  | Capacity | Solar | 7/30/2020 | 6/1/2024 | [5 empty] | 2/25/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-075 | TC1 | PHASE 1 | Purdy-Sapony 115 kV |  | Jarratt Solar, LLC | VA | Greensville | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 93.2 |  | Capacity | Solar | 7/31/2020 | 10/15/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-075/AG1-075_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-075/AG1-075_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-082 | TC1 | PHASE 3 | Ahoskie 34.5 kV |  | NC1 Ahoskie Central, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar,Storage,Hybrid | 7/31/2020 | 12/31/2021 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-082/AG1-082_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-082/AG1-082_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-083 | TC1 | PHASE 2 | Ahoskie 34.5 kV |  | NC-4 Ahoskie North, LLC | NC | Hertford | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar,Storage,Hybrid | 7/31/2020 | 12/31/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-083/AG1-083_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-083/AG1-083_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-090 | TC1 | PHASE 3 | Philipsburg 115 kV |  | CE-Black Moshannon OZ LLC | PA | Centre | Active | Generation Interconnection | PENELEC | 95.0 | 95.0 | 30.0 |  | Capacity | Solar,Storage,Hybrid | 8/1/2020 | 8/1/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-090/AG1-090_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-090/AG1-090_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-098 | TC1 | PHASE 3 | Briery-Clover 230 kV |  | Virginia Electric and Power Company | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 107.0 | 107.0 | 64.2 |  | Capacity | Solar | 8/18/2020 | 12/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-098/ag1-098_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-098/AG1-098_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-105 | TC1 | PHASE 3 | Mount Laurel-Barnes Junction 115 kV |  | Virginia Electric and Power Company | VA | Halifax | Active | Generation Interconnection | Dominion | 90.0 | 90.0 | 54.0 |  | Capacity | Solar | 8/27/2020 | 12/1/2024 | [5 empty] | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-105/AG1-105_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-105/AG1-105_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-106 | TC1 | PHASE 3 | Thelma 230 kV |  | Oak Solar, LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 323.0 | 23.0 | 16.0 |  | Capacity | Solar | 8/28/2020 | 6/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-106/AG1-106_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-106/AG1-106_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-109 | TC1 | PHASE 3 | Valley 138 kV |  | Decatur Storage LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 50.0 | 0.0 | 25.0 |  | Capacity | Storage | 8/31/2020 | 3/1/2022 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-109/AG1-109_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-109/AG1-109_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-118 | TC1 | PHASE 3 | Sugar Grove-Waterman 138kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-118/AG1-118_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-118/AG1-118_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-119 | TC1 | PHASE 1 | Wayne-Byron 345 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-119/AG1-119_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-120 | TC1 | PHASE 2 | Glidden-Cherry Valley 138 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 118.6 | 118.6 | 71.16 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-120/AG1-120_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-120/AG1-120_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-121 | TC1 | PHASE 1 | Kewanee-Streator 138 kV |  | Leeward Renewable Energy Development, LLC | IL | Bureau | Withdrawn | Generation Interconnection | ComEd | 294.7 | 294.7 | 51.9 |  | Capacity | Wind | 8/31/2020 | 12/31/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-121/AG1-121_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-123 | TC1 | PHASE 1 | Amherst 69 kV |  | Five Oaks Solar Project, LLC | VA | Amherst | Withdrawn | Generation Interconnection | AEP | 65.0 | 65.0 | 38.5 |  | Capacity | Solar | 8/31/2020 | 12/1/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-123/AG1-123_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-124 | TC1 | PHASE 3 | Gladstone 138 kV |  | Wild Rose Solar Project, LLC | VA | Nelson | Active | Generation Interconnection | AEP | 90.0 | 90.0 | 53.01 |  | Capacity | Solar | 8/31/2020 | 12/1/2024 | [5 empty] | 3/5/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-124/AG1-124_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-124/AG1-124_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-127 | TC1 | PHASE 3 | Crego Rd 138 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 190.0 | 95.1 | 57.1 |  | Capacity | Solar | 8/31/2020 | 12/29/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-127/AG1-127_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-127/AG1-127_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-133 | TC1 | PHASE 1 | North Anna-Ladysmith 500 kV |  | Virginia Electric and Power Company | VA | Spotsylvania | Withdrawn | Generation Interconnection | Dominion | 128.0 | 128.0 | 76.8 |  | Capacity | Solar | 9/2/2020 | 12/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-133/AG1-133_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-134 | TC1 | PHASE 1 | Kings Dominion DP 115 kV |  | Virginia Electric and Power Company | VA | King William | Withdrawn | Generation Interconnection | Dominion | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/2/2020 | 12/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-134/AG1-134_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-135 | TC1 | PHASE 3 | Garner-Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Richmond | Active | Generation Interconnection | Dominion | 60.0 | 60.0 | 36.0 |  | Capacity | Solar | 9/3/2020 | 12/1/2024 |  |  |  | 12/1/2025 | 2/1/2026 | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-135/AG1-135_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-135/AG1-135_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/ag1_135_csa.pdf | Posted
AG1-146 | TC1 | PHASE 3 | Garner DP-Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Lancaster | Active | Generation Interconnection | Dominion | 30.0 | 30.0 | 18.0 |  | Capacity | Solar | 9/9/2020 | 12/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-146/AG1-146_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-146/AG1-146_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-147 | TC1 | PHASE 3 | Garner DP-Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Lancaster | Active | Generation Interconnection | Dominion | 100.0 | 70.0 | 42.0 |  | Capacity | Solar | 9/9/2020 | 12/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-147/AG1-147_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-147/AG1-147_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-151 | TC1 | PHASE 1 | Endless Caverns 115 kV |  | Prospect Power, LLC | VA | Rockingham | Withdrawn | Generation Interconnection | Dominion | 300.0 | 100.0 | 100.0 |  | Capacity | Storage | 9/10/2020 | 10/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-151/AG1-151_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-153 | TC1 | PHASE 3 | Heritage 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 75.0 | 75.0 | 30.0 |  | Capacity | Storage | 9/10/2020 | 12/1/2023 |  |  |  | 6/22/2028 | 7/8/2028 | 2/20/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-153/AG1-153_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-153/AG1-153_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started | https://www.pjm.com//pjmfiles/pub/planning/project-queues/csa/ag1_153_csa.pdf | Posted
AG1-154 | TC1 | PHASE 3 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Active | Generation Interconnection | Dominion | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 9/10/2020 | 12/1/2023 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-154/AG1-154_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-154/AG1-154_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-160 | TC1 | PHASE 1 | Rogers Road 500 kV |  | Virginia Electric and Power Company | VA | Greensville | Withdrawn | Generation Interconnection | Dominion | 75.0 | 75.0 | 30.0 |  | Capacity | Storage | 9/11/2020 | 12/1/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-160/AG1-160_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-166 | TC1 | PHASE 3 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 6.0 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-166/AG1-166_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-166/AG1-166_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-167 | TC1 | PHASE 3 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Active | Generation Interconnection | Dominion | 35.0 | 15.0 | 4.5 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-167/AG1-167_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-167/AG1-167_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-168 | TC1 | PHASE 3 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Active | Generation Interconnection | Dominion | 50.0 | 15.0 | 4.5 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 4/22/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-168/AG1-168_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-168/AG1-168_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-169 | TC1 | PHASE 2 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Withdrawn | Generation Interconnection | Dominion | 15.0 | 15.0 | 4.5 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-169/AG1-169_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-169/AG1-169_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-170 | TC1 | PHASE 2 | Lone Pine 115 kV |  | NW-Rocky Ford LLC | VA | Nottoway | Withdrawn | Generation Interconnection | Dominion | 10.0 | 10.0 | 3.0 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-170/AG1-170_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-170/AG1-170_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-174 | TC1 | PHASE 1 | Hopewell-Surry 230 kV |  | SR-Colonial Trail LLC | VA | Surry | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/16/2020 | 10/15/2021 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-174/AG1-174_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-178 | TC1 | PHASE 1 | Carson-Suffolk 500 kV |  | Cabin Point Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 500.0 | 500.0 | 324.94 |  | Capacity | Solar | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-178/AG1-178_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-179 | TC1 | PHASE 1 | Brunswick-Gasburg 69 kV |  | Merchant Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 50.0 | 50.0 | 33.66 |  | Capacity | Solar | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-179/AG1-179_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-180 | TC1 | PHASE 1 | Brunswick-Gasburg 69 kV |  | Merchant Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 50.0 | 0.0 | 16.4 |  | Capacity | Storage | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-180/AG1-180_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-181 | TC1 | PHASE 1 | Pamplin-Chase City 115 kV |  | Drakes Branch Solar, LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 101.09 |  | Capacity | Solar | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-181/AG1-181_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-184 | TC1 | PHASE 1 | Carson-Suffolk 500 kV |  | Cabin Point Solar, LLC | VA | Sussex | Withdrawn | Generation Interconnection | Dominion | 500.0 | 0.0 | 175.06 |  | Capacity | Storage | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-184/AG1-184_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-185 | TC1 | PHASE 1 | Pamplin-Chase City 115 kV |  | Drakes Branch Solar, LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 150.0 | 0.0 | 48.91 |  | Capacity | Storage | 9/17/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-185/AG1-185_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-194 | TC1 | PHASE 2 | Nuttall 138 kV |  | Keeneys Creek Solar I, LLC | WV | Fayette | Withdrawn | Generation Interconnection | AEP | 79.0 | 79.0 | 27.0 |  | Capacity | Solar,Storage,Hybrid | 9/18/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-194/AG1-194_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-194/AG1-194_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-195 | TC1 | PHASE 1 | Valley 230 kV |  | Hecate Energy Weyers Cave LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 150.0 |  | Capacity | Solar,Storage,Hybrid | 9/18/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-195/AG1-195_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-196 | TC1 | PHASE 1 | Grottoes 115 kV |  | Hecate Energy Grottoes Solar LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 150.0 |  | Capacity | Solar,Storage,Hybrid | 9/18/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-196/AG1-196_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-199 | TC1 | PHASE 1 | Allen Junction 345 kV |  | Occasio Power Management LLC | OH | Lucas | Withdrawn | Generation Interconnection | ATSI | 300.0 | 300.0 | 300.0 |  | Capacity | Storage | 9/18/2020 | 6/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-199/AG1-199_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-219 | TC1 | PHASE 1 | Layland 69 kV |  | Fayette Solar I, LLC | WV | Fayette | Withdrawn | Generation Interconnection | AEP | 75.0 | 75.0 | 39.5 |  | Capacity | Solar,Storage,Hybrid | 9/23/2020 | 12/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-219/AG1-219_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-224 | TC1 | PHASE 1 | Pendleton-Tanners Creek 138 kV |  | RUSH SOLAR PROJECT II, LLC | IN | Fayette | Withdrawn | Generation Interconnection | AEP | 210.0 | 210.0 | 126.0 |  | Capacity | Solar | 9/24/2020 | 12/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-224/AG1-224_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-225 | TC1 | PHASE 1 | Adams 138 kV |  | ADAMS SOLAR PROJECT, LLC | IN | Adams | Withdrawn | Generation Interconnection | AEP | 346.0 | 346.0 | 207.0 |  | Capacity | Solar | 9/24/2020 | 12/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-225/AG1-225_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-226 | TC1 | PHASE 3 | Eugene-Dequine 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 450.0 | 450.0 | 142.0 |  | Capacity | Solar | 9/24/2020 | 6/1/2024 | [5 empty] | 4/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-226/AG1-226_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-226/AG1-226_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-236 | TC1 | PHASE 3 | Lanesville-Brokaw 345 kV |  | Invenergy Wind Development LLC | IL | Logan | Active | Generation Interconnection | ComEd | 380.0 | 180.0 | 23.4 |  | Capacity | Wind | 9/25/2020 | 12/31/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-236/AG1-236_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-236/AG1-236_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-272 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 6.0 |  | Capacity | Solar,Storage,Hybrid | 9/29/2020 | 3/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-272/AG1-272_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-272/AG1-272_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-273 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 6.0 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-273/AG1-273_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-273/AG1-273_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-274 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 6.0 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-274/AG1-274_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-274/AG1-274_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-277 | TC1 | PHASE 1 | Salem-Beacon Power 69 kV |  | LU-Tank LLC | PA | Luzerne | Withdrawn | Generation Interconnection | PPL | 40.0 | 40.0 | 32.0 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-277/AG1-277_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-277/AG1-277_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-278 | TC1 | PHASE 2 | Salem-Beacon Power 69 kV |  | LU-Tank LLC | PA | Luzerne | Withdrawn | Generation Interconnection | PPL | 60.0 | 20.0 | 15.42 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-278/AG1-278_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-278/AG1-278_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-279 | TC1 | PHASE 1 | Salem-Beacon Power 69 kV |  | LU-Tank LLC | PA | Luzerne | Withdrawn | Generation Interconnection | PPL | 80.0 | 20.0 | 15.42 |  | Capacity | Solar,Storage,Hybrid | 9/28/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-279/AG1-279_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-279/AG1-279_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-284 | TC1 | PHASE 1 | Fork Union 115 kV |  | Weber Solar, LLC | VA | Fluvanna | Withdrawn | Generation Interconnection | Dominion | 70.0 | 70.0 | 42.0 |  | Capacity | Solar | 9/28/2020 | 9/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-284/AG1-284_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-285 | TC1 | PHASE 3 | Chase City-Central 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 125.0 | 125.0 | 75.0 |  | Capacity | Solar | 9/28/2020 | 12/1/2024 | [5 empty] | 2/28/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-285/AG1-285_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-285/AG1-285_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-288 | TC1 | PHASE 1 | Lake of the Woods DP-Wilderness DP 115 kV |  | Locust Grove Solar, LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 96.59 |  | Capacity | Solar | 9/28/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-288/AG1-288_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-289 | TC1 | PHASE 1 | Lake of the Woods DP-Wilderness DP 115 kV |  | Locust Grove Solar, LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 150.0 | 0.0 | 53.41 |  | Capacity | Storage | 9/28/2020 | 6/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-289/AG1-289_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-297 | TC1 | PHASE 3 | Hanna-Tanners Creek 345 kV |  | Hecate Energy Blue River LLC | IN | Shelby | Active | Generation Interconnection | AEP | 300.0 | 300.0 | 75.0 |  | Capacity | Storage | 9/29/2020 | 12/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-297/AG1-297_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-297/AG1-297_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-298 | TC1 | PHASE 2 | Calumet-Burnham 345 kV |  | Big Shoulders Storage LLC | IL | Cook | Withdrawn | Generation Interconnection | ComEd | 500.0 | 500.0 | 500.0 |  | Capacity | Storage | 9/29/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-298/AG1-298_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-298/AG1-298_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-305 | TC1 | PHASE 2 | Louisa-North Anna 230 kV |  | Two Oaks Solar, LLC | VA | Louisa | Withdrawn | Generation Interconnection | Dominion | 63.0 | 63.0 | 37.8 |  | Capacity | Solar | 9/29/2020 | 7/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-305/AG1-305_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-305/AG1-305_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-306 | TC1 | PHASE 1 | Fawkes-Dale 138 kV |  | AEUG Boonesborough Solar, LLC | KY | Madison | Withdrawn | Generation Interconnection | EKPC | 65.0 | 65.0 | 39.0 |  | Capacity | Solar | 9/29/2020 | 10/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-306/AG1-306_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-308 | TC1 | PHASE 1 | Shawville-Philipsburg 34.5 kV |  | Morrisdale Solar I, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | PENELEC | 19.9 | 19.9 | 8.3 |  | Capacity | Solar | 9/29/2020 | 8/1/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-308/AG1-308_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-319 | TC1 | PHASE 1 | Napoleon Muni 138 kV |  | CG Henry County LLC | OH | Henry | Withdrawn | Generation Interconnection | AMPT | 105.0 | 65.0 | 39.0 |  | Capacity | Solar | 9/30/2020 | 11/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-319/AG1-319_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-319/AG1-319_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-320 | TC1 | PHASE 3 | Glendale-Stephensburg 69 kV |  | CPV Stonecrop Solar, LLC | KY | Hardin | Active | Generation Interconnection | EKPC | 82.0 | 82.0 | 54.8 |  | Capacity | Solar | 9/30/2020 | 10/1/2023 | [5 empty] | 2/24/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-321 | TC1 | PHASE 1 | Dresden-Pontiac Midpoint 345 kV |  | CPV Prairie Dock Solar, LLC | IL | Livingston | Withdrawn | Generation Interconnection | ComEd | 200.0 | 200.0 | 126.4 |  | Capacity | Solar | 9/30/2020 | 10/1/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-321/AG1-321_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-323 | TC1 | PHASE 3 | Blue Jacket 138 kV |  | Hodson GreenDefine Blue Jacket LLC | OH | Logan | Active | Generation Interconnection | Dayton | 40.0 | 40.0 | 40.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 9/1/2023 | [5 empty] | 3/3/2025 |  |  |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-323/AG1-323_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-341 | TC1 | PHASE 3 | Summer Shade 161 kV |  | Naturgy Candela DevCo LLC | KY | Metcalfe | Active | Generation Interconnection | EKPC | 106.0 | 106.0 | 63.6 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/15/2023 | [5 empty] | 2/7/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-342 | TC1 | PHASE 3 | Dryburg 115 kV |  | Staunton Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 36.0 | 36.0 | 21.6 |  | Capacity | Solar | 9/30/2020 | 12/1/2023 | [5 empty] | 2/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-342/AG1-342_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-342/AG1-342_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-343 | TC1 | PHASE 2 | Boykins-Murphy 115 kV |  | White Oak Solar Facility LLC | VA | Southampton | Withdrawn | Generation Interconnection | Dominion | 62.5 | 62.5 | 35.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-343/AG1-343_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-343/AG1-343_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-346 | TC1 | PHASE 2 | Mount Jackson DP 115 kV |  | Ginger Gold Solar LLC | VA | Shenandoah | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/30/2020 | 12/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-346/AG1-346_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-346/AG1-346_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-353 | TC1 | PHASE 1 | Green County-Marion County 161 kV |  | Creekview Solar, LLC | KY | Taylor | Withdrawn | Generation Interconnection | EKPC | 98.0 | 98.0 | 58.8 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-353/AG1-353_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-353/AG1-353_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-354 | TC1 | PHASE 3 | Summershade-Green County 161 kV |  | Exie Solar, LLC | KY | Green | Active | Generation Interconnection | EKPC | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 2/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-354/AG1-354_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-354/AG1-354_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-359 | TC1 | PHASE 1 | Fentress 230 kV |  | Fentress Energy Storage, LLC | VA | City of Chesapeake | Withdrawn | Generation Interconnection | Dominion | 127.5 | 127.5 | 127.5 |  | Capacity | Storage | 9/30/2020 | 12/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-359/AG1-359_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-364 | TC1 | PHASE 1 | Deep Creek 115 kV |  | Crossroads Energy Storage LLC | VA | City of Chesapeake | Withdrawn | Generation Interconnection | Dominion | 100.0 | 100.0 | 40.0 |  | Capacity | Storage | 9/30/2020 | 11/30/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-364/AG1-364_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-367 | TC1 | PHASE 3 | DeSoto 345 kV |  | Esker Solar Park II LLC | IN | Delaware | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/30/2020 | 10/31/2024 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-367/AG1-367_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-367/AG1-367_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-371 | TC1 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 600.0 | 0.0 | 30.0 |  | Capacity | Storage | 9/30/2020 | 11/1/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-371/AG1-371_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-373 | TC1 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 600.0 | 0.0 | 10.0 |  | Capacity | Storage | 9/30/2020 | 11/1/2024 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-373/AG1-373_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-374 | TC1 | PHASE 3 | Blue Mound 345 kV |  | Deriva Energy Solar, LLC | IL | McLean | Active | Generation Interconnection | ComEd | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 9/30/2020 | 12/1/2024 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-374/AG1-374_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-374/AG1-374_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-375 | TC1 | PHASE 3 | Sorenson-Desoto 345 kV |  | Blackford County Solar Park LLC | IN | Blackford | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/30/2020 | 10/31/2024 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-375/AG1-375_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-375/AG1-375_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-377 | TC1 | PHASE 3 | Philipsburg 115 kV |  | CE-Black Moshannon OZ LLC | PA | Centre | Active | Generation Interconnection | PENELEC | 115.0 | 20.0 | 6.0 |  | Capacity | Solar | 9/30/2020 | 8/15/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-377/AG1-377_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-377/AG1-377_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-378 | TC1 | PHASE 3 | Philipsburg 115 kV |  | CE-Black Moshannon OZ LLC | PA | Centre | Active | Generation Interconnection | PENELEC | 135.0 | 20.0 | 6.0 |  | Capacity | Solar | 9/30/2020 | 8/15/2023 | [5 empty] | 1/31/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-378/AG1-378_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-378/AG1-378_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-379 | TC1 | PHASE 1 | Minonk 345 kV |  | Minonk Solar, LLC | IL | Woodford | Withdrawn | Generation Interconnection | ComEd | 200.0 | 200.0 | 137.2 |  | Capacity | Solar | 9/30/2020 | 8/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-379/AG1-379_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-384 | TC1 | PHASE 2 | Twitty's Creek 115 kV |  | CV-Tollhouse LLC | VA | Charlotte | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 6.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-384/AG1-384_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-384/AG1-384_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-392 | TC1 | PHASE 1 | Gold 115 kV I |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 30.0 | 30.0 | 18.0 |  | Capacity | Solar | 9/30/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392/AG1-392_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392/AG1-392_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-392A | TC1 | PHASE 1 | Gold 115 kV II |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 60.0 | 30.0 | 18.0 |  | Capacity | Solar | 10/1/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392A/AG1-392A_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392A/AG1-392A_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-392B | TC1 | PHASE 1 | Gold 115 kV III |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 75.0 | 15.0 | 9.0 |  | Capacity | Solar | 10/1/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392B/AG1-392B_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392B/AG1-392B_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-392C | TC1 | PHASE 1 | Gold 115 kV IV |  | PO-Cowburn LLC | PA | Potter | Withdrawn | Generation Interconnection | PENELEC | 90.0 | 15.0 | 9.0 |  | Capacity | Solar | 10/1/2020 | 6/1/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-392C/AG1-392C_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-392C/AG1-392C_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-393 | TC1 | PHASE 3 | Fort Pickett DP 34.5 kV |  | DW-Lew Jones LLC | VA | Dinwiddie | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/30/2020 | 3/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-393/AG1-393_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-393/AG1-393_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-394 | TC1 | PHASE 3 | Boykins 34.5 kV |  | SH-Mehrrin LLC | VA | Southampton | Active | Generation Interconnection | Dominion | 14.2 | 14.2 | 5.0 |  | Capacity | Solar | 9/30/2020 | 3/1/2022 | [5 empty] | 2/18/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-394/AG1-394_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-394/AG1-394_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-399 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 300.0 | 300.0 | 52.8 |  | Capacity | Wind | 9/30/2020 | 9/24/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-399/AG1-399_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-400 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 150.0 | 150.0 | 150.0 |  | Capacity | Storage | 9/30/2020 | 9/24/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-400/AG1-400_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-402 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 150.0 | 150.0 | 150.0 |  | Capacity | Storage | 9/30/2020 | 9/24/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-402/AG1-402_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-404 | TC1 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Withdrawn | Generation Interconnection | ComEd | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 9/30/2020 | 9/24/2024 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-404/AG1-404_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-405 | TC1 | PHASE 3 | Walnut Grove-Asahi 69 kV |  | Sunflower Prairie Solar Project, LLC | KY | McLean | Active | Generation Interconnection | EKPC | 57.0 | 57.0 | 34.2 |  | Capacity | Solar | 9/30/2020 | 9/25/2024 | [5 empty] | 2/24/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-406 | TC1 | PHASE 3 | Walnut Grove-Asahi 69 kV |  | Sunflower Prairie Solar Project, LLC | KY | McLean | Active | Generation Interconnection | EKPC | 79.0 | 22.0 | 22.0 |  | Capacity | Storage | 9/30/2020 | 9/25/2024 | [5 empty] | 2/12/2025 |  |  |  | Not Applicable |  | Not Applicable |  | In Progress |  | Not Started |  | Not Started
AG1-410 | TC1 | PHASE 3 | Maddox Creek-RP Mone 345 kV |  | Butterfly Meadows Solar Project, LLC | OH | Van Wert | Active | Generation Interconnection | AEP | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 9/30/2020 | 9/25/2024 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-410/AG1-410_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-410/AG1-410_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-411 | TC1 | PHASE 3 | Maddox Creek-RP Mone 345 kV |  | Butterfly Meadows Solar Project, LLC | OH | Van Wert | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 9/30/2020 | 9/25/2024 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-411/AG1-411_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-411/AG1-411_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-412 | TC1 | PHASE 2 | Ladysmith CT-Mine Road 230 kV |  | Matta Grid, LLC | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 200.0 | 200.0 | 80.0 |  | Capacity | Storage | 9/30/2020 | 12/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-412/AG1-412_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-412/AG1-412_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-421 | TC1 | PHASE 1 | Lexington-Dooms 230 kV |  | Leeward Renewable Energy Development, LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-421/AG1-421_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-422 | TC1 | PHASE 1 | Lexington-Dooms 230 kV |  | Leeward Renewable Energy Development, LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 50.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/30/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-422/AG1-422_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-423 | TC1 | PHASE 1 | Byron-Wayne 345 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Withdrawn | Generation Interconnection | ComEd | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-423/AG1-423_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-424 | TC1 | PHASE 1 | Sowers 138 kV |  | Leeward Renewable Energy Development, LLC | IN | Allen | Withdrawn | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 6/24/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-424/AG1-424_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-425 | TC1 | PHASE 1 | Groton 138 kV |  | Wheatsborough Solar, LLC | OH | Erie | Withdrawn | Generation Interconnection | ATSI | 125.0 | 0.0 | 20.0 |  | Capacity | Storage | 9/30/2020 | 10/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-425/AG1-425_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-426 | TC1 | PHASE 1 | Bremo-Scottsville 138 kV |  | Riverstone Solar, LLC | VA | Buckingham | Withdrawn | Generation Interconnection | AEP | 149.5 | 0.0 | 17.0 |  | Capacity | Storage | 9/30/2020 | 10/31/2023 | [5 empty] | 8/2/2024 | 8/2/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-426/AG1-426_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-427 | TC1 | PHASE 2 | Chase City-Drakes Branch 115 kV |  | ACE Development Company II, LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 118.56 | 118.56 | 71.136 |  | Capacity | Solar | 9/30/2020 | 12/31/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-427/AG1-427_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-427/AG1-427_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-428 | TC1 | PHASE 2 | Danieltown DP–Brunswick 69 kV |  | ACE Development Company II, LLC | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 46.8 | 46.8 | 28.08 |  | Capacity | Solar | 9/30/2020 | 12/31/2024 | [5 empty] | 2/5/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-428/AG1-428_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-428/AG1-428_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-432 | TC1 | PHASE 1 | Curdsville DP-Willis Mt. 115 kV |  | ACE Development Company II, LLC | VA | Buckingham | Withdrawn | Generation Interconnection | Dominion | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-432/AG1-432_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-433 | TC1 | PHASE 3 | Keystone-DeSoto 345 kV |  | RWE Renewables Development, LLC | IN | Blackford | Active | Generation Interconnection | AEP | 300.0 | 100.0 | 17.6 |  | Capacity | Wind | 9/30/2020 | 12/31/2023 | [5 empty] | 3/11/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-433/AG1-433_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-433/AG1-433_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-434 | TC1 | DP2 | Electric Junction-Nelson 345 kV |  | RWE Renewables Development, LLC | IL | Lee | Withdrawn | Generation Interconnection | ComEd | 175.0 | 175.0 | 35.2 |  | Capacity | Wind | 9/30/2020 | 12/31/2023 | [5 empty] | 2/3/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-434/AG1-434_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-434/AG1-434_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-435 | TC1 | PHASE 1 | Kewanee-Hennepin 138 kV |  | RWE Clean Energy Development, LLC | IL | Bureau | Withdrawn | Generation Interconnection | ComEd | 150.0 | 150.0 | 35.2 |  | Capacity | Wind | 9/30/2020 | 12/31/2023 | [5 empty] | 2/21/2025 | 2/21/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-435/AG1-435_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-435/AG1-435_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-436 | TC1 | PHASE 3 | Olive-University Park 345 kV |  | RWE Solar Development, LLC | IN | LaPorte | Active | Generation Interconnection | AEP | 250.0 | 125.0 | 75.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 3/4/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-436/AG1-436_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-436/AG1-436_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-437 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE Solar Development, LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-437/AG1-437_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-437/AG1-437_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-438 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE Solar Development, LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-438/AG1-438_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-438/AG1-438_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-439 | TC1 | PHASE 2 | Chinquapin 230 kV |  | RWE Solar Development, LLC | NC | Edgecombe | Withdrawn | Generation Interconnection | Dominion | 250.0 | 250.0 | 150.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-439/AG1-439_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-439/AG1-439_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-440 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | RWE Solar Development, LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 75.0 | 75.0 | 45.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-440/AG1-440_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-441 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | RWE Solar Development, LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 75.0 | 75.0 | 45.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-441/AG1-441_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-442 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE Solar Development, LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 135.0 | 35.0 | 35.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-442/AG1-442_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-442/AG1-442_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-443 | TC1 | PHASE 2 | Cashie-Earleys 230 kV |  | RWE Solar Development, LLC | NC | Bertie | Withdrawn | Generation Interconnection | Dominion | 135.0 | 35.0 | 35.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-443/AG1-443_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-443/AG1-443_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-444 | TC1 | PHASE 2 | Chinquapin 230 kV |  | RWE Solar Development, LLC | NC | Edgecombe | Withdrawn | Generation Interconnection | Dominion | 330.0 | 80.0 | 80.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-444/AG1-444_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-444/AG1-444_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-445 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | Fitzsimons Solar, LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 101.0 | 26.0 | 26.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 11/8/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-445/AG1-445_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-446 | TC1 | PHASE 1 | Palmer Springs 115 kV |  | RWE Solar Development, LLC | VA | Mecklenburg | Withdrawn | Generation Interconnection | Dominion | 101.0 | 26.0 | 26.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-446/AG1-446_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-447 | TC1 | PHASE 3 | Olive-University Park 345 kV |  | RWE Solar Development, LLC | IN | LaPorte | Active | Generation Interconnection | AEP | 305.0 | 55.0 | 55.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-447/AG1-447_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-447/AG1-447_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-449 | TC1 | PHASE 2 | Rawlings-Carson 500 kV |  | RWE Solar Development, LLC | VA | Dinwiddie | Withdrawn | Generation Interconnection | Dominion | 436.0 | 122.0 | 122.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-449/AG1-449_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-449/AG1-449_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-450 | TC1 | PHASE 3 | Airey-Vienna 69 kV II |  | RWE Solar Development, LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 125.0 | 25.0 | 25.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 1/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-450/AG1-450_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-450/AG1-450_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-451 | TC1 | PHASE 2 | Curdsville DP-Willis Mt. 115 kV |  | RWE Solar Development, LLC | VA | Buckingham | Withdrawn | Generation Interconnection | Dominion | 120.0 | 20.0 | 20.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-451/AG1-451_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-451/AG1-451_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-453 | TC1 | PHASE 1 | Guardian 138 kV |  | RWE Solar Development, LLC | IN | Noble | Withdrawn | Generation Interconnection | AEP | 140.0 | 140.0 | 84.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-453/AG1-453_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-454 | TC1 | PHASE 1 | Guardian 138 kV |  | RWE Solar Development, LLC | IN | Noble | Withdrawn | Generation Interconnection | AEP | 190.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-454/AG1-454_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-456 | TC1 | PHASE 1 | Wildcat 138 kV |  | Willowbrook Solar I, LLC | OH | Highland | Withdrawn | Generation Interconnection | AEP | 180.0 | 30.0 | 30.0 |  | Capacity | Storage | 9/30/2020 | 12/31/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-456/AG1-456_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-460 | TC1 | PHASE 3 | Kincaid-Pana 345 kV |  | Black Diamond Solar Power, LLC | IL | Christian | Active | Generation Interconnection | ComEd | 329.0 | 30.0 | 12.0 |  | Capacity | Storage | 9/30/2020 | 6/1/2022 | [5 empty] | 3/14/2025 |  | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-460/AG1-460_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-460/AG1-460_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-462 | TC1 | PHASE 3 | Cordova 345 kV |  | Gipper Solar Farm, LLC | IL | Whiteside | Active | Generation Interconnection | ComEd | 255.0 | 255.0 | 153.0 |  | Capacity | Solar | 10/1/2020 | 10/1/2023 | [5 empty] | 2/27/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-462/AG1-462_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-462/AG1-462_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-471 | TC1 | PHASE 3 | Up Church-Wayne County 69 kV |  | Barrelhead Solar, LLC | KY |  | Active | Generation Interconnection | EKPC | 54.0 | 54.0 | 32.4 |  | Capacity | Solar | 9/30/2020 | 10/2/2023 | [5 empty] | 2/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-471/AG1-471_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-471/AG1-471_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-473 | TC1 | PHASE 1 | Shingletown-Lewistown 230 kV |  | North Corners Energy, LLC | PA | Huntingdon | Withdrawn | Generation Interconnection | PENELEC | 53.9 | 53.9 | 32.34 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-473/AG1-473_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-473/AG1-473_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-483 | TC1 | FINAL AGREEMENT | Dickerson 230 kV | Fourth Quarter | Fourth Quarter BESS, LLC | MD | Montgomery | EP | Generation Interconnection | PEPCO | 500.0 | 500.0 | 500.0 |  | Capacity | Storage | 10/1/2020 | 6/1/2024 | 2/1/2030 |  |  | 12/15/2029 | 11/1/2029 | 4/30/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-483/AG1-483_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-483/AG1-483_imp_PHASE_2.htm | Posted |  | Not Required |  | Not Started |  | Not Started
AG1-488 | TC1 | PHASE 1 | Marion Co 161 kV |  | BrightNight, LLC | KY | Marion | Withdrawn | Generation Interconnection | EKPC | 70.0 | 70.0 | 42.0 |  | Capacity | Solar | 9/30/2020 | 9/30/2022 | [5 empty] | 6/24/2024 | 6/21/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-488/AG1-488_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-494 | TC1 | PHASE 3 | Boxwood-Riverville 138 kV |  | Mainspring Grid, LLC | VA | Amherst | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 9/30/2020 | 12/1/2023 | [5 empty] | 3/12/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-494/AG1-494_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-494/AG1-494_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-497 | TC1 | PHASE 2 | Cartanza 230 kV |  | Morgan Branch Solar I, LLC | DE | Kent | Withdrawn | Generation Interconnection | DPL | 120.0 | 120.0 | 84.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/30/2023 | [5 empty] | 1/24/2025 | 1/22/2025 | Customer Initiated Withdrawal | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-497/AG1-497_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-497/AG1-497_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-502 | TC1 | PHASE 2 | Oak Green 115 kV |  | Oak Green Solar LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 80.0 | 80.0 | 64.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/30/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-502/AG1-502_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-503 | TC1 | PHASE 2 | Oak Green 115 kV |  | Oak Green Solar LLC | VA | Orange | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 16.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 6/30/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met |  | Not Applicable | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-503/AG1-503_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-505 | TC1 | PHASE 1 | Rawlings-Clover 500 kV |  | Bellflower Holdings, LLC | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 9/30/2020 | 7/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-505/AG1-505_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-506 | TC1 | PHASE 1 | Rawlings-Clover 500 kV |  | Bellflower Holdings, LLC | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 9/30/2020 | 7/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-506/AG1-506_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-522 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-522/AG1-522_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-522/AG1-522_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-523 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 600.0 | 300.0 | 180.0 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-523/AG1-523_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-523/AG1-523_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-524 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 900.0 | 300.0 | 180.0 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-524/AG1-524_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-524/AG1-524_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-525 | TC1 | PHASE 2 | Sullivan-Rockport 765 kV |  | PJM Solar Devco I, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 1200.0 | 300.0 | 180.0 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-525/AG1-525_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-525/AG1-525_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-526 | TC1 | PHASE 3 | West Garrard 345 kV |  | PJM Solar Devco I, LLC | KY | Garrard | Active | Generation Interconnection | EKPC | 222.0 | 222.0 | 133.2 |  | Capacity | Solar | 9/30/2020 | 6/1/2023 | [5 empty] | 2/21/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-526/AG1-526_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-526/AG1-526_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-531 | TC1 | PHASE 1 | Poolesville-Winchester 230 kV |  | TCE Virginia Development, LLC | VA | Isle of Wight | Withdrawn | Generation Interconnection | Dominion | 54.0 | 54.0 | 32.4 |  | Capacity | Solar | 9/30/2020 | 12/12/2023 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-531/AG1-531_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-536 | TC1 | PHASE 3 | Garner-Northern Neck 115 kV |  | Virginia Electric and Power Company | VA | Richmond | Active | Generation Interconnection | Dominion | 75.0 | 75.0 | 32.0 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-536/AG1-536_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-536/AG1-536_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-537 | TC1 | PHASE 2 | Barterbrook-Stuarts Draft 115 kV |  | Chestnut Storage, LLC | VA | Augusta | Withdrawn | Generation Interconnection | Dominion | 75.0 | 75.0 | 32.0 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-537/AG1-537_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-537/AG1-537_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-538 | TC1 | PHASE 1 | Remington-Gordonsville 230 kV |  | Longleaf Storage, LLC | VA | Culpeper | Withdrawn | Generation Interconnection | Dominion | 75.0 | 75.0 | 32.0 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-538/AG1-538_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-539 | TC1 | PHASE 1 | Grit DP-Perth 115 kV |  | Sourbark Storage, LLC | VA | Pittsylvania | Withdrawn | Generation Interconnection | Dominion | 75.0 | 75.0 | 32.0 |  | Capacity | Storage | 9/30/2020 | 10/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-539/AG1-539_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-547 | TC1 | PHASE 1 | Mount Airy-Chatham 69 kV |  | Curie Solar, LLC | VA | Pittsylvania | Withdrawn | Generation Interconnection | Dominion | 50.0 | 50.0 | 32.54 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 10/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-547/AG1-547_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG1-548 | TC1 | PHASE 3 | Erie South-Union City 115 kV |  | French Creek Energy, LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 150.0 | 150.0 | 45.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 10/31/2022 | [5 empty] | 3/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-548/AG1-548_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-548/AG1-548_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-549 | TC1 | PHASE 1 | Keystone 230 kV |  | Plum Creek Energy, LLC | PA | Armstrong | Withdrawn | Generation Interconnection | PENELEC | 100.0 | 100.0 | 85.0 |  | Capacity | Solar,Storage,Hybrid | 9/30/2020 | 10/31/2022 | [5 empty] | 1/27/2025 | 1/22/2025 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-549/AG1-549_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-549/AG1-549_imp_PHASE_2.htm | Posted |  | Not Started |  | Not Started |  | Not Started
AG1-551 | TC1 | PHASE 3 | Parmele 12.5 kV |  | Parnell Solar, LLC | NC | Martin | Active | Generation Interconnection | Dominion | 19.99 | 19.99 | 13.1 |  | Capacity | Solar | 9/30/2020 | 10/15/2023 | [5 empty] | 2/7/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-551/AG1-551_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-551/AG1-551_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-552 | TC1 | PHASE 3 | Carolina 13.2 kV |  | Ray Solar, LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 18.0 | 18.0 | 12.2 |  | Capacity | Solar | 9/30/2020 | 10/15/2023 | [5 empty] | 2/25/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-552/AG1-552_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-552/AG1-552_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-553 | TC1 | PHASE 3 | Cordova 345 kV |  | Beacon Solar, LLC | IL | Rock Island | Active | Generation Interconnection | ComEd | 260.0 | 260.0 | 0.0 |  | Energy | Solar | 9/30/2020 | 12/29/2023 | [5 empty] | 3/24/2025 |  |  | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-553/AG1-553_imp_PHASE_1.htm | Posted | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_2/AG1-553/AG1-553_imp_PHASE_2.htm | Posted |  | In Progress |  | Not Started |  | Not Started
AG1-556 | TC1 | PHASE 1 | Lexington 115 kV |  | Sand Dragon Energy LLC | VA | Rockbridge | Withdrawn | Generation Interconnection | Dominion | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 9/30/2020 | 6/1/2024 | [5 empty] | 6/27/2024 | 6/24/2024 | Customer Milestone Not Met | https://www.pjm.com//pjmfiles/pub/planning/project-queues/TC1/PHASE_1/AG1-556/AG1-556_imp_PHASE_1.htm | Posted |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-005 | TC2 | PHASE 1 | Garner-Lancaster 115 kV |  | Waller Solar I, LLC | VA | Lancaster | Active | Generation Interconnection | Dominion | 196.0 | 20.0 | 8.4 |  | Capacity | Solar | 10/2/2020 | 12/31/2022 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-008 | TC2 | PHASE 1 | Erie South-Warren 230 kV |  | Blatche Solar, LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 60.0 | 60.0 | 40.2 |  | Capacity | Solar | 10/8/2020 | 3/30/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-009 | TC2 | PHASE 1 | Erie South-Warren 230 kV II |  | Blatche Solar, LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 80.0 | 20.0 | 12.9 |  | Capacity | Solar | 10/8/2020 | 3/30/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-010 | TC2 | PHASE 1 | Peninsula-Whealton 115 kV | Hampton BESS 3 | Delorean Power LLC dba Lightshift Energy | VA | City of Hampton | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 75.96 |  | Capacity | Storage | 10/9/2020 | 1/1/2023 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-014 | TC2 | PHASE 1 | Meadow Lake 345 kV |  | Black Prairie Storage LLC | IN | White | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 10/19/2020 | 10/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-016 | TC2 | PHASE 1 | Oyster Creek-Whitings 34.5 kV |  | Lacey Holding / Ocean View Acres | NJ | Ocean | Active | Generation Interconnection | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Solar | 10/20/2020 | 12/17/2021 | [5 empty] | 3/20/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-020 | TC2 | PHASE 1 | Arnolds Corner 34.5 kV | Arnolds Corner Energy Storage | Arnold Corner Energy Storage 1 LLC | VA | King George | Active | Generation Interconnection | Dominion | 7.0 | 7.0 | 2.8 |  | Capacity | Storage | 10/23/2020 | 12/30/2022 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-029 | TC2 | PHASE 1 | Forest G. Hipple-Collingwood 345 kV |  | Southern Pike Solar LLC | IN | Noble | Active | Generation Interconnection | AEP | 300.0 | 300.0 | 39.0 |  | Capacity | Solar | 10/23/2020 | 6/1/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-035 | TC2 | APPLICATION REVIEW | Salem - Woodstown 69 kV |  | ACE Development Company, LLC | NJ | Salem | Withdrawn | Generation Interconnection | AEC | 71.0 | 33.0 | 22.0 |  | Capacity | Solar,Storage,Hybrid | 11/11/2020 | 12/31/2021 | [5 empty] | 2/11/2025 | 2/11/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-037 | TC2 | PHASE 1 | Findlay-Clinton 23 kV |  | PG Solar LLC | PA | Allegheny | Active | Generation Interconnection | DL | 4.7 | 4.7 | 2.82 |  | Capacity | Solar | 11/13/2020 | 12/1/2021 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-049 | TC2 | PHASE 1 | Van Dorn 34.5 kV | Alexandria | Covanta | VA | Arlington | Active | Generation Interconnection | Dominion | 20.0 | 0.0 | 20.0 |  | Capacity | Biomass | 11/20/2020 | 12/31/2020 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-053 | TC2 | PHASE 1 | Fulton 138 kV |  | Orchid Acres Solar Project, LLC | OH | Fulton | Active | Generation Interconnection | ATSI | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 12/2/2020 | 9/25/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-054 | TC2 | PHASE 1 | Fulton 138 kV |  | Orchid Acres Solar Project, LLC | OH | Fulton | Active | Generation Interconnection | ATSI | 400.0 | 100.0 | 100.0 |  | Capacity | Storage | 12/2/2020 | 9/25/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-057 | TC2 | PHASE 1 | Cardington-Liberty 69 kV II |  | Crossroads Solar I, LLC | OH | Morrow | Active | Generation Interconnection | ATSI | 74.0 | 10.0 | 6.0 |  | Capacity | Solar | 12/7/2020 | 11/30/2022 | [5 empty] | 4/22/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-061 | TC2 | PHASE 1 | Powerton-Nevada 345 kV |  | Aurora Solar LLC | IL | Lasalle | Active | Generation Interconnection | ComEd | 200.0 | 50.0 | 20.0 |  | Capacity | Storage | 12/11/2020 | 12/31/2023 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-062 | TC2 | PHASE 1 | Williams 138 kV |  | Catamount Wind LLC | WV | Grant | Active | Generation Interconnection | APS | 147.0 | 147.0 | 21.609 |  | Capacity | Wind | 12/15/2020 | 8/1/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-063 | TC2 | PHASE 1 | North Hampton 69 kV |  | Brookfield Twin Creeks Solar LLC | OH | Clark | Active | Generation Interconnection | ATSI | 54.0 | 54.0 | 34.5 |  | Capacity | Solar | 12/16/2020 | 12/31/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-068 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 12/30/2020 | 12/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-069 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 250.0 | 150.0 | 90.0 |  | Capacity | Solar | 12/30/2020 | 12/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-072 | TC2 | PHASE 1 | Rockport 765 kV |  | Bluegrass Power LLC | IN | Spencer | Active | Generation Interconnection | AEP | 700.0 | 700.0 | 700.0 |  | Capacity | Natural Gas | 1/6/2021 | 5/31/2026 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-073 | TC2 | PHASE 1 | Crooksville 69 kV |  | SR Madison, LLC | KY | Madison | Active | Generation Interconnection | EKPC | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 1/11/2021 | 5/1/2024 | [5 empty] | 4/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-074 | TC2 | PHASE 1 | Meckesville Tap 69kV |  | Plainfield Solar, LLC | PA | Carbon | Active | Generation Interconnection | PPL | 38.0 | 38.0 | 26.2 |  | Capacity | Solar | 1/15/2021 | 12/31/2023 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-077 | TC2 | PHASE 1 | Clover-Rawlings 500 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 700.0 | 200.0 | 120.0 |  | Capacity | Solar | 1/19/2021 | 6/30/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-080 | TC2 | PHASE 1 | Lexington 115 kV | Sand Dragon Energy | Sand Dragon Energy LLC | VA | Rockbridge | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 78.0 |  | Capacity | Storage | 1/21/2021 | 6/1/2024 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-081 | TC2 | PHASE 1 | Mt. Sterling-Fogg Pike 69 kV |  | SR Fayette II, LLC | KY | Montgomery | Active | Generation Interconnection | EKPC | 30.0 | 30.0 | 18.0 |  | Capacity | Solar | 1/21/2021 | 5/1/2024 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-082 | TC2 | PHASE 1 | Nottingham 138 kV |  | Energy Pastures Solar Project, LLC | OH | Harrison | Active | Generation Interconnection | AEP | 200.0 | 200.0 | 133.4 |  | Capacity | Solar | 1/22/2021 | 12/1/2024 | [5 empty] | 5/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-084 | TC2 | APPLICATION REVIEW | Greentown 138 kV |  | Locomotive Solar, LLC | IN | Howard | Withdrawn | Generation Interconnection | AEP | 100.0 | 100.0 | 40.0 |  | Capacity | Storage | 1/22/2021 | 12/31/2023 | [5 empty] | 4/4/2025 | 4/3/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-085 | TC2 | PHASE 1 | West Del-Royerton 138 kV |  | Royerton Solar, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 140.0 | 40.0 | 24.0 |  | Capacity | Solar | 1/22/2021 | 12/31/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-086 | TC2 | PHASE 1 | Mt. Jackson DP-Mt. Jackson 115 kV | OFW Solar Farm | OFW Solar Farm, LLC | VA | Shenandoah | Active | Generation Interconnection | Dominion | 75.0 | 75.0 | 45.0 |  | Capacity | Solar,Storage,Hybrid | 1/22/2021 | 12/30/2022 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-088 | TC2 | PHASE 1 | Midlothian 230 kV |  | Hermon Energy Center, LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 150.0 |  | Capacity | Storage | 1/26/2021 | 4/15/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-090 | TC2 | PHASE 1 | Scalp Level 23 kV IV |  | Neptune Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 14.0 | 14.0 | 8.4 |  | Capacity | Solar | 1/26/2021 | 1/31/2023 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-091 | TC2 | PHASE 1 | Scalp Level 23 kV V |  | Neptune Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 20.0 | 6.0 | 3.6 |  | Capacity | Solar | 1/26/2021 | 1/15/2023 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-092 | TC2 | PHASE 1 | Todd 69 kV |  | Richfield Solar Energy LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 50.0 | 0.0 | 11.0 |  | Capacity | Solar | 1/26/2021 | 12/31/2021 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-093 | TC2 | PHASE 1 | Colonial Trail-Hopewell 230 kV |  | Admiral Solar LLC | VA | Prince George | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 100.0 |  | Capacity | Solar,Storage,Hybrid | 1/26/2021 | 12/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-094 | TC2 | PHASE 1 | Summer Shade-Green County 161 kV |  | Coneflower Solar LLC | KY | Metcalfe | Active | Generation Interconnection | EKPC | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 1/27/2021 | 4/1/2024 | [5 empty] | 3/20/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-095 | TC2 | PHASE 1 | Hopewell 34.5 kV (Circuit 313) |  | Virginia Electric and Power Company | VA | Prince George | Active | Generation Interconnection | Dominion | 18.0 | 18.0 | 10.8 |  | Capacity | Solar | 1/28/2021 | 12/8/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-096 | TC2 | PHASE 1 | Dauphin PG Tie-Dauphin Juniata Tie 69 kV |  | Dauphin Solar I, LLC | PA | Dauphin | Active | Generation Interconnection | PPL | 55.0 | 0.0 | 0.0 |  | Energy | Storage | 1/28/2021 | 12/1/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-098 | TC2 | APPLICATION REVIEW | Copperstone-North Lebanon 230 kV II |  | Lebanon Solar I, LLC | PA | Lebanon | Withdrawn | Generation Interconnection | ME | 70.0 | 0.0 | 0.0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 2/10/2025 | 2/10/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-099 | TC2 | APPLICATION REVIEW | Moshannon-Milesburg 230 kV V |  | MPG Solar, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 161.98 | 0.0 | 0.0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 3/3/2025 | 3/3/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-100 | TC2 | APPLICATION REVIEW | Moshannon-Milesburg 230 kV VI |  | MPG Solar, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 161.98 | 0.0 | 0.0 |  | Energy | Storage | 1/28/2021 | 6/30/2022 | [5 empty] | 3/3/2025 | 3/3/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-104 | TC2 | PHASE 1 | Marysville-Flatlick 765 kV |  | Oak Run Solar Project, LLC | OH | Madison | Active | Generation Interconnection | AEP | 400.0 | 400.0 | 253.7 |  | Capacity | Solar | 1/29/2021 | 9/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-106 | TC2 | PHASE 1 | Marysville-Flatlick 765 kV |  | Oak Run Solar Project, LLC | OH | Madison | Active | Generation Interconnection | AEP | 400.0 | 0.0 | 150.0 |  | Capacity | Storage | 1/29/2021 | 12/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-107 | TC2 | PHASE 1 | Marysville-Flatlick 765 kV |  | Oak Run Solar Project, LLC | OH | Madison | Active | Generation Interconnection | AEP | 400.0 | 0.0 | 150.0 |  | Capacity | Storage | 1/29/2021 | 12/1/2024 | [5 empty] | 3/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-109 | TC2 | PHASE 1 | Fitchville-New London 69 kV |  | Rosemary Solar, LLC | OH | Huron | Active | Generation Interconnection | ATSI | 40.0 | 40.0 | 28.1 |  | Capacity | Solar | 1/29/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-111 | TC2 | PHASE 1 | Perth 34.5 kV Substation (Circuit 408) |  | Koala Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 14.5 | 14.5 | 8.7 |  | Capacity | Solar | 1/29/2021 | 2/6/2023 | [5 empty] | 4/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-112 | TC2 | PHASE 1 | Perth 34.5 kV Substation (Circuit 404) |  | Kangaroo Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 15.2 | 15.2 | 9.12 |  | Capacity | Solar | 1/29/2021 | 3/24/2023 | [5 empty] | 4/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-114 | TC2 | PHASE 1 | Dresden-Pontiac Midpoint 345 kV |  | CPV Prairie Dock Solar, LLC | IL | Livingston | Active | Generation Interconnection | ComEd | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 1/29/2021 | 3/1/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-116 | TC2 | PHASE 1 | Olive-Reynolds 345 #1 345 kV |  | Honey Creek Energy, LLC | IN | White | Active | Generation Interconnection | AEP | 300.0 | 100.0 | 60.0 |  | Capacity | Solar,Storage,Hybrid | 1/29/2021 | 10/31/2023 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-119 | TC2 | PHASE 1 | Galion-Roberts South 138 kV II |  | Marion County Solar Project, LLC | OH | Marion | Active | Generation Interconnection | ATSI | 80.0 | 80.0 | 53.6 |  | Capacity | Solar | 1/29/2021 | 9/1/2024 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-120 | TC2 | PHASE 1 | Everetts 34.5 kV |  | Wildcat Road Solar, LLC | NC | Martin | Active | Generation Interconnection | Dominion | 21.0 | 21.0 | 14.0 |  | Capacity | Solar | 1/29/2021 | 12/15/2024 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-121 | TC2 | PHASE 1 | Mackeys 230 kV |  | Albemarle Beach Solar, LLC | NC | Washington | Active | Generation Interconnection | Dominion | 140.0 | 0.0 | 0.0 |  | Energy | Storage | 1/29/2021 | 12/15/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-124 | TC2 | PHASE 1 | Shackleford-Harmony 115 kV |  | Virginia Electric and Power Company | VA | King and Queen | Active | Generation Interconnection | Dominion | 149.9 | 0.0 | 33.34 |  | Capacity | Solar | 1/29/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-125 | TC2 | PHASE 1 | Camden-Crystal 69 kV |  | Alamo Solar I, LLC | OH | Preble | Active | Generation Interconnection | Dayton | 69.9 | 0.0 | 15.44 |  | Capacity | Solar | 1/29/2021 | 12/31/2022 | [5 empty] | 4/10/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-126 | TC2 | PHASE 1 | Eugene 345 kV |  | TGE Illinois 211, LLC | IN | Vermillion | Active | Generation Interconnection | AEP | 150.0 | 150.0 | 90.0 |  | Capacity | Solar,Storage,Hybrid | 1/29/2021 | 6/30/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-130 | TC2 | APPLICATION REVIEW | Colby Tap-Valley 138 kV |  | CP Glenwood LLC | MI | Van Buren | Withdrawn | Generation Interconnection | AEP | 55.0 | 55.0 | 37.2 |  | Capacity | Solar,Storage,Hybrid | 2/2/2021 | 12/31/2026 | [5 empty] | 4/2/2025 | 3/30/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-131 | TC2 | APPLICATION REVIEW | Almena-Valley 69 kV |  | CP South Branch LLC | MI | Van Buren | Withdrawn | Generation Interconnection | AEP | 40.0 | 40.0 | 20.0 |  | Capacity | Solar | 2/1/2021 | 12/31/2026 | [5 empty] | 4/2/2025 | 3/31/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-132 | TC2 | APPLICATION REVIEW | Hartford-South Haven 69 kV |  | CP McDonald Station LLC | MI | Van Buren | Withdrawn | Generation Interconnection | AEP | 15.0 | 15.0 | 7.5 |  | Capacity | Solar | 2/1/2021 | 12/31/2026 | [5 empty] | 4/2/2025 | 3/30/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-143 | TC2 | APPLICATION REVIEW | Burma-Sligo 25 kV |  | CP McCall Road LLC | PA | Clarion | Withdrawn | Generation Interconnection | APS | 20.0 | 20.0 | 10.0 |  | Capacity | Solar | 2/16/2021 | 12/31/2026 | [5 empty] | 3/14/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-148 | TC2 | PHASE 1 | S Berwick - Galion 345 kV |  | Armadillo Solar LLC | OH | Wyandot | Active | Generation Interconnection | AEP | 86.0 | 86.0 | 0.0 |  | Energy | Storage | 2/22/2021 | 12/2/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-149 | TC2 | PHASE 1 | Galion-South Berwick 345 kV |  | Wombat Solar LLC | OH | Crawford | Active | Generation Interconnection | AEP | 400.0 | 400.0 | 52.0 |  | Capacity | Solar | 2/22/2021 | 12/2/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-150 | TC2 | APPLICATION PHASE | River Dock 23 kV |  | Lock+ Hydro Friends Fund XLII, LLC | PA | Allegheny | Withdrawn | Generation Interconnection | DL | 5.25 | 5.25 | 5.25 |  | Capacity | Hydro | 2/23/2021 | 12/31/2022 | [5 empty] | 4/7/2025 | 4/7/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-151 | TC2 | PHASE 1 | Trices Lake - James River Tap 115 kV |  | Cumberland Solar, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 2/23/2021 | 2/2/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-152 | TC2 | PHASE 1 | Banister-Bear Skin 138 kV |  | Virginia Electric and Power Company | VA | Pittsylvania | Active | Generation Interconnection | AEP | 131.0 | 131.0 | 79.0 |  | Capacity | Solar | 2/23/2021 | 2/2/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-159 | TC2 | PHASE 1 | Williamstown 69 kV |  | Round Trip, LLC | KY | Grant | Active | Generation Interconnection | EKPC | 61.0 | 61.0 | 57.6 |  | Capacity | Solar,Storage,Hybrid | 2/25/2021 | 9/15/2023 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-161 | TC2 | PHASE 1 | Wheelabrator Frackville-Gilberton 69 kV |  | New Boston Solar, LLC | PA | Schuylkill | Active | Generation Interconnection | PPL | 43.0 | 43.0 | 18.06 |  | Capacity | Solar | 2/25/2021 | 12/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-162 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Salmon Solar LLC | IN | Rush | Active | Generation Interconnection | AEP | 115.0 | 115.0 | 15.0 |  | Capacity | Solar | 2/25/2021 | 12/2/2024 | [5 empty] | 4/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-163 | TC2 | PHASE 1 | Dequine-Eugene 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 700.0 | 250.0 | 35.0 |  | Capacity | Solar | 2/25/2021 | 6/1/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-164 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Cobia Solar LLC | IN | Decatur | Active | Generation Interconnection | AEP | 385.0 | 270.0 | 35.1 |  | Capacity | Solar | 2/25/2021 | 12/2/2024 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-165 | TC2 | PHASE 1 | Dumont-Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 200.0 | 200.0 | 26.0 |  | Capacity | Solar | 2/25/2021 | 12/2/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-166 | TC2 | PHASE 1 | Newville-Nottingham Tap 1 69 kV |  | Costen Solar, Inc | PA | Cumberland | Active | Generation Interconnection | PPL | 10.0 | 10.0 | 0.0 |  | Energy | Solar | 2/25/2021 | 8/18/2023 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-171 | TC2 | PHASE 1 | Lunenburg-Nutbush 115 kV |  | Couch Creek Solar LLC | VA | Lunenburg | Active | Generation Interconnection | Dominion | 60.0 | 60.0 | 36.0 |  | Capacity | Solar | 2/26/2021 | 7/3/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-176 | TC2 | PHASE 1 | Geneva 115 kV |  | Trestle Solar Farm, LLC | PA | Crawford | Active | Generation Interconnection | PENELEC | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 2/26/2021 | 1/31/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-179 | TC2 | PHASE 1 | Coburg 69 kV |  | Round Trip, LLC | KY | Adair | Active | Generation Interconnection | EKPC | 60.0 | 60.0 | 57.0 |  | Capacity | Solar,Storage,Hybrid | 2/26/2021 | 9/15/2023 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-181 | TC2 | PHASE 1 | Airey - Golden Hill 69 kV |  | Old Line Energy, LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 28.0 | 28.0 | 2.8 |  | Capacity | Solar | 2/26/2021 | 6/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-182 | TC2 | PHASE 1 | Doubs-Bismark 500 kV |  | ACE Development Company, LLC | VA | Frederick | Active | Generation Interconnection | Dominion | 200.0 | 200.0 | 133.3333 |  | Capacity | Solar,Storage,Hybrid | 2/26/2021 | 12/31/2022 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-184 | TC2 | PHASE 1 | Harbert Metering 138 kV |  | STMO bn, LLC | KY | Knott | Active | Generation Interconnection | AEP | 210.0 | 210.0 | 126.0 |  | Capacity | Solar | 2/27/2021 | 6/1/2024 | [5 empty] | 4/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-188 | TC2 | PHASE 1 | Farmville - Buckingham 230 kV |  | Bear Creek Solar, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 140.0 | 140.0 | 89.0 |  | Capacity | Solar | 2/27/2021 | 3/1/2024 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-189 | TC2 | PHASE 1 | Washington-Furnace Brook Tap 34.5 kV |  | Harmony Sand Solar Farm, LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Solar | 2/27/2021 | 2/23/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-191 | TC2 | PHASE 1 | Mississinewa 138 kV |  | BR Solar Sheriff 2 LLC | IN | Grant | Active | Generation Interconnection | AEP | 30.0 | 30.0 | 18.0 |  | Capacity | Solar,Storage,Hybrid | 2/27/2021 | 11/30/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-192 | TC2 | PHASE 1 | Mississinewa 138 kV |  | BR Solar Sheriff 3 LLC | IN | Grant | Active | Generation Interconnection | AEP | 19.0 | 19.0 | 11.4 |  | Capacity | Solar,Storage,Hybrid | 2/27/2021 | 12/15/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-193 | TC2 | PHASE 1 | Turner 34.5 kV |  | Virginia Electric and Power Company | VA | Henrico | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 2/27/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-198 | TC2 | PHASE 1 | Briery - Finneywood 230 kV |  | Gabriel Energy, LLC | VA | Prince Edward | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 2/28/2021 | 2/25/2024 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-200 | TC2 | PHASE 1 | North Warren–Russell 34.5 kV |  | Sugaree Solar LLC | PA | Warren | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/2/2021 | 1/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-202 | TC2 | APPLICATION REVIEW | Reusens 12.47 kV |  | James Energy Center, LLC | VA | City of Lynchburg | Withdrawn | Generation Interconnection | AEP | 20.0 | 20.0 | 20.0 |  | Capacity | Storage | 3/4/2021 | 10/31/2022 | [5 empty] | 3/11/2025 | 3/11/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-206 | TC2 | PHASE 1 | Tennessee Gas-East Towanda 115 kV |  | Agnes Solar LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 48.0 | 48.0 | 28.8 |  | Capacity | Solar | 3/4/2021 | 1/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-208 | TC2 | PHASE 1 | Greenwood DP - St. Johns DP 115 kV |  | Busbees Solar, LLC | VA | Louisa | Active | Generation Interconnection | Dominion | 70.0 | 70.0 | 44.47 |  | Capacity | Solar | 3/5/2021 | 6/30/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-212 | TC2 | PHASE 1 | Dumont-Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 400.0 | 200.0 | 26.0 |  | Capacity | Solar | 3/8/2021 | 12/2/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-213 | TC2 | PHASE 1 | Gary D.P Tap - Gary D.P 115 kV |  | Virginia Electric and Power Company | VA | Lunenburg | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/8/2021 | 12/1/2025 | [5 empty] | 3/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-215 | TC2 | PHASE 1 | Garner DP-Lancaster 115 kV |  | Waller Solar I, LLC | VA | Lancaster | Active | Generation Interconnection | Dominion | 196.0 | 0.0 | 36.92 |  | Capacity | Solar | 3/9/2021 | 12/31/2023 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-216 | TC2 | PHASE 1 | East Sidney-Quincy 138 kV |  | Clearview Solar I, LLC | OH | Champaign | Active | Generation Interconnection | Dayton | 144.0 | 0.0 | 25.92 |  | Capacity | Solar | 3/9/2021 | 12/31/2023 | [5 empty] | 4/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-219 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Cobia Solar LLC | IN | Decatur | Active | Generation Interconnection | AEP | 715.0 | 330.0 | 42.9 |  | Capacity | Solar | 3/9/2021 | 12/2/2024 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-220 | TC2 | PHASE 1 | East Towanda-South Troy 115 kV |  | Franklin Energy, LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 31.0 | 31.0 | 19.2 |  | Capacity | Solar | 3/10/2021 | 9/30/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-221 | TC2 | PHASE 1 | South Troy - North Towanda 34.5 kV |  | Franklin Energy, LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 13.2 |  | Capacity | Solar | 3/10/2021 | 9/30/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-228 | TC2 | PHASE 1 | Washington-Furnace Brook Tap 34.5kV |  | Reeder Farm Solar Farm, LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 11.2 | 11.2 | 4.704 |  | Capacity | Solar | 3/12/2021 | 3/31/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-230 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 3/12/2021 | 12/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-236 | TC2 | PHASE 1 | Potter-Harlan 69 kV |  | Harlansburg PV I, LLC | PA | Lawrence | Active | Generation Interconnection | ATSI | 60.0 | 20.0 | 2.0 |  | Capacity | Solar | 3/15/2021 | 10/30/2024 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-237 | TC2 | PHASE 1 | Thelma 230kV |  | Oak Solar LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 323.0 | 0.0 | 0.0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-238 | TC2 | PHASE 1 | Earleys 230 kV |  | Aulander Holloman Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 99.9 | 0.0 | 0.0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-239 | TC2 | PHASE 1 | Hickory-Shawboro 230 kV |  | Ranchland Solar, LLC | NC | Currituck | Active | Generation Interconnection | Dominion | 60.0 | 0.0 | 0.0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-240 | TC2 | PHASE 1 | Old Church 34.5 kV |  | Mechanicsville Solar, LLC | VA | Hanover | Active | Generation Interconnection | Dominion | 25.0 | 0.0 | 0.0 |  | Energy | Storage | 3/16/2021 | 12/15/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-245 | TC2 | PHASE 1 | Olive - Reynolds #1 345 kV |  | Starke Central Project, LLC | IN | Starke | Active | Generation Interconnection | AEP | 210.0 | 210.0 | 126.0 |  | Capacity | Solar | 3/16/2021 | 12/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-247 | TC2 | APPLICATION REVIEW | Northwestern REC Dixonburg-Vernon 34.5 kV |  | Cassidy Solar LLC | PA | Crawford | Withdrawn | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/17/2021 | 1/15/2023 | [5 empty] | 2/6/2025 | 2/6/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-248 | TC2 | PHASE 1 | East Elkhart – Elcona Tap 138 kV |  | Amberjack Solar LLC | IN | Elkhart | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 0.0 |  | Energy | Storage | 3/17/2021 | 12/2/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-249 | TC2 | PHASE 1 | Stoneboro-Perry 69 kV |  | Steamboat Solar LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/17/2021 | 1/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-250 | TC2 | PHASE 1 | Stoneboro-Perry 69 kV II |  | Steamboat Solar LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 40.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/17/2021 | 1/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-260 | TC2 | APPLICATION REVIEW | Crystal Hill - Perth 115 kV |  | Virginia Electric and Power Company | VA | Halifax | Withdrawn | Generation Interconnection | Dominion | 149.0 | 149.0 | 89.4 |  | Capacity | Solar | 3/18/2021 | 12/1/2025 | [5 empty] | 4/22/2025 | 3/31/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-262 | TC2 | PHASE 1 | Dryburg 115 kV |  | Staunton Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 47.0 | 11.0 | 6.6 |  | Capacity | Solar | 3/18/2021 | 12/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-270 | TC2 | PHASE 1 | Clover 230 kV |  | Clover Storage, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 105.0 |  | Capacity | Storage | 3/19/2021 | 12/31/2025 | [5 empty] | 4/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-272 | TC2 | PHASE 1 | Berry Hill 138 kV |  | Tupelo Storage, LLC | VA | Pittsylvania | Active | Generation Interconnection | AEP | 55.0 | 55.0 | 21.3 |  | Capacity | Storage | 3/19/2021 | 10/1/2024 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-279 | TC2 | PHASE 1 | Hagerstown-Conservit 34.5 kV |  | Franklin Energy, LLC | MD | Washington | Active | Generation Interconnection | APS | 20.0 | 20.0 | 12.9 |  | Capacity | Solar | 3/22/2021 | 9/30/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-281 | TC2 | PHASE 1 | Church 138 kV |  | Church Storage LLC | MD | Queen Anne's | Active | Generation Interconnection | DPL | 50.0 | 50.0 | 50.0 |  | Capacity | Storage | 3/22/2021 | 5/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-282 | TC2 | APPLICATION REVIEW | Kuranga Power Generator |  | The Associates Incubator | OH | Butler | Withdrawn | Generation Interconnection | DEOK | 10.0 | 10.0 | 3.102 |  | Capacity | Solar,Wind,Hybrid | 3/22/2021 | 2/10/2022 | [5 empty] | 2/12/2025 | 2/12/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-284 | TC2 | PHASE 1 | Catharpin 230 kV |  | Urban Grid Solar Projects, LLC. | VA | Prince William | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 150.0 |  | Capacity | Storage | 3/22/2021 | 12/31/2023 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-288 | TC2 | PHASE 1 | Stonewall 138 kV |  | Urban Grid Solar Projects, LLC. | VA | Frederick | Active | Generation Interconnection | APS | 150.0 | 150.0 | 150.0 |  | Capacity | Storage | 3/22/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-289 | TC2 | PHASE 1 | Amsden – Fremont Center 69 kV |  | Chinchilla Solar LLC | OH | Seneca | Active | Generation Interconnection | AEP | 66.6 | 66.6 | 0.0 |  | Energy | Storage | 3/23/2021 | 12/2/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-290 | TC2 | PHASE 1 | Amsden – Fremont Center 69 kV |  | Chinchilla Solar LLC | OH | Seneca | Active | Generation Interconnection | AEP | 105.0 | 38.4 | 0.0 |  | Energy | Storage | 3/22/2021 | 12/2/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-297 | TC2 | PHASE 1 | Cumberland 230 kV |  | Calpine Mid-Atlantic Development, LLC | NJ | Cumberland | Active | Generation Interconnection | AEC | 19.0 | 19.0 | 11.4 |  | Capacity | Solar | 3/23/2021 | 6/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-298 | TC2 | PHASE 1 | Loretto 69 kV |  | Crab Run Solar Project, LLC | KY | Marion | Active | Generation Interconnection | EKPC | 60.0 | 60.0 | 40.0 |  | Capacity | Solar | 3/23/2021 | 9/1/2024 | [5 empty] | 4/11/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-300 | TC2 | PHASE 1 | Meadow Brook 138 kV |  | Meadow Brook Storage, LLC | VA | Frederick | Active | Generation Interconnection | APS | 100.0 | 100.0 | 70.0 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 3/20/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-304 | TC2 | PHASE 1 | Liberty 230 kV |  | Urban Grid Solar Projects, LLC. | VA | Prince William | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 150.0 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-310 | TC2 | PHASE 1 | Matt Funk 138 kV |  | Matt Funk Storage, LLC | VA | Roanoke | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 70.0 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-311 | TC2 | PHASE 1 | Smith Mountain 138 kV |  | Smith Mountain Storage, LLC | VA | Bedford | Active | Generation Interconnection | AEP | 75.0 | 75.0 | 52.5 |  | Capacity | Storage | 3/23/2021 | 12/31/2023 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-314 | TC2 | APPLICATION PHASE | Gilboa-Jones Branch 138 kV III |  | Deep Lake Energy Center, LLC | WV | Nicholas | Withdrawn | Generation Interconnection | APS | 150.0 | 0.0 | 67.0 |  | Capacity | Storage | 3/25/2021 | 5/1/2024 | [5 empty] | 12/12/2024 | 11/27/2024 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-320 | TC2 | PHASE 1 | Ladysmith 230 kV |  | Ladysmith Storage, LLC | VA | Caroline | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 105.0 |  | Capacity | Storage | 3/24/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-327 | TC2 | PHASE 1 | Tennessee Gas-East Towanda 115 kV |  | Agnes Solar LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 58.0 | 10.0 | 6.0 |  | Capacity | Solar | 3/24/2021 | 1/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-328 | TC2 | PHASE 1 | Dumont - Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 600.0 | 200.0 | 26.0 |  | Capacity | Solar | 3/25/2021 | 12/2/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-329 | TC2 | PHASE 1 | S Berwick - Galion 345 kV |  | Wombat Solar LLLC | OH | Wyandot | Active | Generation Interconnection | AEP | 400.0 | 200.0 | 156.0 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 4/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-330 | TC2 | PHASE 1 | Dumont - Greentown 765 kV |  | Wahoo Solar LLC | IN | Marshall | Active | Generation Interconnection | AEP | 600.0 | 200.0 | 156.0 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-331 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Cobia Solar LLC | IN | Decatur | Active | Generation Interconnection | AEP | 715.0 | 200.0 | 156.0 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 4/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-332 | TC2 | PHASE 1 | East Elkhart – Elcona Tap 138 kV |  | Amberjack Solar LLC | IN | Elkhart | Active | Generation Interconnection | AEP | 200.0 | 100.0 | 100.0 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-336 | TC2 | PHASE 1 | Midway 138 kV |  | Reserve Energy Exploration Company | OH | Henry | Active | Generation Interconnection | ATSI | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/25/2021 | 11/30/2023 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-337 | TC2 | PHASE 1 | Midway 138 kV II |  | Reserve Energy Exploration Company | OH | Henry | Active | Generation Interconnection | ATSI | 100.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/25/2021 | 11/30/2023 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-338 | TC2 | PHASE 1 | Rogers Road - Carson 500 kV |  | Cassius Blue Solar LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 40.0 | 40.0 | 40.0 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-339 | TC2 | PHASE 1 | Rogers Road - Carson 500 kV |  | Cassius Blue Solar LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 3/25/2021 | 12/2/2024 | [5 empty] | 5/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-341 | TC2 | PHASE 1 | Ridge Road 115 kV |  | Mighty Blue LLC | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/25/2021 | 12/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-343 | TC2 | PHASE 1 | Eugene - Dequine 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 78.0 |  | Capacity | Storage | 3/26/2021 | 12/2/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-344 | TC2 | PHASE 1 | Dequine 345 bkV |  | Rainbow Trout Solar LLC | IN |  | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 78.0 |  | Capacity | Storage | 3/26/2021 | 12/2/2024 | [5 empty] | 4/15/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-345 | TC2 | PHASE 1 | Eugene - Dequine 345 kV |  | Dolphin Solar LLC | IN | Fountain | Active | Generation Interconnection | AEP | 150.0 | 50.0 | 39.0 |  | Capacity | Storage | 3/26/2021 | 12/2/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-347 | TC2 | PHASE 1 | Indian River 230 kV II |  | US Wind Inc. | DE | Sussex | Active | Generation Interconnection | DPL | 448.8 | 448.8 | 121.2 |  | Capacity | Offshore Wind | 3/26/2021 | 8/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-348 | TC2 | APPLICATION REVIEW | Indian River 230 kV II |  | US Wind Inc. | DE | Sussex | Withdrawn | Generation Interconnection | DPL | 897.6 | 897.6 | 242.3 |  | Capacity | Offshore Wind | 3/26/2021 | 8/31/2025 | [5 empty] | 4/1/2025 | 2/25/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-354 | TC2 | APPLICATION REVIEW | Ragland - Grant Branch 138 kV |  | Mountaineer Solar LLC | WV | Mingo | Withdrawn | Generation Interconnection | AEP | 100.0 | 100.0 | 72.92 |  | Capacity | Solar,Storage,Hybrid | 3/26/2021 | 9/30/2024 | [5 empty] | 2/6/2025 | 2/6/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-355 | TC2 | APPLICATION REVIEW | North Muskingum River - Philo 138 kV |  | IRGAH Renewables Development LLC | OH | Morgan | Withdrawn | Generation Interconnection | AEP | 125.0 | 125.0 | 82.4 |  | Capacity | Solar,Storage,Hybrid | 3/26/2021 | 6/1/2024 | [5 empty] | 3/31/2025 | 3/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-356 | TC2 | PHASE 1 | South Troy - Canton 34.5 kV |  | Robin Solar LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/26/2021 | 1/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-357 | TC2 | PHASE 1 | Wilton 345 kV |  | Bluegill Energy Storage LLC | IL | Will | Active | Generation Interconnection | ComEd | 250.0 | 250.0 | 250.0 |  | Capacity | Storage | 3/26/2021 | 11/15/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-360 | TC2 | PHASE 1 | Broadford 138 kV |  | Laurel Creek Energy Storage LLC | VA | Smyth | Active | Generation Interconnection | AEP | 250.0 | 250.0 | 250.0 |  | Capacity | Storage | 3/26/2021 | 11/15/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-363 | TC2 | PHASE 1 | Powerton 345 kV |  | Mackinaw Solar LLC | IL | Tazewell | Active | Generation Interconnection | ComEd | 300.0 | 300.0 | 180.0 |  | Capacity | Solar | 3/26/2021 | 5/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-364 | TC2 | PHASE 1 | Powerton 345 kV |  | Mackinaw Solar LLC | IL | Tazewell | Active | Generation Interconnection | ComEd | 500.0 | 200.0 | 120.0 |  | Capacity | Solar | 3/26/2021 | 5/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-365 | TC2 | PHASE 1 | Conneaut Tap-Werner 69 kV |  | Amadeus Solar LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 35.0 | 35.0 | 21.0 |  | Capacity | Solar | 3/26/2021 | 5/31/2023 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-366 | TC2 | PHASE 1 | Garner Delivery Point - Lancaster 115 kV |  | Virginia Electric and Power Company | VA | Lancaster | Active | Generation Interconnection | Dominion | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/26/2021 | 12/1/2025 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-369 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Virginia Electric and Power Company | VA | Greensville | Active | Generation Interconnection | Dominion | 86.0 | 86.0 | 51.6 |  | Capacity | Solar | 3/26/2021 | 12/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-370 | TC2 | PHASE 1 | Tillman 138 kV |  | Tillman Storage LLC | IN | Allen | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/26/2021 | 10/31/2024 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-375 | TC2 | PHASE 1 | Fostoria Central 345 kV |  | Foster Energy Storage LLC | OH | Hancock | Active | Generation Interconnection | AEP | 500.0 | 500.0 | 500.0 |  | Capacity | Storage | 3/29/2021 | 11/15/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-378 | TC2 | PHASE 1 | North Hampton – Medway 69 kV |  | Brookfield Twin Creeks Solar LLC | OH | Clark | Active | Generation Interconnection | ATSI | 74.0 | 20.0 | 13.5 |  | Capacity | Solar | 3/29/2021 | 7/31/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-379 | TC2 | PHASE 1 | Easton - Steele 138 kV III |  | Crockett Solar I, LLC | MD | Talbot | Active | Generation Interconnection | DPL | 79.0 | 20.0 | 20.0 |  | Capacity | Storage | 3/29/2021 | 9/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-380 | TC2 | PHASE 1 | Carville 138 kV IV |  | Concho Solar I, LLC | MD | Queen Anne's | Active | Generation Interconnection | DPL | 106.0 | 20.0 | 20.0 |  | Capacity | Storage | 3/29/2021 | 9/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-382 | TC2 | PHASE 1 | Cashie 230 kV |  | Merry Hill PV I, LLC | NC | Bertie | Active | Generation Interconnection | Dominion | 70.0 | 70.0 | 42.0 |  | Capacity | Solar | 3/29/2021 | 9/20/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-384 | TC2 | PHASE 1 | Chesterfield 230 kV |  | Virginia Electric and Power Company | VA | Chesterfield | Active | Generation Interconnection | Dominion | 60.0 | 60.0 | 24.0 |  | Capacity | Storage | 3/29/2021 | 12/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-385 | TC2 | PHASE 1 | North Hampton 69 kV |  | Brookfield Twin Creeks Solar LLC | OH | Clark | Active | Generation Interconnection | ATSI | 128.0 | 54.0 | 36.5 |  | Capacity | Solar | 3/29/2021 | 7/31/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-386 | TC2 | APPLICATION REVIEW | Kittanning-Rural Valley 25 kV |  | IMG Solar LLC | PA | Armstrong | Withdrawn | Generation Interconnection | APS | 30.0 | 30.0 | 18.0 |  | Capacity | Solar | 3/29/2021 | 4/1/2023 | [5 empty] | 3/14/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-400 | TC2 | PHASE 1 | Allen 345 kV |  | EDPR Northeast Allen Solar Park III LLC | IN | Allen | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/30/2021 | 10/31/2025 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-401 | TC2 | PHASE 1 | Losantville 345 kV |  | Riverstart Solar Park LLC | IN | Randolph | Active | Generation Interconnection | AEP | 200.0 | 0.0 | 44.0 |  | Capacity | Solar | 3/30/2021 | 12/15/2021 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-402 | TC2 | PHASE 1 | Allen 345 kV |  | EDPR Northeast Allen Energy Storage II LLC | IN | Allen | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/30/2021 | 10/31/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-403 | TC2 | PHASE 1 | Meadow Brook - Mt. Storm 500 kV |  | Old Fields Solar, LLC | WV | Hardy | Active | Generation Interconnection | APS | 125.0 | 125.0 | 52.5 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-404 | TC2 | PHASE 1 | Meadow Brook - Mt. Storm 500 kV II |  | Old Fields Solar, LLC | WV | Hardy | Active | Generation Interconnection | APS | 250.0 | 125.0 | 52.5 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-405 | TC2 | PHASE 1 | Continental 69 kV |  | Blue Harvest Solar Park LLC | OH | Putnam | Active | Generation Interconnection | AEP | 49.9 | 0.0 | 10.98 |  | Capacity | Solar | 3/30/2021 | 10/31/2022 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-406 | TC2 | PHASE 1 | Payne 69 kV |  | Timber Road Solar Park LLC | OH | Paulding | Active | Generation Interconnection | AEP | 49.9 | 0.0 | 10.98 |  | Capacity | Solar | 3/30/2021 | 10/31/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-408 | TC2 | PHASE 1 | Allen 345 kV |  | EDPR Northeast Allen Solar Park LLC | IN | Allen | Active | Generation Interconnection | AEP | 100.0 | 0.0 | 18.0 |  | Capacity | Solar | 3/30/2021 | 9/30/2022 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-411 | TC2 | PHASE 1 | Statler Hill 115 kV |  | Iris Energy LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 63.0 | 63.0 | 40.7 |  | Capacity | Solar | 3/31/2021 | 7/1/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-418 | TC2 | PHASE 1 | Blain 115 kV |  | Wills Creek Solar LLC | PA | Perry | Active | Generation Interconnection | PENELEC | 40.0 | 40.0 | 20.0 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 5/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-420 | TC2 | PHASE 1 | Eclipse #2 34.5 kV |  | Bear Oak Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 25.0 | 25.0 | 14.0 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 5/31/2023 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-423 | TC2 | PHASE 1 | Cherry Run–Harmony 138 kV |  | Falling Waters Solar, LLC | WV | Barbour | Active | Generation Interconnection | APS | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-424 | TC2 | PHASE 1 | Bonnieville - Lebanon 138 kV |  | Magnolia Solar and Grazing Farm LLC | KY | Larue | Active | Generation Interconnection | EKPC | 63.25 | 63.25 | 34.95 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 5/31/2023 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-426 | TC2 | PHASE 1 | Wakefield - Waverly 115 kV |  | Waverly Solar 1, LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 50.0 | 50.0 | 47.66 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-427 | TC2 | PHASE 1 | Waverly 115 kV |  | Old Forty Road Solar LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 85.0 | 85.0 | 66.3 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-428 | TC2 | PHASE 1 | Wakefield 115 kV |  | Peter’s Bridge Road Solar 1, LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 170.0 | 170.0 | 135.7 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-429 | TC2 | PHASE 1 | Burma - Armstrong 138 kV | Gardenia | Gardenia Solar, LLC | PA | Clarion | Active | Generation Interconnection | APS | 69.0 | 69.0 | 53.86 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 2/29/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-430 | TC2 | PHASE 1 | Sunbury-Dalmatia 69 kV II |  | Breezeway Solar LLC | PA | Northumberland | Active | Generation Interconnection | PPL | 60.0 | 60.0 | 37.7 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-436 | TC2 | PHASE 1 | Carson - Rogers Road 500 kV |  | Monarch Solar, LLC | VA | Sussex | Active | Generation Interconnection | Dominion | 400.0 | 400.0 | 400.0 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 12/31/2023 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-438 | TC2 | PHASE 1 | Union City 34.5 kV |  | Clemens Solar LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 10.0 | 10.0 | 6.7 |  | Capacity | Solar | 3/30/2021 | 6/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-439 | TC2 | PHASE 1 | Oxbow 34.5 kV |  | Field Brook Solar LLC | PA | Wyoming | Active | Generation Interconnection | PENELEC | 9.8 | 9.8 | 5.3 |  | Capacity | Solar | 3/30/2021 | 6/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-440 | TC2 | PHASE 1 | Twittys Creek - Madisonville 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 4/18/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-441 | TC2 | PHASE 1 | Twittys Creek - Madisonville 115 kV |  | Virginia Electric and Power Company | VA | Charlotte | Active | Generation Interconnection | Dominion | 225.0 | 125.0 | 75.0 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 4/18/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-442 | TC2 | PHASE 1 | Twittys Creek - Madisonville 115 kV |  | Taro Solar, LLC | VA | Charlotte | Active | Generation Interconnection | Dominion | 140.0 | 140.0 | 84.0 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 4/15/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-444 | TC2 | PHASE 1 | Bixby - Biers Run 345 kV |  | Brook Trout Solar, LLC | OH | Pickaway | Active | Generation Interconnection | AEP | 163.0 | 163.0 | 122.5 |  | Capacity | Solar | 3/30/2021 | 12/31/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-447 | TC2 | PHASE 1 | Cedar Creek 138 kV VII |  | Freepoint Solar LLC | DE | New Castle | Active | Generation Interconnection | DPL | 134.3 | 20.0 | 12.0 |  | Capacity | Solar | 3/30/2021 | 2/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-448 | TC2 | PHASE 1 | Cross School - Westvaco 138 kV |  | Potomac Hills Energy, LLC | WV | Mineral | Active | Generation Interconnection | APS | 50.0 | 50.0 | 30.0 |  | Capacity | Solar | 3/30/2021 | 3/24/2024 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-449 | TC2 | PHASE 1 | Jefferson-Greentown 765 kV |  | Salmon Solar LLC | IN | Rush | Active | Generation Interconnection | AEP | 835.0 | 120.0 | 15.0 |  | Capacity | Solar | 3/30/2021 | 12/2/2024 | [5 empty] | 4/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-450 | TC2 | PHASE 1 | Bridgeport 230 kV |  | Logan Energy Storage, L.L.C. | NJ | Gloucester | Active | Generation Interconnection | AEC | 219.0 | 219.0 | 115.3 |  | Capacity | Storage | 3/30/2021 | 3/1/2025 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-451 | TC2 | PHASE 1 | Chambers 230 kV |  | Carneys Point Energy Storage, L.L.C. | NJ | Salem | Active | Generation Interconnection | AEC | 240.0 | 240.0 | 123.0 |  | Capacity | Storage | 3/30/2021 | 6/1/2024 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-453 | TC2 | PHASE 1 | Lasalle - Plano 345 kV |  | FOX VALLEY ENERGY FACILITY, LLC | IL | Kendall | Active | Generation Interconnection | ComEd | 280.0 | 280.0 | 196.0 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-454 | TC2 | PHASE 1 | Dequine - Eugene 345 kV |  | ALGONQUIN POWER (FOUNTAIN COUNTY SOLAR), LLC | IN | Fountain | Withdrawn | Generation Interconnection | AEP | 300.0 | 300.0 | 210.0 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 4/7/2025 | 4/6/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-455 | TC2 | PHASE 1 | Dequine - Sullivan 345 kV |  | ALGONQUIN POWER (FOUNTAIN COUNTY SOLAR), LLC | IN | Fountain | Withdrawn | Generation Interconnection | AEP | 280.0 | 280.0 | 196.0 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 4/7/2025 | 4/6/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-456 | TC2 | PHASE 1 | Pierce Brook-Lewis Run 230 kV |  | McKean County Solar, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 80.0 | 80.0 | 55.8 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-457 | TC2 | PHASE 1 | Pierce Brook - Lewis Run 230 kV |  | McKean County Solar, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 160.0 | 80.0 | 55.8 |  | Capacity | Solar | 3/30/2021 | 3/31/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-458 | TC2 | PHASE 1 | Kittatinny-Newton 34.5 kV II |  | VESI 25 LLC | NJ | Sussex | Active | Generation Interconnection | JCPL | 19.8 | 0.0 | 1.89 |  | Capacity | Storage | 3/30/2021 | 5/31/2022 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-459 | TC2 | PHASE 1 | Allenwood-Larrabee 34.5 kV II |  | VESI 24 LLC | NJ | Monmouth | Active | Generation Interconnection | JCPL | 7.0 | 0.0 | 0.7 |  | Capacity | Storage | 3/30/2021 | 3/31/2022 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-460 | TC2 | PHASE 1 | East Flemington-Lebanon 34.5 kV II |  | Ftera Energy APD Flemington, LLC | NJ | Hunterdon | Active | Generation Interconnection | JCPL | 20.0 | 0.0 | 2.0 |  | Capacity | Storage | 3/30/2021 | 8/31/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-462 | TC2 | PHASE 1 | Progress Park - Glen Lyn 138 kV |  | May Solar LLC | VA | Wythe | Active | Generation Interconnection | AEP | 150.0 | 150.0 | 78.0 |  | Capacity | Solar,Storage,Hybrid | 3/30/2021 | 10/31/2024 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-466 | TC2 | PHASE 1 | Culloden - Wyoming 765 kV |  | Hobet Solar I, LLC | WV |  | Active | Generation Interconnection | AEP | 330.0 | 330.0 | 198.0 |  | Capacity | Solar | 3/30/2021 | 6/30/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-467 | TC2 | PHASE 1 | Beason 345 kV |  | Invenergy Solar Project Development LLC | IL | Logan | Active | Generation Interconnection | ComEd | 115.0 | 69.0 | 115.0 |  | Capacity | Solar | 3/31/2021 | 12/31/2025 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-469 | TC2 | PHASE 1 | Westmoreland – Oak Grove 230 kV |  | Invenergy Solar Project Development LLC | VA | Westmoreland | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/31/2021 | 12/31/2025 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-476 | TC2 | PHASE 1 | Hokes-Grantley 69 kV II |  | Cottontail Solar 2, LLC | PA | York | Active | Generation Interconnection | ME | 20.0 | 0.0 | 0.1 |  | Capacity | Solar | 3/31/2021 | 3/31/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-477 | TC2 | PHASE 1 | Hokes-Jackson 69 kV III |  | Cottontail Solar 8, LLC | PA | York | Active | Generation Interconnection | ME | 20.0 | 0.0 | 0.5 |  | Capacity | Solar | 3/31/2021 | 4/30/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-478 | TC2 | PHASE 1 | Hokes-Jackson 69 kV IV |  | Cottontail Solar 1, LLC | PA | York | Active | Generation Interconnection | ME | 20.0 | 0.0 | 0.5 |  | Capacity | Solar | 3/31/2021 | 3/31/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-479 | TC2 | PHASE 1 | Penns Tap-Richfield Tie 69 kV II |  | Cottontail Solar 6, LLC | PA | Snyder | Active | Generation Interconnection | PPL | 20.0 | 0.0 | 4.1 |  | Capacity | Solar | 3/31/2021 | 10/31/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-481 | TC2 | PHASE 1 | Derry Tap-Derry Bus 69 kV III |  | Cottontail Solar 4, LLC | PA | Northumberland | Active | Generation Interconnection | PPL | 20.0 | 0.0 | 4.1 |  | Capacity | Solar | 3/31/2021 | 7/31/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-484 | TC2 | PHASE 1 | Mifflintown Bus-Mifflintown Tap 69 kV II |  | Cottontail Solar 5, LLC | PA | Juniata | Active | Generation Interconnection | PPL | 20.0 | 0.0 | 4.1 |  | Capacity | Solar | 3/31/2021 | 8/31/2022 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-487 | TC2 | PHASE 1 | Madison - Tanners Creek 138 kV |  | Bellflower Solar 1, LLC | IN | Henry | Active | Generation Interconnection | AEP | 152.5 | 0.0 | 10.6 |  | Capacity | Solar | 3/31/2021 | 5/31/2022 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-491 | TC2 | PHASE 1 | Meadow Lake 345 kV |  | Black Prairie Solar Park II LLC | IN | White | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/31/2021 | 9/1/2024 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-492 | TC2 | PHASE 1 | Meadow Lake 345 kV |  | Black Prairie Storage II LLC | IN | White | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/31/2021 | 9/1/2024 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-498 | TC2 | PHASE 1 | Obetz 138 kV |  | Invenergy Storage Development LLC | OH | Franklin | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 50.0 |  | Capacity | Storage | 3/31/2021 | 12/31/2025 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-505 | TC2 | PHASE 1 | Westvaco - Mt Zion 138 kV |  | Fairlawn Hydroelectric Company LLC | MD | Garrett | Active | Generation Interconnection | APS | 14.0 | 14.0 | 14.0 |  | Capacity | Hydro | 3/31/2021 | 12/31/2023 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-509 | TC2 | APPLICATION REVIEW | Robinson 69 kV |  | IRGAH Renewables Development LLC | WV |  | Withdrawn | Generation Interconnection | AEP | 55.0 | 55.0 | 36.3 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 3/4/2025 | 3/4/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-515 | TC2 | PHASE 1 | Midway 345 kV III |  | STARLING SOLAR PROJECT, LLC | OH | Lucas | Active | Generation Interconnection | ATSI | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/31/2021 | 10/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-516 | TC2 | PHASE 1 | Pecatonica 138kV |  | KESTREL SOLAR, LLC | IL | Winnebago | Active | Generation Interconnection | ComEd | 120.0 | 120.0 | 72.0 |  | Capacity | Solar | 3/31/2021 | 10/31/2023 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-518 | TC2 | PHASE 1 | Tech Drive 138 kV |  | Delorean Power LLC dba Lightshift Energy | VA | Montgomery | Active | Generation Interconnection | AEP | 80.0 | 80.0 | 32.0 |  | Capacity | Storage | 3/31/2021 | 1/1/2024 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-519 | TC2 | PHASE 1 | Royerton - Desoto 138 kV |  | Muncie Solar 1, LLC | IN | Delaware | Active | Generation Interconnection | AEP | 111.0 | 111.0 | 87.8 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 2/29/2024 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-522 | TC2 | PHASE 1 | Five Forks 115 kV |  | Macon PV I LLC | NC | Warren | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/31/2021 | 7/30/2025 | [5 empty] | 3/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-524 | TC2 | PHASE 1 | LaSalle Station - Mazon 138 kV |  | Hog Run Solar, LLC | IL | Grundy | Active | Generation Interconnection | ComEd | 110.0 | 110.0 | 110.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2023 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-527 | TC2 | PHASE 1 | Kewanee-Toulon 138 kV |  | Invenergy Wind Development LLC | IL | Stark | Active | Generation Interconnection | ComEd | 200.0 | 200.0 | 26.0 |  | Capacity | Wind | 3/31/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-528 | TC2 | PHASE 1 | Bustleburg Tap - Fairfield DP 115 kV |  | Sunday Solar LLC | VA | Rockbridge | Active | Generation Interconnection | Dominion | 140.0 | 140.0 | 72.8 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 10/31/2024 | [5 empty] | 4/11/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-531 | TC2 | APPLICATION REVIEW | Greystone - West Denville 34.5 kV |  | West Denville LLC | NJ | Morris | Withdrawn | Generation Interconnection | JCPL | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 3/31/2021 | 7/31/2022 | [5 empty] | 1/31/2025 | 1/31/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-532 | TC2 | PHASE 1 | Pohatcong-Newburgh Tap 34.5 kV |  | V20 Mansfield LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-533 | TC2 | PHASE 1 | Newburgh-Pohatcong 34.5 kV |  | AF1327 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 3/31/2021 | 8/31/2021 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-534 | TC2 | PHASE 1 | Hackettstown-Pohatcong R722-7 34.5 kV |  | Mansfield 3 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-535 | TC2 | PHASE 1 | Hackettstown-Pohatcong J738-1 34.5 kV II |  | Mansfield 3 LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 40.0 | 20.0 | 0.0 |  | Energy | Storage | 3/31/2021 | 8/31/2022 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-538 | TC2 | APPLICATION REVIEW | Ridgeway - Motion Control 46 kV |  | EL-Jakes Hollow LLC | PA | Elk | Withdrawn | Generation Interconnection | APS | 20.0 | 20.0 | 15.42 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 10/15/2022 | [5 empty] | 3/3/2025 | 2/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-541 | TC2 | PHASE 1 | Perth - Crystal Hill 115 kV |  | Slick Rock Solar LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 65.0 | 65.0 | 39.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/3/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-542 | TC2 | APPLICATION REVIEW | North Shenandoah – Merck 115 kV |  | Knight Energy Center, LLC | VA | Rockingham | Withdrawn | Generation Interconnection | Dominion | 70.0 | 70.0 | 42.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/3/2024 | [5 empty] | 3/31/2025 | [9 empty] | Not Started |  | Not Started
AG2-544 | TC2 | PHASE 1 | Silver Lake 345 kV |  | Monarch Grid, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 200.0 | 200.0 | 80.0 |  | Capacity | Storage | 3/31/2021 | 11/6/2024 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-545 | TC2 | PHASE 1 | Silver Lake 345 kV |  | Monarch Grid, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 600.0 | 400.0 | 160.0 |  | Capacity | Storage | 3/31/2021 | 11/6/2024 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-548 | TC2 | PHASE 1 | Corwin - Elk 138 kV |  | Hamden Energy LLC | OH | Jackson | Active | Generation Interconnection | AEP | 90.0 | 90.0 | 54.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-550 | TC2 | PHASE 1 | Bluff Point - Randolph 138 kV |  | Riverstart Solar Park VI LLC | IN | Randolph | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 3/31/2021 | 10/31/2024 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-551 | TC2 | PHASE 1 | Bluff Point - Randolph 138 kV |  | Riverstart Solar Park VI LLC | IN | Randolph | Active | Generation Interconnection | AEP | 150.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/31/2021 | 10/31/2024 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-553 | TC2 | PHASE 1 | Bullitt County 161 kV |  | EDP Renewables North America LLC | KY | Bullitt | Active | Generation Interconnection | EKPC | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 3/31/2021 | 9/1/2024 | [5 empty] | 4/15/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-558 | TC2 | APPLICATION REVIEW | Shawville - Phillipsburg 34.5 kV II |  | Morrisdale Solar II, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 39.8 | 19.9 | 8.3 |  | Capacity | Solar | 3/31/2021 | 4/1/2023 | [5 empty] | 1/23/2025 | 1/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-559 | TC2 | APPLICATION REVIEW | Shawville - Phillipsburg 34.5 kV III |  | Morrisdale Solar III, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 59.7 | 19.9 | 8.3 |  | Capacity | Solar | 3/31/2021 | 4/1/2024 | [5 empty] | 1/23/2025 | 1/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-560 | TC2 | APPLICATION REVIEW | Phillipsburg (Karthaus) 34.5 kV |  | Morrisdale Solar IV, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | APS | 79.6 | 19.9 | 8.3 |  | Capacity | Solar | 3/31/2021 | 4/1/2025 | [5 empty] | 1/23/2025 | 1/23/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-561 | TC2 | PHASE 1 | Glory - Glen Campbell 34.5 kV |  | Chestnut Solar LLC | PA | Indiana | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 3/31/2021 | 12/15/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-562 | TC2 | APPLICATION REVIEW | Elderberry 345 kV |  | St. Joseph Energy Center, LLC | IN | St. Joseph | Withdrawn | Generation Interconnection | AEP | 767.0 | 52.0 | 0.0 |  | Energy | Natural Gas | 3/31/2021 | 10/31/2022 | [5 empty] | 4/2/2025 | 4/1/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-564 | TC2 | PHASE 1 | Sulphur Springs 138 kV |  | Heartland Solar, LLC | OH | Crawford | Active | Generation Interconnection | AEP | 49.99 | 49.99 | 32.9 |  | Capacity | Solar | 3/31/2021 | 7/1/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-566 | TC2 | PHASE 1 | Briery - Finneywood 230 kV |  | Gabriel Storage, LLC | VA | Prince Edward | Active | Generation Interconnection | Dominion | 110.0 | 30.0 | 12.0 |  | Capacity | Storage | 3/31/2021 | 3/29/2024 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-568 | TC2 | PHASE 1 | Stink Run – Sundial 138 kV |  | Sundial Energy, LLC | WV |  | Active | Generation Interconnection | AEP | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/31/2021 | 2/25/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-570 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Zeus Energy, LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 400.0 | 400.0 | 100.0 |  | Capacity | Solar | 3/31/2021 | 3/29/2024 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-571 | TC2 | PHASE 1 | Heritage - Wake 500 kV |  | Zeus storage, LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 500.0 | 100.0 | 40.0 |  | Capacity | Storage | 3/31/2021 | 3/29/2024 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-575 | TC2 | PHASE 1 | Crego Rd. 138 kV |  | Leeward Renewable Energy Development, LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 290.0 | 100.0 | 80.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2024 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-580 | TC2 | APPLICATION REVIEW | Rawlings-Clover 500 kV |  | Bellflower Holdings, LLC | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 1/29/2021 | 10/1/2024 | [5 empty] | 3/6/2025 | 3/6/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-581 | TC2 | PHASE 1 | Rawlings-Clover 500 kV |  | Bellflower Holdings, LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 1/29/2021 | 10/1/2024 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-582 | TC2 | PHASE 1 | Flint Run 500 kV |  | CPV Shay, LLC | WV | Doddridge | Active | Generation Interconnection | APS | 2100.0 | 2100.0 | 2075.0 |  | Capacity | Natural Gas | 3/31/2021 | 7/1/2026 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-583 | TC2 | PHASE 1 | Bremo - Cartersville 230 kV |  | Boston Hill Solar, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 115.0 | 115.0 | 69.0 |  | Capacity | Solar | 3/31/2021 | 6/30/2026 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-585 | TC2 | PHASE 1 | Kensignton 138kV |  | Grand Marsh Solar 2, LLC | IL | Kankakee | Active | Generation Interconnection | ComEd | 125.0 | 125.0 | 75.0 |  | Capacity | Solar | 3/31/2021 | 12/1/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-587 | TC2 | PHASE 1 | Graceton 230 kV |  | Old Line Energy, LLC | MD | Harford | Active | Generation Interconnection | BGE | 50.0 | 50.0 | 20.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-589 | TC2 | PHASE 1 | Ravenswood - Hemlock 69 kV |  | Riverlake Energy, LLC | OH | Meigs | Active | Generation Interconnection | AEP | 20.0 | 20.0 | 2.0 |  | Capacity | Solar | 3/31/2021 | 6/1/2024 | [5 empty] | 4/30/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-590 | TC2 | APPLICATION REVIEW | Shingletown-Lewistown 230 kV |  | North Corners Energy, LLC | PA | Huntingdon | Withdrawn | Generation Interconnection | PENELEC | 92.1 | 38.2 | 22.9 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 1/30/2025 | 1/30/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-594 | TC2 | PHASE 1 | Benton-Scott 69 kV II |  | North Corners Energy, LLC | PA | Columbia | Active | Generation Interconnection | PPL | 20.0 | 20.0 | 2.0 |  | Capacity | Solar | 3/31/2021 | 6/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-595 | TC2 | PHASE 1 | LaRue - North Waldo 138 kV |  | Riverlake Energy, LLC | OH | Marion | Active | Generation Interconnection | AEP | 65.0 | 65.0 | 6.5 |  | Capacity | Solar | 3/31/2021 | 6/1/2024 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-599 | TC2 | APPLICATION REVIEW | Furnace Brook-Warren 34.5 kV |  | Oxford Textile Solar Farm, LLC | NJ | Warren | Withdrawn | Generation Interconnection | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 2/18/2025 | 2/18/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-600 | TC2 | PHASE 1 | American Can-BASF 34.5 kV |  | East Asbury Anderson Solar Farm, LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-602 | TC2 | APPLICATION REVIEW | Maysville 69 kV V |  | MC Solar, LLC | PA | Mercer | Withdrawn | Generation Interconnection | ATSI | 50.0 | 0.0 | 0.0 |  | Energy | Storage | 3/31/2021 | 9/15/2022 | [5 empty] | 3/11/2025 | 3/11/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AG2-603 | TC2 | PHASE 1 | Huffman 138 kV |  | Issa Solar LLC | VA | Carroll | Active | Generation Interconnection | AEP | 77.0 | 77.0 | 77.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 10/31/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-606 | TC2 | PHASE 1 | Sunbury-Juniata 500 kV |  | North Corners Energy, LLC | PA | Perry | Active | Generation Interconnection | PPL | 89.0 | 89.0 | 35.6 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 6/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-607 | TC2 | PHASE 1 | St. Johns - Dunbrook 34.5 kV |  | Cauthornville PV I, LLC | VA | King and Queen | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.74 |  | Capacity | Solar | 3/31/2021 | 11/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-615 | TC2 | PHASE 1 | Carlos Junction-Garrett 138 kV |  | Squirrel Run Solar, L.L.C. | MD | Allegany | Active | Generation Interconnection | APS | 100.0 | 100.0 | 62.6 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-616 | TC2 | PHASE 1 | Churchtown - Upper Pittsgrove 138 kV |  | Goldenrod Energy Center, LLC | NJ | Salem | Active | Generation Interconnection | AEC | 50.0 | 50.0 | 32.35 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-617 | TC2 | PHASE 1 | Waugh Chapel 115 kV |  | Dairy Farm Solar, L.L.C. | MD | Anne Arundel | Active | Generation Interconnection | BGE | 55.0 | 55.0 | 33.0 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-618 | TC2 | PHASE 1 | Morgantown 230 kV |  | DESRI Tidewater Development, L.L.C. | MD | Charles | Active | Generation Interconnection | PEPCO | 110.0 | 110.0 | 71.5 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-621 | TC2 | PHASE 1 | Hoytdale 138 kV |  | ACE Development Company, LLC | PA | Beaver | Active | Generation Interconnection | ATSI | 150.0 | 150.0 | 150.0 |  | Capacity | Storage | 3/31/2021 | 5/31/2023 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-625 | TC2 | PHASE 1 | Pequest River-Furnace Brook Tap 34.5 kV II |  | Chamberlain West Solar Farm LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-626 | TC2 | PHASE 1 | Pequest River-Furnace Brook Tap 34.5 kV III |  | Chamberlain East Solar Farm LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 12.5 | 12.5 | 5.25 |  | Capacity | Solar | 3/31/2021 | 4/30/2021 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-627 | TC2 | PHASE 1 | Woodstown-High Street 69 kV |  | South Harrison Solar, LLC | NJ | Gloucester | Active | Generation Interconnection | AEC | 40.0 | 40.0 | 24.0 |  | Capacity | Solar | 3/31/2021 | 6/30/2024 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-631 | TC2 | PHASE 1 | Boydton Plank Road 115 kV |  | ACE Development Company, LLC | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 3/31/2021 | 4/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-637 | TC2 | PHASE 1 | Randolph - Hodgin 138 kV |  | ACE Development Company, LLC | IN | Randolph | Active | Generation Interconnection | AEP | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 3/31/2021 | 4/1/2025 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-639 | TC2 | PHASE 1 | Chickahominy 230 kV |  | ACE Development Company II, LLC | VA | Charles City | Active | Generation Interconnection | Dominion | 340.0 | 20.0 | 20.0 |  | Capacity | Storage | 3/31/2021 | 4/1/2025 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-640 | TC2 | APPLICATION REVIEW | Danieltown DP–Brunswick 69 kV |  | ACE Development Company II, LLC | VA | Brunswick | Withdrawn | Generation Interconnection | Dominion | 46.8 | 0.0 | 18.7 |  | Capacity | Storage | 3/31/2021 | 4/1/2025 | [5 empty] | 3/31/2025 | 2/24/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AG2-646 | TC2 | PHASE 1 | Chesterfield 230 kV |  | Pine Tree Power Management LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 200.0 | 200.0 | 200.0 |  | Capacity | Storage | 3/31/2021 | 6/10/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-654 | TC2 | PHASE 1 | Craigsville - Leards Crossing 12 kV |  | IMG Solar LLC | PA | Armstrong | Active | Generation Interconnection | APS | 14.7 | 14.7 | 8.8 |  | Capacity | Solar | 3/31/2021 | 6/1/2022 | [5 empty] | 4/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-655 | TC2 | PHASE 1 | Mt. Storm-Bismark 500 kV |  | Mount Storm Solar, LLC | WV | Grant | Active | Generation Interconnection | Dominion | 500.0 | 500.0 | 210.0 |  | Capacity | Solar | 3/31/2021 | 6/30/2024 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-657 | TC2 | PHASE 1 | Carbondale 138 kV |  | Mammoth Solar, LLC | WV | Fayette | Active | Generation Interconnection | AEP | 90.0 | 90.0 | 37.8 |  | Capacity | Solar | 3/31/2021 | 6/30/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-658 | TC2 | PHASE 1 | Cowen 138 kV |  | Halo Solar WV LLC | WV | Webster | Active | Generation Interconnection | APS | 210.0 | 210.0 | 135.3 |  | Capacity | Solar | 3/31/2021 | 12/31/2024 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-659 | TC2 | PHASE 1 | Kerr Dam – Hawtree 115 kV |  | Bracey PV I, LLC | VA | Mecklenburg | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 3/31/2021 | 7/30/2025 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-660 | TC2 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 600.0 | 0.0 | 20.0 |  | Capacity | Storage | 3/31/2021 | 11/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-661 | TC2 | PHASE 1 | Hopewell - Colonial Trail 230 kV |  | Wild Indigo Energy Center LLC | VA | Surry | Active | Generation Interconnection | Dominion | 150.0 | 0.0 | 20.0 |  | Capacity | Storage | 3/31/2021 | 10/31/2024 | [5 empty] | 4/30/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-665 | TC2 | PHASE 1 | Corwin - Elk 138 kV |  | Hamden Energy LLC | OH | Jackson | Active | Generation Interconnection | AEP | 180.0 | 90.0 | 54.0 |  | Capacity | Solar,Storage,Hybrid | 3/31/2021 | 12/31/2024 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-668 | TC2 | PHASE 1 | Harvey Run 34.5 kV |  | Du Bois PV I, LLC | PA | Clearfield | Withdrawn | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.5 |  | Capacity | Solar | 3/31/2021 | 11/1/2023 | [5 empty] | 4/22/2025 | 4/22/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-670 | TC2 | PHASE 1 | Greensburg 69 kV |  | Innergex Renewable Development USA, LLC | KY | Green | Active | Generation Interconnection | EKPC | 75.0 | 75.0 | 45.0 |  | Capacity | Solar | 3/31/2021 | 12/31/2023 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-675 | TC2 | PHASE 1 | Cordova 345 kV |  | Gipper Solar Farm, LLC | IL | Rock Island | Active | Generation Interconnection | ComEd | 335.0 | 80.0 | 32.0 |  | Capacity | Storage | 3/31/2021 | 10/1/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AG2-690 | TC2 | APPLICATION REVIEW | Sullivan - Rockport 765 kV |  | Solar Prairie Holdco, LLC | IN | Sullivan | Withdrawn | Generation Interconnection | AEP | 300.0 | 300.0 | 120.0 |  | Capacity | Storage | 3/31/2021 | 6/1/2024 | [5 empty] | 1/29/2025 | 1/29/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-004 | TC2 | PHASE 1 | Avon - Renaker 138 kV |  | SR Fayette, LLC | KY | Fayette | Active | Generation Interconnection | EKPC | 40.0 | 40.0 | 24.0 |  | Capacity | Solar | 4/7/2021 | 12/1/2023 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-005 | TC2 | PHASE 1 | East Towanda-South Troy 115 kV II | Godfrey Solar III | Franklin Energy, LLC | PA | Bradford | Active | Generation Interconnection | PENELEC | 51.0 | 20.0 | 14.0 |  | Capacity | Solar | 4/9/2021 | 9/30/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-012 | TC2 | PHASE 1 | Louisa - North Anna 230 kV |  | Two Oaks Storage, LLC | VA | Louisa | Active | Generation Interconnection | Dominion | 50.0 | 50.0 | 20.0 |  | Capacity | Storage | 4/19/2021 | 3/29/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-027 | TC2 | PHASE 1 | Cartanza 230 kV |  | Calpine Mid-Atlantic Development, LLC | DE | Kent | Active | Generation Interconnection | DPL | 25.0 | 25.0 | 15.0 |  | Capacity | Solar | 5/20/2021 | 6/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-033 | TC2 | PHASE 1 | Sligo 34.5 kV |  | Sligo Solar, LLC | NC | Currituck | Active | Generation Interconnection | Dominion | 19.5 | 19.5 | 13.0 |  | Capacity | Solar | 6/14/2021 | 8/15/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-034 | TC2 | PHASE 1 | Patton Road Junction - Summer Shade 69 kV | Scotland Solar | Scotland Solar, LLC | KY | Barren | Active | Generation Interconnection | EKPC | 100.0 | 100.0 | 70.0 |  | Capacity | Solar | 6/14/2021 | 11/15/2025 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-035 | TC2 | PHASE 1 | Plymouth 34.5 kV |  | Park Solar, LLC | NC | Washington | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 13.5 |  | Capacity | Solar | 6/14/2021 | 9/15/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-040 | TC2 | PHASE 1 | Mackeys - Creswell 115 kV |  | ACE Development Company, LLC | NC | Washington | Active | Generation Interconnection | Dominion | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 6/23/2021 | 7/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-041 | TC2 | PHASE 1 | Pennville 138 kV |  | ACE Development Company, LLC | IN | Jay | Active | Generation Interconnection | AEP | 125.0 | 125.0 | 75.0 |  | Capacity | Solar | 6/23/2021 | 7/1/2025 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-042 | TC2 | PHASE 1 | Providence Forge-Turner 115kV | Stony Run Solar Project, LLC | Stony Run Solar Project, LLC | VA | Charles City | Active | Generation Interconnection | Dominion | 154.0 | 154.0 | 99.9 |  | Capacity | Solar | 6/25/2021 | 9/1/2024 | [5 empty] | 4/14/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-044 | TC2 | PHASE 1 | Nelson - Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 800.0 | 200.0 | 120.0 |  | Capacity | Solar | 6/30/2021 | 12/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-045 | TC2 | APPLICATION REVIEW | Zion Energy Center 345 kV |  | Zion Energy LLC | IL | Lake | Withdrawn | Generation Interconnection | ComEd | 658.0 | 23.0 | 13.8 |  | Capacity | Solar | 7/1/2021 | 6/1/2023 | [5 empty] | 2/28/2025 | 2/27/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-046 | TC2 | PHASE 1 | Peach Bottom 500 kV |  | Calpine Mid Merit, LLC | PA | York | Withdrawn | Generation Interconnection | PECO | 905.0 | 25.0 | 15.0 |  | Capacity | Solar | 7/1/2021 | 6/1/2023 | [5 empty] | 4/25/2025 | 4/25/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-047 | TC2 | PHASE 1 | Marengo - Belvidere 138 kV |  | BLUE STONE RENEWABLE XIV LLC | IL | Boone | Active | Generation Interconnection | ComEd | 58.6 | 58.6 | 37.0 |  | Capacity | Solar | 7/6/2021 | 9/13/2022 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-050 | TC2 | PHASE 1 | Eclipse-Piney 115 kV |  | Deal Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 50.0 | 50.0 | 30.0 |  | Capacity | Solar | 7/7/2021 | 7/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-051 | TC2 | PHASE 1 | Eclipse-Piney 115 kV II |  | Deal Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 80.0 | 30.0 | 18.0 |  | Capacity | Solar | 7/7/2021 | 7/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-054 | TC2 | PHASE 1 | Upton-Whitings 34.5 kV |  | Pasadena Pemberton Solar Farm, LLC | NJ | Ocean | Active | Generation Interconnection | JCPL | 8.25 | 8.25 | 3.465 |  | Capacity | Solar | 7/9/2021 | 7/8/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-055 | TC2 | PHASE 1 | Kyger Creek - Don Marquis 345 kV |  | Furnace Solar, LLC | OH | Jackson | Active | Generation Interconnection | OVEC | 220.0 | 220.0 | 154.0 |  | Capacity | Solar | 7/14/2021 | 11/15/2026 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-056 | TC2 | PHASE 1 | Red House D.P. 115kV | Sugar Solar LLC | Sugar Solar, LLC | VA | Campbell | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 68.5 |  | Capacity | Solar | 7/14/2021 | 11/15/2026 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-057 | TC2 | PHASE 1 | Edgewood 12.47 kV |  | Kumquat & Citron Cleantech LLC | MD | Wicomico | Active | Generation Interconnection | DPL | 7.2 | 7.2 | 3.0 |  | Capacity | Solar | 7/15/2021 | 1/31/2023 | [5 empty] | 3/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-059 | TC2 | PHASE 1 | Sharp Road 69 kV |  | Frasier Solar, LLC | OH | Knox | Active | Generation Interconnection | AEP | 120.0 | 40.0 | 24.0 |  | Capacity | Solar | 7/16/2021 | 12/31/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-060 | TC2 | PHASE 1 | Cardington-Liberty 69 kV III | Crossroads Solar I | Crossroads Solar I, LLC | OH | Morrow | Active | Generation Interconnection | ATSI | 94.0 | 20.0 | 12.0 |  | Capacity | Solar | 7/20/2021 | 12/31/2024 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-065 | TC2 | PHASE 1 | Hopewell 34.5kV | Churchill Storage Solutions LLC | Churchill Storage Solutions LLC | VA | City of Hopewell | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 8.0 |  | Capacity | Storage | 7/27/2021 | 5/1/2023 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-066 | TC2 | PHASE 1 | Hopewell 34.5kV | Churchill Storage Solutions LLC | Churchill Storage Solutions LLC | VA | City of Hopewell | Active | Generation Interconnection | Dominion | 10.0 | 10.0 | 4.0 |  | Capacity | Storage | 7/27/2021 | 5/1/2023 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-069 | TC2 | PHASE 1 | Jerome – Mohicanville 69 kV |  | JR ME LLC | OH | Ashland | Active | Generation Interconnection | ATSI | 17.0 | 17.0 | 10.2 |  | Capacity | Solar | 7/28/2021 | 11/30/2023 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-070 | TC2 | PHASE 1 | Jerome – Mohicanville 69 kV |  | JR ME LLC | OH | Ashland | Active | Generation Interconnection | ATSI | 34.0 | 17.0 | 10.2 |  | Capacity | Solar | 7/28/2021 | 11/30/2023 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-071 | TC2 | PHASE 1 | Midlothian 34.5 kV |  | Virginia Electric and Power Company | VA | Powhatan | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 7/29/2021 | 7/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-072 | TC2 | PHASE 1 | Lick Fork 69 kV |  | Bold Camp CF Solar, LLC | VA | Dickenson | Active | Generation Interconnection | AEP | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 7/29/2021 | 3/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-073 | TC2 | PHASE 1 | Lick Fork 69 kV |  | Bold Camp CF Solar, LLC | VA | Dickenson | Active | Generation Interconnection | AEP | 40.0 | 20.0 | 12.0 |  | Capacity | Solar | 7/29/2021 | 3/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-075 | TC2 | PHASE 1 | North Waldo - Wild Creek 138 kV |  | Chestnut Solar, LLC | OH | Marion | Active | Generation Interconnection | AEP | 68.0 | 8.0 | 24.7 |  | Capacity | Solar | 7/29/2021 | 12/31/2022 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-076 | TC2 | APPLICATION REVIEW | Loyalhanna - Reed Junction 25 kV |  | CP Loyalhanna Creek LLC | PA | Westmoreland | Withdrawn | Generation Interconnection | APS | 18.0 | 18.0 | 9.0 |  | Capacity | Solar | 7/29/2021 | 12/31/2023 | [5 empty] | 3/14/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-081 | TC2 | PHASE 1 | Knob Lick 69kV |  | Wildrye Solar LLC | KY | Metcalfe | Active | Generation Interconnection | EKPC | 60.0 | 60.0 | 36.0 |  | Capacity | Solar | 7/30/2021 | 12/20/2024 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-082 | TC2 | PHASE 1 | Knob Lick 69kV |  | Wildrye Solar LLC | KY | Metcalfe | Active | Generation Interconnection | EKPC | 104.0 | 44.0 | 26.4 |  | Capacity | Solar | 7/30/2021 | 12/20/2024 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-083 | TC2 | PHASE 1 | Summer Shade - Green County 161 kV |  | Coneflower Solar 2 LLC | KY | Metcalfe | Active | Generation Interconnection | EKPC | 250.0 | 100.0 | 60.0 |  | Capacity | Solar | 7/30/2021 | 12/20/2024 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-086 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 90.0 | 90.0 | 90.0 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-087 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 110.0 | 20.0 | 20.0 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 5/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-088 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 130.0 | 20.0 | 20.0 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 5/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-089 | TC2 | PHASE 1 | Morrisville 230kV | Summersweet Energy Center, LLC | Summersweet Energy Center, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 150.0 | 20.0 | 20.0 |  | Capacity | Storage | 7/30/2021 | 7/31/2023 | [5 empty] | 5/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-091 | TC2 | PHASE 1 | Ahoskie 34.5kV |  | Colice Hall Solar, LLC | NC | Hertford | Active | Generation Interconnection | Dominion | 17.0 | 0.0 | 0.0 |  | Energy | Storage | 7/30/2021 | 11/15/2024 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-092 | TC2 | PHASE 1 | SedgeHill - Person 230 kV |  | Scarlet Oak Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 90.0 | 90.0 | 54.0 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 6/1/2025 | [5 empty] | 3/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-094 | TC2 | PHASE 1 | Wells - Shinrock 69 kV I | Norwalk Solar I | Norwalk Solar, LLC | OH | Huron | Active | Generation Interconnection | ATSI | 49.9 | 49.9 | 29.94 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 6/1/2025 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-098 | TC2 | PHASE 1 | Wolf Glade-West Carroll 138 kV |  | Pipers Gap Solar, LLC | VA | Carroll | Active | Generation Interconnection | AEP | 40.0 | 40.0 | 24.0 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 6/1/2025 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-102 | TC2 | PHASE 1 | Seward-Glory 115 kV |  | Clarke Run Solar LLC | PA | Indiana | Active | Generation Interconnection | PENELEC | 100.0 | 100.0 | 63.4 |  | Capacity | Solar | 7/30/2021 | 12/31/2024 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-106 | TC2 | PHASE 1 | Winterpock 34.5kV | 360 Solar Center, LLC | 360 Solar Center, LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 26.0 | 26.0 | 15.6 |  | Capacity | Solar | 8/4/2021 | 10/31/2023 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-107 | TC2 | PHASE 1 | Winterpock 34.5kV | 360 Solar Center, LLC | 360 Solar Center, LLC | VA | Chesterfield | Active | Generation Interconnection | Dominion | 26.0 | 26.0 | 15.6 |  | Capacity | Solar | 8/4/2021 | 10/31/2023 | [5 empty] | 4/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-108 | TC2 | PHASE 1 | Spruance NUG 230 kV |  | Spruance Operating Services LLC | VA | City of Richmond | Active | Generation Interconnection | Dominion | 66.0 | 0.0 | 9.0 |  | Capacity | Natural Gas | 8/4/2021 | 6/1/2022 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-124 | TC2 | PHASE 1 | Vint Hill 34.5kV | Reid Energy Center, LLC | Reid Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-125 | TC2 | PHASE 1 | Sycoline 34.5kV | Evergreen Energy Center, LLC | Evergreen Energy Center, LLC | VA | Loudoun | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-127 | TC2 | PHASE 1 | Railroad 34.5kV | Railroad Energy Center, LLC | Railroad Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-128 | TC2 | PHASE 1 | Railroad 34.5kV | Bethlehem Energy Center, LLC | Bethlehem Energy Center, LLC | VA | Prince William | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 0.0 |  | Energy | Storage | 8/23/2021 | 12/23/2022 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-133 | TC2 | PHASE 1 | Saltville - Tazewell 138 kV |  | Hermes Solar LLC | VA | Tazewell | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 8/23/2021 | 12/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-136 | TC2 | PHASE 1 | Falcon -Middle Creek 46 kV |  | Big Sandy Renewables LLC | KY |  | Active | Generation Interconnection | AEP | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 8/25/2021 | 12/31/2024 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-138 | TC2 | PHASE 1 | Penniman 34.5 kV |  | Virginia Electric and Power Company | VA | City of Williamsburg | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 8.4 |  | Capacity | Solar | 7/30/2021 | 7/15/2022 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-140 | TC2 | PHASE 1 | Vasco 138 kV |  | Red Stone Renewables, LLC | PA | Westmoreland | Active | Generation Interconnection | APS | 150.0 | 150.0 | 115.0 |  | Capacity | Solar,Storage,Hybrid | 7/30/2021 | 12/31/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-144 | TC2 | PHASE 1 | Peter's Mountain 138 kV |  | Aries Solar Project LLC | VA | Giles | Active | Generation Interconnection | AEP | 120.0 | 120.0 | 50.4 |  | Capacity | Solar | 8/26/2021 | 12/31/2024 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-145 | TC2 | PHASE 1 | Peter's Mountain 138 kV |  | Aries Solar Project LLC | VA | Giles | Active | Generation Interconnection | AEP | 200.0 | 80.0 | 80.0 |  | Capacity | Storage | 8/26/2021 | 12/31/2024 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-146 | TC2 | PHASE 1 | White Rock - Wayne 345 kV |  | Mound Solar, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 8/26/2021 | 12/31/2025 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-147 | TC2 | PHASE 1 | White Rock - Wayne 345 kV |  | Mound Solar, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 400.0 | 200.0 | 120.0 |  | Capacity | Solar | 8/27/2021 | 12/31/2025 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-148 | TC2 | PHASE 1 | White Rock - Wayne 345 kV |  | Mound Solar, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 600.0 | 200.0 | 120.0 |  | Capacity | Solar | 8/26/2021 | 12/31/2025 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-150 | TC2 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 1000.0 | 200.0 | 120.0 |  | Capacity | Solar | 8/28/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-151 | TC2 | PHASE 1 | Nelson-Electric Junction 345 kV |  | Steward Creek Solar, LLC | IL | Lee | Active | Generation Interconnection | ComEd | 1200.0 | 200.0 | 120.0 |  | Capacity | Solar | 8/27/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-152 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 150.0 | 0.0 | 30.0 |  | Capacity | Storage | 8/27/2021 | 12/31/2025 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-153 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 8/27/2021 | 12/31/2025 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-154 | TC2 | PHASE 1 | Dumont 345 kV |  | Dumont Solar, LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 150.0 | 0.0 | 30.0 |  | Capacity | Storage | 8/27/2021 | 12/31/2025 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-157 | TC2 | PHASE 1 | Penniman - Waller 230 kV |  | Delorean Power LLC | VA | York | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 8/31/2021 | 1/1/2025 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-158 | TC2 | PHASE 1 | Eclipse-Piney 115 kV III |  | Deal Solar LLC | PA | Venango | Active | Generation Interconnection | PENELEC | 80.0 | 0.0 | 30.0 |  | Capacity | Storage | 9/1/2021 | 8/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-159 | TC2 | PHASE 1 | Conneaut-Conneaut Tap 69 kV | ASD Carmen PA2 Solar | ASD Carmen PA2 Solar LLC | PA | Crawford | Active | Generation Interconnection | ATSI | 20.0 | 20.0 | 13.9 |  | Capacity | Solar | 8/30/2021 | 11/1/2023 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-160 | TC2 | APPLICATION REVIEW | Tower Hill 34.5 kV | ASD Warner PA2 Solar LLC | ASD Warner PA2 Solar LLC | PA | Tioga | Withdrawn | Generation Interconnection | PENELEC | 20.0 | 20.0 | 13.3 |  | Capacity | Solar | 8/31/2021 | 11/1/2023 | [5 empty] | 3/28/2025 | 3/28/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-162 | TC2 | PHASE 1 | Curryville-RKB-Yellow Creek 23 kV | ASD Woodbury PA2 Solar I | ASD Woodbury PA2 Solar I LLC | PA | Bedford | Active | Generation Interconnection | PENELEC | 16.0 | 16.0 | 11.0 |  | Capacity | Solar | 8/31/2021 | 11/1/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-163 | TC2 | APPLICATION REVIEW | Millersburg 69 kV |  | Derby Solar Farm, LLC | KY |  | Withdrawn | Generation Interconnection | EKPC | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/1/2021 | 7/31/2025 | [5 empty] | 1/28/2025 | 1/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-164 | TC2 | PHASE 1 | Oak Level - Tank Hill 138 kV |  | Robin Ridge Solar, LLC | VA | Franklin | Active | Generation Interconnection | AEP | 35.0 | 35.0 | 21.0 |  | Capacity | Solar | 8/31/2021 | 12/20/2024 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-165 | TC2 | PHASE 1 | Will County 138 kV |  | NRG Midwest Storage LLC | IL | Will | Active | Generation Interconnection | ComEd | 72.0 | 72.0 | 0.0 |  | Energy | Storage | 8/31/2021 | 6/1/2025 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-170 | TC2 | PHASE 1 | Columbia DP 115kV | Horsepen Creek Solar I | Horsepen Creek Solar, LLC | VA | Goochland | Active | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 8/27/2021 | 12/20/2024 | [5 empty] | 3/27/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-179 | TC2 | PHASE 1 | Edinburg - Woodstock DP 34.5 kV |  | Valley Overlook Solar, LLC | VA | Shenandoah | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 8/31/2021 | 12/31/2022 | [5 empty] | 4/9/2025 | 4/9/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-185 | TC2 | APPLICATION REVIEW | Benn's Church - Smithfield 34.5 kV |  | Prairie Solar, LLC | VA | Isle of Wight | Withdrawn | Generation Interconnection | Dominion | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 8/31/2021 | 12/31/2022 | [5 empty] | 3/31/2025 | 2/25/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-188 | TC2 | PHASE 1 | Pigeon Creek 138 kV |  | Twisted Gun Solar, LLC | WV | Mingo | Active | Generation Interconnection | AEP | 140.0 | 140.0 | 84.0 |  | Capacity | Solar | 8/31/2021 | 6/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-189 | TC2 | PHASE 1 | Hopkins 138 kV |  | Hobet Solar I, LLC | WV |  | Active | Generation Interconnection | AEP | 140.0 | 140.0 | 84.0 |  | Capacity | Solar | 8/31/2021 | 6/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-196 | TC2 | PHASE 1 | Prairie 345 kV |  | Pleasant Grove Solar 2, LLC | IL | McHenry | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 9/2/2021 | 12/15/2026 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-197 | TC2 | APPLICATION REVIEW | Occoquan 230kV |  | Covanta Energy Marketing LLC | VA | Fairfax | Withdrawn | Generation Interconnection | Dominion | 98.0 | 0.0 | 7.1 |  | Capacity | Biomass | 9/1/2021 | 8/20/2021 | [5 empty] | 3/31/2025 | 3/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-201 | TC2 | PHASE 1 | Allegheny-New Baltimore 115kV | Mountain Ridge Solar | Mango Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 40.0 | 40.0 | 24.0 |  | Capacity | Solar | 9/3/2021 | 8/31/2023 | [5 empty] | 3/20/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-203 | TC2 | PHASE 1 | Allegheny-Somerset 115 kV | Turnpike Solar | Turnpike Solar, LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 70.0 | 70.0 | 42.0 |  | Capacity | Solar | 9/3/2021 | 8/31/2023 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-205 | TC2 | PHASE 1 | Allegheny-New Baltimore 115kV |  | Mango Solar LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 40.0 | 0.0 | 16.0 |  | Capacity | Storage | 9/3/2021 | 8/31/2023 | [5 empty] | 3/20/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-206 | TC2 | PHASE 1 | Bethelboro 138 kV | Lafayette Storage | Lafayette Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 60.0 | 60.0 | 60.0 |  | Capacity | Storage | 9/8/2021 | 12/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-212 | TC2 | PHASE 1 | Bethlehem - Lilly 46 kV | Noels Creek Solar | Noels Creek Solar, LLC | PA | Cambria | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/7/2021 | 12/31/2022 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-215 | TC2 | PHASE 1 | Central VA-Twitty 115 kV |  | Mountain Pine Chase City LLC | VA | Charlotte | Active | Generation Interconnection | Dominion | 31.5 | 31.5 | 18.9 |  | Capacity | Solar,Storage,Hybrid | 9/9/2021 | 2/1/2025 | [5 empty] | 4/25/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-216 | TC2 | PHASE 1 | Smithfield-Surry 230 kV |  | Mountain Pine Surry LLC | VA | Isle of Wight | Active | Generation Interconnection | Dominion | 99.0 | 99.0 | 79.2 |  | Capacity | Solar,Storage,Hybrid | 9/8/2021 | 2/1/2025 | [5 empty] | 4/25/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-217 | TC2 | PHASE 1 | Kidds Store - Fork Union 115 kV II |  | Mountain Pine Kidds Store LLC | VA | Fluvanna | Active | Generation Interconnection | Dominion | 57.0 | 57.0 | 34.2 |  | Capacity | Solar | 9/9/2021 | 2/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-220 | TC2 | PHASE 1 | Remington CT 230 kV |  | Virginia Electric and Power Company | VA | Fauquier | Active | Generation Interconnection | Dominion | 100.0 | 0.0 | 60.0 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-221 | TC2 | PHASE 1 | Heritage 500 kV |  | Virginia Electric and Power Company | VA | Brunswick | Active | Generation Interconnection | Dominion | 75.0 | 0.0 | 45.0 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-222 | TC2 | PHASE 1 | Ladysmith CT 230 kV |  | Virginia Electric and Power Company | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 50.0 | 0.0 | 30.0 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 4/29/2025 | 4/29/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-223 | TC2 | PHASE 1 | Poland Rd-Runway DP 230 kV |  | Virginia Electric and Power Company | VA | Loudoun | Active | Generation Interconnection | Dominion | 150.0 | 0.0 | 20.0 |  | Capacity | Storage | 9/8/2021 | 12/1/2023 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-226 | TC2 | PHASE 1 | Clubhouse - Sapony 230 kV |  | Virginia Electric and Power Company | VA | City of Emporia | Withdrawn | Generation Interconnection | Dominion | 115.0 | 115.0 | 69.0 |  | Capacity | Solar | 9/8/2021 | 12/1/2025 | [5 empty] | 4/11/2025 | 4/11/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-227 | TC2 | PHASE 1 | Flemming - Fremont 69 kV |  | Virginia Electric and Power Company | VA | Wise | Active | Generation Interconnection | AEP | 51.3 | 51.3 | 30.78 |  | Capacity | Solar | 9/8/2021 | 12/1/2025 | [5 empty] | 4/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-234 | TC2 | PHASE 1 | Wempletown 345 kV |  | Gemini Solar LLC | IL | Winnebago | Active | Generation Interconnection | ComEd | 224.0 | 224.0 | 29.12 |  | Capacity | Solar | 9/10/2021 | 11/21/2025 | [5 empty] | 4/10/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-239 | TC2 | PHASE 1 | Upchurch - Zula 69 kV |  | Clinton Solar, LLC | KY | Boone | Active | Generation Interconnection | EKPC | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-241 | TC2 | PHASE 1 | Cobbs Creek - James River Industrial 115kV | Energix Westmoreland LLC | Energix Westmoreland, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 3/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-247 | TC2 | PHASE 1 | Lardin - Lake Lynn 138kV | Poseidon Solar 1 | Poseidon Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 40.0 | 40.0 | 24.0 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-248 | TC2 | PHASE 1 | Lardin - Lake Lynn 138kV | Poseidon Solar 2 | Poseidon Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 65.0 | 25.0 | 15.0 |  | Capacity | Solar | 9/9/2021 | 12/31/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-249 | TC2 | PHASE 1 | Lardin – Lake Lynn 138kV | Poseidon Storage | Poseidon Energy, LLC | PA | Fayette | Active | Generation Interconnection | APS | 145.0 | 80.0 | 80.0 |  | Capacity | Storage | 9/9/2021 | 12/31/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-251 | TC2 | PHASE 1 | Todds Tavern- Spotsylvania/Goldsdale 115kV | Tavern Energy LLC | Tavern Energy, LLC | VA | Spotsylvania | Active | Generation Interconnection | Dominion | 50.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/9/2021 | 12/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-254 | TC2 | PHASE 1 | Greenland Gap 500 kV II | Mount Storm Repower | Renew Development Holdco LLC | WV | Barbour | Active | Generation Interconnection | APS | 171.4 | 171.4 | 36.538 |  | Capacity | Wind | 9/10/2021 | 7/31/2025 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-255 | TC2 | PHASE 1 | Greenland Gap III | Mount Storm Repower BESS 1 | Mount Storm BESS 1 LLC | WV | Grant | Active | Generation Interconnection | APS | 240.0 | 240.0 | 240.0 |  | Capacity | Storage | 9/9/2021 | 7/31/2025 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-257 | TC2 | PHASE 1 | Broadway - Washington 34.5 kV | Kober Solar Farm | CEP NJ Kober Land LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/9/2021 | 12/23/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-258 | TC2 | PHASE 1 | Belford - Keansburg 34.5 kV | Port Belford Solar Farm | Port Belford Solar Farm, LLC | NJ | Monmouth | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/10/2021 | 12/23/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-260 | TC2 | PHASE 1 | New Freedom - Monroe 230 kV |  | Haddy Energy Storage LLC | NJ | Camden | Active | Generation Interconnection | AEC | 300.0 | 300.0 | 300.0 |  | Capacity | Storage | 9/10/2021 | 6/30/2025 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-261 | TC2 | PHASE 1 | Northeast - Riverside 230 kV | Pulaski Energy Storage | Pulaski Energy Storage LLC | MD | Baltimore County | Active | Generation Interconnection | BGE | 135.0 | 135.0 | 135.0 |  | Capacity | Storage | 9/10/2021 | 6/30/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-263 | TC2 | PHASE 1 | Chancellor 115 kV |  | Scarlet Energy Storage LLC | VA | Spotsylvania | Active | Generation Interconnection | Dominion | 200.0 | 200.0 | 200.0 |  | Capacity | Storage | 9/9/2021 | 6/30/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-265 | TC2 | PHASE 1 | Winslow - Monroe 69kV | Winslow Landfill Solar Farm | Winslow LF Solar Farm, LLC | NJ | Camden | Active | Generation Interconnection | AEC | 29.4 | 29.4 | 12.35 |  | Capacity | Solar | 9/10/2021 | 12/23/2022 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-268 | TC2 | PHASE 1 | Seward-Glory 115 kV II | Clark Run Solar BESS | Clarke Run Solar LLC | PA | Indiana | Active | Generation Interconnection | PENELEC | 100.0 | 0.0 | 36.6 |  | Capacity | Storage | 9/9/2021 | 12/31/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-269 | TC2 | PHASE 1 | Claytor 138 kV |  | Claytor Energy Storage, LLC | VA | Pulaski | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/9/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-271 | TC2 | PHASE 1 | Cashie 230 kV |  | Merry Hill PV I, LLC | NC | Bertie | Active | Generation Interconnection | Dominion | 110.0 | 40.0 | 24.0 |  | Capacity | Solar | 9/9/2021 | 9/20/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-272 | TC2 | PHASE 1 | Argenta - Twin Branch 345 kV |  | Bankson Solar Project, LLC | MI | Van Buren | Active | Generation Interconnection | AEP | 185.0 | 185.0 | 123.9 |  | Capacity | Solar | 9/10/2021 | 5/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-274 | TC2 | PHASE 1 | Butler 69 kV |  | Vineland Newfield Solar Farm, LLC | NJ | Gloucester | Active | Generation Interconnection | AEC | 16.7 | 16.7 | 7.0 |  | Capacity | Solar | 9/9/2021 | 12/23/2022 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-280 | TC2 | PHASE 1 | Jetersville-Ponton 115 kV |  | Amelia Energy Facility, LLC | VA | Amelia | Active | Generation Interconnection | Dominion | 106.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/9/2021 | 12/12/2023 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-281 | TC2 | PHASE 1 | Bluegrass Parkway Tap - Woodlawn 69 kV |  | Soltage KY DevCo, LLC | KY | Nelson | Active | Generation Interconnection | EKPC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/9/2021 | 6/7/2024 | [5 empty] | 4/10/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-282 | TC2 | PHASE 1 | Galion - Ohio Central 345 kV |  | Woodbury Solar, LLC | OH | Morrow | Active | Generation Interconnection | AEP | 150.0 | 150.0 | 90.0 |  | Capacity | Solar | 9/9/2021 | 5/1/2025 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-283 | TC2 | PHASE 1 | Mount Storm-Pruntytown 500kV | CPV Wilson Solar | CPV Wilson Solar, LLC | MD | Garrett | Active | Generation Interconnection | APS | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 9/9/2021 | 10/31/2024 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-285 | TC2 | PHASE 1 | Sandwich 138 kV |  | Somonauk Solar LLC | IL | DeKalb | Active | Generation Interconnection | ComEd | 86.0 | 86.0 | 11.18 |  | Capacity | Solar | 9/9/2021 | 12/31/2025 | [5 empty] | 4/15/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-290 | TC2 | PHASE 1 | BASF - Washburn Solar 34.5 kV | Changewater Solar Farm | Changewater Solar Farm LLC | NJ | Warren | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/9/2021 | 9/9/2022 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-291 | TC2 | PHASE 1 | Rock Creek-Hummel Creek 138 kV |  | Invenergy Solar Project Development LLC | IN | Huntington | Active | Generation Interconnection | AEP | 185.0 | 185.0 | 111.0 |  | Capacity | Solar | 9/10/2021 | 12/31/2025 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-292 | TC2 | PHASE 1 | Sullivan 345 kV |  | Trade Post Solar LLC | IN | Sullivan | Active | Generation Interconnection | AEP | 200.0 | 0.0 | 44.0 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-294 | TC2 | PHASE 1 | Mclean 345 kV |  | Blooming Grove Solar Energy Center LLC | IL | McLean | Active | Generation Interconnection | ComEd | 350.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/11/2021 | 12/31/2025 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-295 | TC2 | PHASE 1 | Brokaw to Mt Pulaski 345 kV |  | Invenergy Wind Development LLC | IL | McLean | Active | Generation Interconnection | ComEd | 130.0 | 130.0 | 22.88 |  | Capacity | Wind | 9/10/2021 | 12/31/2025 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-296 | TC2 | PHASE 1 | Beason 345 kV |  | Invenergy Solar Project Development LLC | IL | Logan | Active | Generation Interconnection | ComEd | 175.0 | 60.0 | 60.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-297 | TC2 | PHASE 1 | Kewanee - E.D. Edwards 138 kV |  | Invenergy Wind Development LLC | IL | Stark | Active | Generation Interconnection | ComEd | 200.0 | 200.0 | 26.0 |  | Capacity | Wind | 9/10/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-298 | TC2 | PHASE 1 | Meridian 345 kV |  | Invenergy Storage Development LLC | IN | Whitley | Active | Generation Interconnection | AEP | 75.0 | 75.0 | 75.0 |  | Capacity | Storage | 9/14/2021 | 12/31/2025 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-302 | TC2 | PHASE 1 | Olive - Reynolds 345 kV |  | Bottlebrush Energy Storage LLC | IN | Pulaski | Active | Generation Interconnection | AEP | 275.0 | 75.0 | 75.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-304 | TC2 | PHASE 1 | Delaware-Van Buren 138 kV |  | Meadow Forge Solar Energy LLC | IN | Delaware | Active | Generation Interconnection | AEP | 163.0 | 0.0 | 9.8 |  | Capacity | Solar | 9/11/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-305 | TC2 | PHASE 1 | Olive - Reynolds 345 kV |  | Bottlebrush Solar Energy LLC | IN | Pulaski | Active | Generation Interconnection | AEP | 275.0 | 0.0 | 35.72 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-306 | TC2 | PHASE 1 | Mississinewa-Gaston 138 kV |  | Golden Aster Solar Energy LLC | IN | Grant | Active | Generation Interconnection | AEP | 160.0 | 0.0 | 28.8 |  | Capacity | Solar | 9/11/2021 | 12/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-307 | TC2 | PHASE 1 | Delaware-Van Buren 138 kV |  | Invenergy Storage Development LLC | IN | Delaware | Active | Generation Interconnection | AEP | 213.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/11/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-308 | TC2 | PHASE 1 | Pennville - Adams 138 kV |  | Invenergy Storage Development LLC | IN | Jay | Active | Generation Interconnection | AEP | 205.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-309 | TC2 | PHASE 1 | Kenzie Creek-Colby 138 kV |  | Wingstem Solar Energy LLC | MI | Cass | Active | Generation Interconnection | AEP | 150.0 | 0.0 | 27.0 |  | Capacity | Solar | 9/11/2021 | 12/31/2023 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-311 | TC2 | PHASE 1 | Heartsease DP - Mayo Dunbar 115kV |  | Edgecombe Solar LLC | NC | Edgecombe | Active | Generation Interconnection | Dominion | 75.0 | 0.0 | 2.25 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-313 | TC2 | PHASE 1 | Moshannon-Milesburg 230 kV VII | Nittany North Solar | Invenergy Solar Project Development LLC | PA | Centre | Active | Generation Interconnection | APS | 100.0 | 100.0 | 60.0 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 12/31/2025 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-314 | TC2 | PHASE 1 | East Danville 138 kV |  | Pittsylvania Energy Storage LLC | VA | Pittsylvania | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 9/11/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-316 | TC2 | PHASE 1 | Todd 25 kV |  | Todd Solar LLC | MD | Dorchester | Active | Generation Interconnection | DPL | 20.0 | 0.0 | 4.4 |  | Capacity | Solar | 9/11/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-318 | TC2 | PHASE 1 | Cole 345 kV |  | Invenergy Storage Development LLC | OH | Franklin | Active | Generation Interconnection | AEP | 60.0 | 60.0 | 60.0 |  | Capacity | Storage | 9/11/2021 | 12/31/2025 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-319 | TC2 | PHASE 1 | East Springfield-London 138 kV II | Sloopy Storage | Invenergy Storage Development LLC | OH | Clark | Active | Generation Interconnection | ATSI | 54.0 | 54.0 | 54.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-320 | TC2 | PHASE 1 | Blue Jacket - Kirby 138 kV |  | Invenergy Storage Development LLC | OH | Logan | Active | Generation Interconnection | Dayton | 275.55 | 69.0 | 69.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-321 | TC2 | PHASE 1 | Eldean 138 kV |  | Invenergy Storage Development LLC | OH | Miami | Active | Generation Interconnection | Dayton | 232.0 | 54.0 | 54.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2025 | [5 empty] | 3/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-323 | TC2 | PHASE 1 | Elmont 230 kV |  | Invenergy Storage Development LLC | VA | City of Suffolk | Active | Generation Interconnection | Dominion | 100.0 | 100.0 | 100.0 |  | Capacity | Storage | 9/9/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-324 | TC2 | PHASE 1 | Colonial Trail – Surry 230 kV |  | Invenergy Solar Project Development LLC | VA | Surry | Active | Generation Interconnection | Dominion | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 9/10/2021 | 12/31/2025 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-325 | TC2 | PHASE 1 | Kirk 138 kV |  | Invenergy Storage Development LLC | OH | Licking | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/9/2021 | 12/31/2025 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-327 | TC2 | PHASE 1 | Hardin Switch 345 kV |  | Hardin Solar Energy III LLC | OH | Hardin | Active | Generation Interconnection | AEP | 250.0 | 0.0 | 8.44 |  | Capacity | Solar | 9/10/2021 | 12/31/2023 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-328 | TC2 | PHASE 1 | Blue Jacket - Kirby 138 kV |  | Fountain Point Solar Energy LLC | OH | Logan | Active | Generation Interconnection | Dayton | 275.55 | 0.0 | 21.3 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 12/31/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-331 | TC2 | PHASE 1 | Edinboro South-Erie South 25kV | McLane Solar | IMG Solar LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 19.9 | 19.9 | 11.9 |  | Capacity | Solar | 9/9/2021 | 6/1/2023 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-334 | TC2 | PHASE 1 | Lakehurst - Whitings 34.5 kV | Heritage Solar Farm | Heritage Solar Farm, LLC | NJ | Ocean | Active | Generation Interconnection | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Solar | 9/10/2021 | 9/9/2022 | [5 empty] | 4/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-337 | TC2 | PHASE 1 | Randolph - Hodgin 138 kV |  | Summit Solar, LLC | IN | Randolph | Active | Generation Interconnection | AEP | 46.0 | 46.0 | 39.0 |  | Capacity | Solar | 9/10/2021 | 9/30/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-338 | TC2 | PHASE 1 | New Sub S2354 138kV |  | Prairie Brome Solar LLC | IL | Lee | Active | Generation Interconnection | ComEd | 180.0 | 180.0 | 23.4 |  | Capacity | Solar | 9/10/2021 | 11/21/2025 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-339 | TC2 | PHASE 1 | West Crawford 69 kV |  | River Otter Solar LLC | OH | Wyandot | Active | Generation Interconnection | AEP | 80.0 | 80.0 | 6.76 |  | Capacity | Solar | 9/10/2021 | 11/21/2025 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-340 | TC2 | PHASE 1 | Cheat Lake-Ruthbelle 138 kV | Preston County Solar Project | Rockville Solar LLC | WV | Preston | Active | Generation Interconnection | APS | 48.89 | 48.89 | 29.33 |  | Capacity | Solar | 9/10/2021 | 5/31/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-341 | TC2 | PHASE 1 | ESS-H445 3B 138kv |  | ibVEnergy Partners LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 150.0 | 150.0 | 96.6 |  | Capacity | Solar | 9/10/2021 | 12/7/2025 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-343 | TC2 | PHASE 1 | Crystal Hill DP- Perth 115kV | CEP Solar, LLC | Boxwood Solar, LLC | VA | Halifax | Active | Generation Interconnection | Dominion | 69.0 | 69.0 | 41.4 |  | Capacity | Solar | 9/10/2021 | 9/30/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-345 | TC2 | PHASE 1 | Remington 324 34.5 kV |  | Bealeton Solar, LLC | VA | Fauquier | Active | Generation Interconnection | Dominion | 14.0 | 14.0 | 8.4 |  | Capacity | Solar | 9/10/2021 | 3/31/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-348 | TC2 | PHASE 1 | Indian Creek 34.5 kV |  | Highlands CF Solar, LLC | VA | Wise | Active | Generation Interconnection | AEP | 10.0 | 10.0 | 6.0 |  | Capacity | Solar | 9/10/2021 | 12/21/2023 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-352 | TC2 | APPLICATION REVIEW | Red Eye 138 kV |  | Altavista Solar, LLC | VA | Campbell | Withdrawn | Generation Interconnection | AEP | 40.0 | 40.0 | 40.0 |  | Capacity | Storage | 9/10/2021 | 9/30/2023 | [5 empty] | 4/24/2025 | 3/28/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-353 | TC2 | PHASE 1 | Lena 138 kV |  | Blue Violet Energy, LLC | IL | Stephenson | Active | Generation Interconnection | ComEd | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/10/2021 | 9/10/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-354 | TC2 | PHASE 1 | Lena 138 kV |  | Blue Violet Energy, LLC | IL | Stephenson | Active | Generation Interconnection | ComEd | 60.0 | 40.0 | 40.0 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-355 | TC2 | PHASE 1 | Owl Trap Switching Station 115kV | Carvers Creek LLC | Carvers Creek LLC | VA | Gloucester | Withdrawn | Generation Interconnection | Dominion | 40.0 | 40.0 | 40.0 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 3/25/2025 | 3/25/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-356 | TC2 | PHASE 1 | Kings Creek 138kV |  | Great Bay Solar II, LLC | MD | Somerset | Withdrawn | Generation Interconnection | DPL | 30.0 | 30.0 | 30.0 |  | Capacity | Storage | 9/10/2021 | 9/30/2023 | [5 empty] | 3/19/2025 | 3/14/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-357 | TC2 | PHASE 1 | Pierce Brook-Lewis Run 230kV | McKean Solar 1 - 20 MW | McKean County Solar, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 180.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/10/2021 | 9/10/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-358 | TC2 | PHASE 1 | Pierce Brook-Lewis Run 230kV | McKean Solar 1 - Energy Storage | McKean County Solar, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 200.0 | 20.0 | 20.0 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-359 | TC2 | PHASE 1 | Pierce Brook - Lewis Run 230 kV | McKean Solar 2 - 20 MW | McKean County Solar, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 220.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/10/2021 | 9/10/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-360 | TC2 | PHASE 1 | Pierce Brook - Lewis Run 230 kV | McKean Solar 2 - Energy Storage | McKean County Solar, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 240.0 | 20.0 | 20.0 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-361 | TC2 | APPLICATION REVIEW | Minonk 345 kV |  | Minonk Solar, LLC | IL | Woodford | Withdrawn | Generation Interconnection | ComEd | 50.0 | 50.0 | 50.0 |  | Capacity | Storage | 9/10/2021 | 9/10/2024 | [5 empty] | 3/13/2025 | 3/12/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-367A | TC2 | PHASE 1 | Franklin 138 kV II | Iron Javelin Emerald | Emerald Renewable LLC | PA | Greene | Active | Generation Interconnection | APS | 72.0 | 72.0 | 43.2 |  | Capacity | Solar | 9/10/2021 | 9/10/2023 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-376 | TC2 | PHASE 1 | Ronceverte - Clenden 46 kV | Trillium PV I | Trillium PV I, LLC | WV | Greenbrier | Withdrawn | Generation Interconnection | APS | 28.0 | 28.0 | 16.8 |  | Capacity | Solar | 9/10/2021 | 6/1/2025 | [5 empty] | 4/22/2025 | 4/22/2025 | Customer Initiated Withdrawal |  | InActive |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-377 | TC2 | PHASE 1 | Clover- Farmville 230kV | Keysville PV I, LLC | Keysville PV I, LLC | VA | Prince Edward | Active | Generation Interconnection | Dominion | 186.0 | 186.0 | 111.6 |  | Capacity | Solar | 9/10/2021 | 6/1/2025 | [5 empty] | 4/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-378 | TC2 | PHASE 1 | Lunenburg- Butcher Creek 115kV | Victoria PV I, LLC | Victoria PV I, LLC | VA | Lunenburg | Withdrawn | Generation Interconnection | Dominion | 51.0 | 51.0 | 30.6 |  | Capacity | Solar | 9/10/2021 | 6/1/2025 | [5 empty] | 4/17/2025 | 4/16/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-380 | TC2 | PHASE 1 | Mt Olive - Kenny 69kV |  | Forest Lane Solar, LLC | MD | Worcester | Active | Generation Interconnection | DPL | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/10/2021 | 12/20/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-387 | TC2 | PHASE 1 | Meadowbrook-Greenland Gap 500kV | CPV Capon Springs Wind | CPV Springs Wind, LLC | WV | Hampshire | Active | Generation Interconnection | APS | 150.0 | 150.0 | 22.05 |  | Capacity | Wind | 9/10/2021 | 1/9/2025 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-390 | TC2 | APPLICATION REVIEW | TBD 69 kV | THP Solar 1 | PA Project 1, LLC | PA | Northumberland | Withdrawn | Generation Interconnection | PPL | 19.9 | 19.9 | 14.1 |  | Capacity | Solar | 9/10/2021 | 7/31/2023 | [5 empty] | 3/13/2025 | 3/12/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-391 | TC2 | PHASE 1 | Olive 138 kV | Michiana Solar | ibV Energy Partners LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 67.0 |  | Capacity | Solar | 9/10/2021 | 7/16/2025 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-392 | TC2 | PHASE 1 | Gravel Pit-Kankakee 138 kV |  | ibVEnergy Partners LLC | IN | St. Joseph | Active | Generation Interconnection | AEP | 90.0 | 90.0 | 60.0 |  | Capacity | Solar | 9/10/2021 | 7/16/2025 | [5 empty] | 5/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-396 | TC2 | PHASE 1 | Gary 24.94 kV |  | Ameresco Inc | VA | Lunenburg | Active | Generation Interconnection | Dominion | 12.0 | 12.0 | 1.8 |  | Capacity | Solar | 9/10/2021 | 10/2/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-397 | TC2 | PHASE 1 | Shacklesfords 34.5 kV |  | Ameresco Inc | VA | King and Queen | Active | Generation Interconnection | Dominion | 19.818 | 19.818 | 2.97 |  | Capacity | Solar | 9/10/2021 | 10/2/2023 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-399 | TC2 | PHASE 1 | North Doswell 12.5 kV |  | Ameresco Inc | VA | Hanover | Active | Generation Interconnection | Dominion | 9.87 | 9.87 | 1.48 |  | Capacity | Solar | 9/22/2021 | 10/2/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-408 | TC2 | PHASE 1 | Freeman DP – Lawrenceville 115 kV |  | SR Brunswick, LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 120.0 | 120.0 | 75.0 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-426 | TC2 | PHASE 1 | Gilboa-Jones Branch 138 kV IV |  | Nicholas County Solar Project, LLC | WV | Kanawha | Active | Generation Interconnection | APS | 64.6 | 64.6 | 64.6 |  | Capacity | Storage | 9/11/2021 | 12/31/2023 | [5 empty] | 4/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-426A | TC2 | PHASE 1 | Gilboa-Jones Branch 138 kV V |  | Nicholas County Solar Project, LLC | WV | Nicholas | Active | Generation Interconnection | APS | 96.9 | 32.3 | 32.3 |  | Capacity | Storage | 9/11/2021 | 12/31/2023 | [5 empty] | 4/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-427 | TC2 | PHASE 1 | Tommy Gooch - Garrard County 69 kV |  | ACE Development Company, LLC | KY |  | Active | Generation Interconnection | EKPC | 100.0 | 100.0 | 60.0 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 4/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-428 | TC2 | PHASE 1 | Tommy Gooch - Garrard County 69 kV |  | ACE Development Company, LLC | KY | Boone | Active | Generation Interconnection | EKPC | 100.0 | 0.0 | 40.0 |  | Capacity | Storage | 9/10/2021 | 9/1/2026 | [5 empty] | 4/16/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-429 | TC2 | PHASE 1 | Flemingsburg - Spurlock 138 kV |  | ACE Development Company, LLC | KY | Fleming | Active | Generation Interconnection | EKPC | 90.0 | 90.0 | 54.0 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-432 | TC2 | PHASE 1 | Randolph - Hodgin 138 kV |  | ACE Development Company, LLC | IN | Randolph | Active | Generation Interconnection | AEP | 150.0 | 0.0 | 60.0 |  | Capacity | Storage | 9/10/2021 | 4/1/2025 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-434 | TC2 | PHASE 1 | Carolina- Earleys 115kV | ACE Development Company, LLC | ACE Development Company, LLC | NC | Northhampton | Active | Generation Interconnection | Dominion | 75.0 | 75.0 | 45.0 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-439 | TC2 | PHASE 1 | Buckingham- Farmville 230kV | ACE Development Company, LLC | ACE Development Company, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 85.0 | 85.0 | 51.0 |  | Capacity | Solar | 9/10/2021 | 9/1/2026 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-440 | TC2 | PHASE 1 | Buckingham- Farmville 230kV | ACE Development Company, LLC | ACE Development Company, LLC | VA | Cumberland | Active | Generation Interconnection | Dominion | 85.0 | 0.0 | 34.0 |  | Capacity | Storage | 9/10/2021 | 9/1/2026 | [5 empty] | 3/28/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-446 | TC2 | APPLICATION REVIEW | Sanders DP - Westmoreland 230 kV |  | Kings Highway Solar LLC | VA | Westmoreland | Active | Generation Interconnection | Dominion | 65.0 | 65.0 | 19.5 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 12/2/2024 | [5 empty] | 3/20/2025 | [9 empty] | Not Started |  | Not Started
AH1-447 | TC2 | APPLICATION REVIEW | Axton – Danville #2 138 kV |  | Cascade Energy Storage, LLC | VA | Pittsylvania | Withdrawn | Generation Interconnection | AEP | 60.0 | 60.0 | 36.0 |  | Capacity | Storage | 9/10/2021 | 12/2/2024 | [5 empty] | 3/20/2025 | [9 empty] | Not Started |  | Not Started
AH1-452 | TC2 | PHASE 1 | Clementine-Clementine Jct. 25 kV | McVille Solar | IMG Solar LLC | PA | Armstrong | Active | Generation Interconnection | APS | 19.9 | 19.9 | 8.35 |  | Capacity | Solar | 9/11/2021 | 6/1/2023 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-460 | TC2 | PHASE 1 | Hooversville - Scalp Level 115 kV | Julius Solar | Julius Energy, LLC | PA | Somerset | Active | Generation Interconnection | PENELEC | 66.0 | 66.0 | 39.6 |  | Capacity | Solar | 9/10/2021 | 12/31/2024 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-461 | TC2 | PHASE 1 | Buckhorn 138 kV |  | Lakeside Energy, LLC | VA | Tazewell | Active | Generation Interconnection | AEP | 80.0 | 80.0 | 80.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2024 | [5 empty] | 3/27/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-462 | TC2 | APPLICATION REVIEW | Rachel Hill 115 kV | Black Tulip Storage | Black Tulip Energy, LLC | PA | Cambria | Withdrawn | Generation Interconnection | PENELEC | 60.0 | 60.0 | 60.0 |  | Capacity | Storage | 9/11/2021 | 12/31/2024 | [5 empty] | 3/3/2025 | 2/12/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-463 | TC2 | PHASE 1 | Owingsville - Preston 69 kV |  | Preston Solar, LLC | KY | Bath | Withdrawn | Generation Interconnection | EKPC | 65.0 | 65.0 | 39.0 |  | Capacity | Solar | 9/10/2021 | 12/31/2024 | [5 empty] | 4/23/2025 | 4/22/2025 | Customer Initiated Withdrawal |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-466 | TC2 | APPLICATION REVIEW | Baker - Broadford 765 kV |  | Stambaugh Solar, LLC | KY | Boone | Withdrawn | Generation Interconnection | AEP | 600.0 | 600.0 | 360.0 |  | Capacity | Solar | 9/10/2021 | 12/31/2024 | [5 empty] | 2/25/2025 | 2/25/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-467 | TC2 | APPLICATION REVIEW | Baker - Broadford 765 kV |  | Stambaugh Storage, LLC | KY | Boone | Withdrawn | Generation Interconnection | AEP | 900.0 | 300.0 | 120.0 |  | Capacity | Storage | 9/10/2021 | 12/31/2024 | [5 empty] | 2/25/2025 | 2/25/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-482 | TC2 | PHASE 1 | Olive - Reynolds #2 345 kV |  | Lightsource Renewable Energy Development, LLC | IN | Pulaski | Active | Generation Interconnection | AEP | 338.0 | 78.0 | 78.0 |  | Capacity | Storage | 9/10/2021 | 9/25/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-487 | TC2 | PHASE 1 | Camp Reynolds 12.5 kV | Maysville Solar 2 | PD Solar 11 LLC | PA | Mercer | Active | Generation Interconnection | ATSI | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/10/2021 | 7/30/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-490 | TC2 | PHASE 1 | Venango Junction - Cambridge Springs 34.5 kV | Tamarack Solar 1 | PD Solar 11 LLC | PA | Crawford | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/10/2021 | 7/30/2024 | [5 empty] | 4/17/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-491 | TC2 | PHASE 1 | Union City 34.5 kV | Waterford Solar 1 | PD Solar 11 LLC | PA | Erie | Active | Generation Interconnection | PENELEC | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/11/2021 | 7/30/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-492 | TC2 | PHASE 1 | Bernville 13 kV | Grand View Solar I | PD Solar 2 LLC | PA | Berks | Active | Generation Interconnection | ME | 20.0 | 20.0 | 12.0 |  | Capacity | Solar | 9/11/2021 | 7/30/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-526 | TC2 | PHASE 1 | Knox - Washington CEC 138 kV | Echelon Solar | Echelon Solar LLC | OH | Carroll | Active | Generation Interconnection | ATSI | 80.0 | 80.0 | 42.0 |  | Capacity | Solar,Storage,Hybrid | 9/11/2021 | 10/31/2025 | [5 empty] | 4/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-528 | TC2 | PHASE 1 | Rawlings - Unity 500 kV | Honeybee Solar, LLC | Honeybee Solar Energy, LLC | VA | Brunswick | Active | Generation Interconnection | Dominion | 300.8 | 300.8 | 180.0 |  | Capacity | Solar | 9/10/2021 | 3/30/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-530 | TC2 | APPLICATION REVIEW | Fairfield – Reily 69 kV |  | Riverlake Energy, LLC | OH | Butler | Withdrawn | Generation Interconnection | DEOK | 28.0 | 28.0 | 16.8 |  | Capacity | Solar | 9/10/2021 | 3/1/2025 | [5 empty] | 2/4/2025 | 2/4/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-533 | TC2 | PHASE 1 | Sunbury-Juniata II | Greenwood Solar II | North Corners Energy, LLC | PA | Perry | Active | Generation Interconnection | PPL | 185.2 | 96.2 | 38.5 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-535 | TC2 | PHASE 1 | Nagel - Cane River 230 kV |  | Pecan Flats Energy, LLC | TN | Hawkins | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 40.0 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-536 | TC2 | PHASE 1 | Church-Oil City 138kV |  | Old Line Energy, LLC | MD | Queen Anne's | Active | Generation Interconnection | DPL | 41.8 | 41.8 | 8.5 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-537 | TC2 | PHASE 1 | Pierce - DOE X-530 345 kV |  | Riverlake Energy, LLC | OH | Highland | Active | Generation Interconnection | OVEC | 178.5 | 178.5 | 17.85 |  | Capacity | Solar | 9/11/2021 | 3/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-538 | TC2 | PHASE 1 | East Lima - Haviland 138 kV |  | Riverlake Energy, LLC | OH | Van Wert | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 20.0 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-539 | TC2 | PHASE 1 | South Kenton 138 kV |  | Riverlake Energy, LLC | OH | Hardin | Active | Generation Interconnection | AEP | 129.4 | 129.4 | 25.88 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 4/23/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-540 | TC2 | PHASE 1 | Byron to Wayne 345 kV |  | Golden Harvest Energy, LLC | IL | Ogle | Active | Generation Interconnection | ComEd | 165.0 | 165.0 | 33.0 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-541 | TC2 | PHASE 1 | Chestnut 345 kV |  | Golden Harvest Energy, LLC | IL | DeWitt | Active | Generation Interconnection | ComEd | 92.4 | 92.4 | 27.72 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-542 | TC2 | PHASE 1 | Crissinger-Delaware Business Park 138kV | Green Camp Solar II | Riverlake Energy, LLC | OH | Marion | Active | Generation Interconnection | ATSI | 110.0 | 110.0 | 22.0 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 3/1/2025 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-543 | TC2 | PHASE 1 | Mulberry – Tazewell 345 kV |  | Golden Harvest Energy, LLC | IL | Livingston | Active | Generation Interconnection | ComEd | 157.4 | 157.4 | 31.48 |  | Capacity | Solar,Storage,Hybrid | 9/11/2021 | 3/1/2025 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-545 | TC2 | PHASE 1 | Wylie Ridge-Tidd 345kV | Cornerstone Solar | North Corners Energy, LLC | PA | Washington | Active | Generation Interconnection | APS | 200.0 | 200.0 | 20.0 |  | Capacity | Solar | 9/10/2021 | 3/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-546 | TC2 | PHASE 1 | Bremo - Buckingham 230 kV |  | Mountain Pine Arvonia LLC | VA | Buckingham | Active | Generation Interconnection | Dominion | 79.8 | 79.8 | 47.8 |  | Capacity | Solar | 9/10/2021 | 2/1/2025 | [5 empty] | 4/7/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-549 | TC2 | PHASE 1 | Allen - RP Mone 345 kV |  | Leeward Renewable Energy Development, LLC | IN | Allen | Active | Generation Interconnection | AEP | 180.0 | 180.0 | 108.0 |  | Capacity | Solar | 9/10/2021 | 12/31/2025 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-552 | TC2 | PHASE 1 | Chalk Point 230 kV |  | Chalk Point Steam, LLC | MD | Prince George's | Active | Generation Interconnection | PEPCO | 670.2 | 670.2 | 670.2 |  | Capacity | Solar,Storage,Hybrid | 9/10/2021 | 6/1/2025 | [5 empty] | 3/24/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-557 | TC2 | APPLICATION REVIEW | Larrabee Collector Station 230 kV | Larrabee 230 kV IV | Atlantic Shores Offshore Wind Project 2, LLC | NJ | Monmouth | Withdrawn | Generation Interconnection | JCPL | 1300.0 | 1300.0 | 228.8 |  | Capacity | Offshore Wind | 9/10/2021 | 10/31/2029 | [5 empty] | 2/14/2025 | 2/14/2025 | Customer Initiated Withdrawal | [7 empty] | Not Started |  | Not Started
AH1-558 | TC2 | PHASE 1 | Four Rivers 230kV | Doswell Limited Partnership | Doswell Limited Partnership | VA | Hanover | Active | Generation Interconnection | Dominion | 996.0 | 250.0 | 250.0 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-560 | TC2 | PHASE 1 | University Park 138 kV |  | University Park Energy, LLC | IL | Will | Active | Generation Interconnection | ComEd | 473.0 | 150.0 | 150.0 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 4/9/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-561 | TC2 | PHASE 1 | Ironwood 230kV | Ironwood Battery Storage | Helix Ironwood, LLC | PA | Lebanon | Active | Generation Interconnection | ME | 1075.0 | 250.0 | 250.0 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 3/31/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-562 | TC2 | PHASE 1 | Springdale 138kV | Springdale Battery Storage II | Springdale Energy, LLC | PA | Allegheny | Active | Generation Interconnection | APS | 356.0 | 250.0 | 250.0 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-563 | TC2 | PHASE 1 | Aurora E.C. 138kV | Aurora Battery Storage II | Aurora Generation, LLC | IL |  | Active | Generation Interconnection | ComEd | 1206.0 | 150.0 | 150.0 |  | Capacity | Storage | 9/11/2021 | 6/1/2025 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-564 | TC2 | PHASE 1 | Rockford II 138 kV |  | Rockford Generation, LLC | IL | Winnebago | Active | Generation Interconnection | ComEd | 330.0 | 150.0 | 150.0 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 4/21/2025 |  | Customer Milestone Not Met |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-565 | TC2 | PHASE 1 | Lemoyne 345kV | Troy Battery Storage | Troy Energy, LLC | OH | Wood | Active | Generation Interconnection | ATSI | 950.0 | 250.0 | 250.0 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 4/30/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-566 | TC2 | PHASE 1 | South Bend 500kV | Armstrong Battery Storage | Armstrong Power, LLC | PA | Armstrong | Active | Generation Interconnection | APS | 1038.1 | 250.0 | 250.0 |  | Capacity | Storage | 9/10/2021 | 6/1/2025 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-567 | TC2 | PHASE 1 | University Park 138 kV |  | University Park Energy, LLC | IL | Will | Active | Generation Interconnection | ComEd | 478.0 | 5.0 | 5.0 |  | Capacity | Natural Gas | 9/10/2021 | 6/1/2025 | [5 empty] | 4/10/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-569 | TC2 | PHASE 1 | Tangy - National 138 kV |  | Glacier Ridge Solar, LLC | OH | Union | Active | Generation Interconnection | ATSI | 42.0 | 42.0 | 31.3 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 4/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-570 | TC2 | PHASE 1 | Millersburg 69 kV |  | South Fork Solar, LLC | KY |  | Active | Generation Interconnection | EKPC | 25.0 | 25.0 | 15.6 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 4/4/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-571 | TC2 | PHASE 1 | Millersburg 69 kV |  | South Fork Solar, LLC | KY |  | Active | Generation Interconnection | EKPC | 45.0 | 20.0 | 12.5 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 4/21/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-572 | TC2 | PHASE 1 | South Morral-Uncapher Switch 69 kV |  | Swamp Fox Solar, LLC | OH | Marion | Active | Generation Interconnection | AEP | 30.0 | 30.0 | 19.3 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-573 | TC2 | PHASE 1 | South Morral-Uncapher Switch 69 kV |  | Swamp Fox Solar, LLC | OH | Marion | Active | Generation Interconnection | AEP | 49.99 | 19.99 | 12.9 |  | Capacity | Solar | 9/10/2021 | 12/1/2024 | [5 empty] | 5/1/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-577 | TC2 | PHASE 1 | Clutch 69 kV |  | Dragonfly Fields Solar Project, LLC | OH | Wayne | Active | Generation Interconnection | AEP | 70.0 | 70.0 | 42.0 |  | Capacity | Solar | 9/10/2021 | 10/15/2028 | [5 empty] | 4/29/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-578 | TC2 | PHASE 1 | Clutch 69 kV |  | Dragonfly Fields Solar Project, LLC | OH | Wayne | Active | Generation Interconnection | AEP | 98.0 | 28.0 | 28.0 |  | Capacity | Storage | 9/10/2021 | 10/15/2028 | [5 empty] | 4/29/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-580 | TC2 | PHASE 1 | Nottingham 138 kV |  | Energy Pastures Solar Project, LLC | OH | Harrison | Active | Generation Interconnection | AEP | 400.0 | 200.0 | 134.0 |  | Capacity | Solar | 9/10/2021 | 5/1/2025 | [5 empty] | 5/2/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-584 | TC2 | PHASE 1 | Nelson-Indian River 138kV |  | RWE Solar Development, LLC | DE | Sussex | Active | Generation Interconnection | DPL | 50.0 | 50.0 | 30.0 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-585 | TC2 | PHASE 1 | Nelson-Indian River 138kV |  | RWE Solar Development, LLC | DE | Sussex | Active | Generation Interconnection | DPL | 100.0 | 50.0 | 30.0 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-586 | TC2 | PHASE 1 | Nelson-Indian River 138kV |  | RWE Solar Development, LLC | DE | Sussex | Active | Generation Interconnection | DPL | 145.0 | 45.0 | 45.0 |  | Capacity | Storage | 9/10/2021 | 12/16/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-587 | TC2 | PHASE 1 | Farmers Valley – Ridgeway 115 kV | Wild Hollow Solar | RWE Solar Development, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-588 | TC2 | PHASE 1 | Lewis Run - Pierce Brook 230 kV | McKean County Solar II | RWE Solar Development, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 240.0 | 240.0 | 144.0 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-589 | TC2 | PHASE 1 | Lewis Run - Pierce Brook 230 kV | Wild Sky Storage | RWE Solar Development, LLC | PA | McKean | Active | Generation Interconnection | PENELEC | 410.0 | 170.0 | 170.0 |  | Capacity | Storage | 9/10/2021 | 12/16/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-590 | TC2 | PHASE 1 | Cherry Ridge 66 kV | Messenger Brothers Solar I | RWE Solar Development, LLC | WV | Grant | Active | Generation Interconnection | APS | 50.0 | 50.0 | 30.0 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 4/3/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-591 | TC2 | PHASE 1 | Cherry Ridge 66kV | Messenger Brothers Solar II | RWE Solar Development, LLC | WV | Grant | Active | Generation Interconnection | APS | 100.0 | 50.0 | 30.0 |  | Capacity | Solar | 9/10/2021 | 12/16/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-592 | TC2 | PHASE 1 | Cherry Ridge 66kV | Messenger Brothers Storage | RWE Solar Development, LLC | WV | Grant | Active | Generation Interconnection | APS | 145.0 | 45.0 | 45.0 |  | Capacity | Storage | 9/10/2021 | 12/16/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-617 | TC2 | PHASE 1 | Harbert Metering 138 kV |  | STMO bn, LLC | KY |  | Active | Generation Interconnection | AEP | 200.0 | 200.0 | 120.0 |  | Capacity | Solar | 9/10/2021 | 9/30/2024 | [5 empty] | 4/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-626 | TC2 | APPLICATION REVIEW | Ladysmith 230 kV |  | Idemitsu Renewables America Development LLC | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 62.5 | 62.5 | 62.5 |  | Capacity | Storage | 9/10/2021 | 3/21/2025 | [5 empty] | 1/14/2025 | 1/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-627 | TC2 | APPLICATION REVIEW | Ladysmith 230 kV II |  | Idemitsu Renewables America Development LLC | VA | Caroline | Withdrawn | Generation Interconnection | Dominion | 125.0 | 62.5 | 62.5 |  | Capacity | Storage | 9/10/2021 | 3/21/2025 | [5 empty] | 1/14/2025 | 1/14/2025 | Customer Milestone Not Met | [7 empty] | Not Started |  | Not Started
AH1-634 | TC2 | PHASE 1 | Indian River 230kV I |  | US Wind, Inc | DE | Sussex | Active | Generation Interconnection | DPL | 323.1 | 68.0 | 17.7 |  | Capacity | Offshore Wind | 9/13/2021 | 12/31/2024 | [5 empty] | 3/19/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-637 | TC2 | PHASE 1 | Oak Grove 34.5 kV |  | Solar VA 2019 LLC | VA | Westmoreland | Active | Generation Interconnection | Dominion | 16.0 | 16.0 | 9.6 |  | Capacity | Solar | 9/13/2021 | 12/15/2022 | [5 empty] | 3/25/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-641 | TC2 | PHASE 1 | Churchtown - Upper Pittsgrove 138kV |  | Goldenrod Energy Center, LLC | NJ | Salem | Active | Generation Interconnection | AEC | 65.0 | 15.0 | 15.0 |  | Capacity | Solar | 9/14/2021 | 12/31/2023 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-644 | TC2 | PHASE 1 | Spicewood Metering 138 kV |  | Kentucky Power Company | KY |  | Active | Generation Interconnection | AEP | 100.0 | 100.0 | 65.0 |  | Capacity | Solar | 9/15/2021 | 1/1/2026 | [5 empty] | 4/22/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-661 | TC2 | PHASE 1 | Cannelville 12.47 kV |  | Tallgrass Muskingum Community Power, LLC | OH | Muskingum | Active | Generation Interconnection | AEP | 10.07 | 10.07 | 9.06 |  | Capacity | Biomass | 9/29/2021 | 7/1/2023 | [5 empty] | 4/30/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-664 | TC2 | PHASE 1 | Goddard-Plumville 138 kV |  | Hummingbird Energy LLC | KY | Fleming | Active | Generation Interconnection | EKPC | 100.0 | 100.0 | 66.8 |  | Capacity | Solar | 9/24/2018 | 6/1/2022 | [5 empty] | 4/18/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-665 | TC2 | APPLICATION REVIEW | Goddard-Plumsville 138 kV II |  | Hummingbird Energy LLC | KY | Fleming | Withdrawn | Generation Interconnection | EKPC | 180.0 | 80.0 | 53.5 |  | Capacity | Solar | 1/23/2019 | 6/1/2022 | [5 empty] | 4/15/2025 | 4/15/2025 | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-666 | TC2 | PHASE 1 | Flemingsburg - Spurlock 138 kV |  | Fleming Solar, LLC | KY | Fleming | Active | Generation Interconnection | EKPC | 80.0 | 80.0 | 48.0 |  | Capacity | Solar | 9/30/2019 | 6/1/2023 | [5 empty] | 4/11/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-667 | TC2 | PHASE 1 | Philipsburg-Shawville 34.5 kV |  | CL-Shiloh LLC | PA | Clearfield | Active | Generation Interconnection | PENELEC | 18.0 | 18.0 | 10.8 |  | Capacity | Solar | 2/29/2020 | 6/1/2021 | [5 empty] | 3/19/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-668 | TC2 | APPLICATION REVIEW | Madisonburg Jct-Millheim 46 kV |  | Millheim Solar I, LLC | PA | Centre | Withdrawn | Generation Interconnection | APS | 19.9 | 19.9 | 8.3 |  | Capacity | Solar | 9/29/2020 | 8/1/2022 | [5 empty] | 3/13/2025 | 3/7/2025 | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-669 | TC2 | PHASE 1 | Circleville-Biers Run 138 kV |  | Innergex Renewable USA, LLC | OH | Ross | Active | Generation Interconnection | AEP | 50.0 | 50.0 | 30.0 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 3/26/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-670 | TC2 | PHASE 1 | Blue Mound-Chestnut 345 kV |  | Wapella Bluffs Wind Project, LLC | IL | McLean | Active | Generation Interconnection | ComEd | 250.0 | 250.0 | 49.6 |  | Capacity | Wind | 9/30/2020 | 9/25/2024 | [5 empty] | 4/8/2025 |  |  |  | In Progress |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-672 | TC2 | PHASE 1 | Farmview 138 kV |  | Freeman Solar LLC | DE | Sussex | Active | Generation Interconnection | DPL | 75.0 | 75.0 | 48.9 |  | Capacity | Solar | 9/30/2020 | 12/31/2023 | [5 empty] | 3/19/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started
AH1-673 | TC2 | PHASE 1 | State Line - River Energy Center 138 kV |  | Big Shoulders Storage LLC | IL | Cook | Active | Generation Interconnection | ComEd | 85.0 | 85.0 | 85.0 |  | Capacity | Storage | 9/30/2020 | 6/1/2023 | [5 empty] | 4/4/2025 |  | Customer Milestone Not Met |  | Revised |  | Not Started |  | Not Started |  | Not Started |  | Not Started

## Definitions-Mapping
Column Names from Data Tab
Project ID | Project/OASIS ID
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
System Impact Study | The Phase I, Phase II and Phase III System Impact Studies are a regional analysis of the effect of adding to the Transmission System the new facilities and services proposed by valid New Service Requests and an evaluation of their impact on deliverability to the aggregate of PJM Network Load.
System Impact Study Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection request process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Generation Interconnection Agreement | After the project’s required study work is completed, PJM will tender a Generation Interconnection Agreement (“GIA”) to be executed by the Project Developer, the Transmission Owner, and PJM.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Submitted Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Decision Point 1 | The Decision Point I shall commence on the first Business Day immediately following the end of Phase I. New Service Requests that are studied in Phase I will enter Decision Point I. Before the close of the Decision Point I, Project Developer or Eligible Customer shall choose either to remain in the Cycle subject to the terms set forth below, or to withdraw its New Service Request.
Decision Point 2 | Decision Point II shall commence on the first Business Day immediately following the end of Phase II. New Service Requests that are studied in Phase II will enter Decision Point II. Before the close of Decision Point II, Project Developer or Eligible Customer shall choose either to remain in the Cycle subject to the terms set forth below, or to withdraw its New Service Request.
Decision Point 3 | Decision Point III shall commence on the first Business Day immediately following the end of Phase II, and shall run concurrently with the Final Agreement Negotiation Phase. New Service Requests that are studied in Phase II will enter Decision Point III. Before the close of Decision Point III, Project Developer or Eligible Customer shall choose either to remain in the Cycle subject to the terms set forth below, or to withdraw its New Service Request.
Final Agreement Negotiation Phase | The phase described in Tariff, Part VII, Subpart D, section 314 or Tariff, Part VIII, Subpart D, section 411 to tender, negotiate, and execute any service agreement in Tariff, Part IX.
Cycle | period of time between the start of an Application phase and conclusion of the corresponding Final Agreement Negotiation Phase. The Cycle consists of the Application Phase, Phase I, Decision Point I, Phase II, Decision Point II, Phase III, Decision Point III, and the Final Agreement Negotiation Phase.