## Data
Project ID | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim/Interconnection Service/Generation Interconnection Agreement | Interim/Interconnection Service/Generation Interconnection Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Submitted Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Commercial Operation Milestone | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Project | Sliding Project
A01 | South Lebanon 230 KV | Ironwood | PA | Lebanon | In Service | ME | 720 | 720 | 673 | 673 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a01_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a01_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 4/1/2002 | 4/1/2002 | 4/1/2002 | N | No
A02 | Oak Hall 138 kV (Oil CT) | Chesapeake | VA | Unknown | In Service | DPL | 315 | 315 | 315 | 311.8 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 8/22/2001 |  | 8/22/2001 | N | No
A03 | Linden 230 kV or 138 kV | Linden 5 & 6 | NJ | Union | In Service | PSEG | 120 | 120 | 120 | 114 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 6/1/2000 |  | 6/1/2000 | N | No
A04 | Linden 230 kV or 138 kV | Linden 1, 2 & 3 | NJ | Union | In Service | PPL | 1186 | 750 | 750 | 750 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a04_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a04_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/10/2004 | 4/1/1997 | N/A | N/A | 3/11/2005 |  |  | 5/1/2006 |  | 5/1/2006 | N | No
A05 | Bergen | Bergen | NJ | Bergen | In Service | PSEG | 500 | 500 | 500 | 500 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a05_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a05_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
A08 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 1140 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a08_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/1/1997 | N/A | N/A |  |  |  | 7/1/2002 |  | 7/1/2002 | N | No
A09 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 1140 | 35 | 35 | 35 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/1/1997 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
A10 | Glory 115 kV | Colver Power | PA | Cambria | In Service | PENELEC | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a10_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 6/2/1997 | N/A | N/A |  |  |  | 1/8/2000 |  | 1/8/2000 | N | No
A11 | Harwood 230 kV | Hazelton | PA | Luzerne | In Service | PPL | 356 | 201 | 201 | 31.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/1997 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
A12 | Martins Creek 230 kV | Lower Mt Bethel | PA | Northampton | In Service | PPL | 600 | 600 | 600 | 582 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/13/2003 | 8/20/1997 | N/A | N/A | 12/15/2003 |  |  | 5/14/2004 |  | 5/14/2004 | N | No
A15 | Sayreville 230 kV | Red Oak CC1, CT1 - CT4 | NJ | Middlesex | In Service | JCPL | 765 | 765 | 765 | 765 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a15_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a15_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/20/1998 | N/A | N/A |  |  |  | 2/1/2002 |  | 2/1/2002 | N | No
A18 | North Temple 230 kV |  | PA | Berks | In Service | ME | 557 | 557 | 557 | 557 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a18_imp2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/a18_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/11/1998 | N/A | N/A |  |  |  | 12/1/2002 | 12/1/2002 | 12/1/2002 | N | No
A19 | Eddystone 230 kV | Liberty (Eddy) | PA | Delaware | In Service | PECO | 521 | 521 | 521 | 521 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a19_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a19_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/15/1998 | N/A | N/A |  |  |  | 1/1/2002 |  | 1/1/2002 | N | No
A21 | Chichester 230 kV | Phillips Island | PA | Philadelphia | In Service | PECO | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a21_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a21_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a21_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/a21_csa.pdf | Document Posted | N/A | N/A | 6/2/2003 | 8/17/1998 | N/A | N/A | 6/4/2004 |  |  | 12/31/2004 |  | 12/31/2004 | N | No
A26 | Linden | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 180 |  | 157.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a26_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a26_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a26_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/1998 | N/A | N/A |  |  |  | 1/25/2002 |  | 1/25/2002 | N | No
A28 | Dover | Kent | DE | Kent | In Service | DPL | 100 | 100 | 98 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a28_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a28_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/4/1998 | N/A | N/A |  |  |  | 6/14/2001 |  | 6/14/2001 | N | No
A29 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | 465 | 465 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a29_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a29_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a29_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/18/1998 | N/A | N/A |  |  |  | 6/13/2003 |  | 6/13/2003 | N | No
A30 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | 465 | 465 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a30_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a30_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/2/2002 | 12/3/1998 | N/A | N/A |  |  |  | 12/1/2005 |  | 12/1/2005 | N | No
A31 | Peckville/Varden 69 kV | Archbald | PA | Lackawanna | In Service | PPL | 46 | 44 | 44 | 43.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a31_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a31_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a31_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/22/1998 | N/A | N/A |  |  |  | 10/27/2001 |  | 10/27/2001 | N | No
A59_W00 | Springdale 138 kV | Springdale 1 & 2 | PA | Allegheny | In Service | APS | 96 | 96 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a59_w00_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a59_w00_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 12/1/2000 |  | 12/1/2000 | N | No
B12_W01 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b12_w01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b12_w01_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 3/1/2002 |  | 3/1/2002 | N | No
B12_W02 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 300 | 300 | 300 | 300 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b12_w01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b12_w02_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 10/1/2002 |  | 10/1/2002 | N | No
B18_W03 | Springdale 138 kV | Springdale CT3, CT4, ST5 | PA | Allegheny | In Service | APS | 525 | 525 | 525 | 509 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b18_w03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b18_w03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 8/1/2003 |  | 8/1/2003 | N | No
A32 | Montour #1 | Montour #1 | PA | Montour | In Service | PPL | 759 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 6/19/2001 |  | 6/19/2001 | N | No
A33 | Montour #2 | Montour #2 | PA | Montour | In Service | PPL | 14 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a33_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a33_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 11/1/2000 |  | 11/1/2000 | N | No
A34 | Brunner 230 kV |  | PA | York | In Service | PPL | 749 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a34_imp2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a34_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 4/27/2002 |  | 4/27/2002 | N | No
A35 | North Bangor 34.5 kV | Grand Central Sanitary LF | PA | Northampton | In Service | ME | 10 | 10 | 10 | 8.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a35_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a35_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a35_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/13/1999 | N/A | N/A |  |  |  | 4/18/2001 |  | 4/18/2001 | N | No
A36 | Hunterstown 500 kV | Hunterstown | PA | Adams | In Service | ME | 830 | 830 | 830 | 830 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a36_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/1999 | N/A | N/A | 4/23/2003 |  |  | 7/31/2003 | 7/31/2003 | 7/31/2003 | N | No
A55 | Lakewood 230kV | Lakewood NUG | NJ | Ocean | In Service | JCPL | 500 | 500 | 500 | 301 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a55_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a55_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 1/7/2003 | 2/22/1999 | N/A | N/A |  |  |  | 12/31/2005 |  | 12/31/2005 | N | No
A59 | Emilie | Ford Mill | PA | Bucks | In Service | PECO | 1145 | 540 | 540 | 540 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/a59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/a59_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/a59_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/a59_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/1/2003 | 4/1/1999 | N/A | N/A | 1/21/2004 |  |  | 5/27/2004 |  | 5/27/2004 | N | No
B02 | Morgantown | Morgantown Units 1 & 2 | MD | Charles | In Service | PEPCO | 80 | 80 | 80 | 80 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
B03 | Hosensack 500kV | Bethlehem | PA | Northampton | In Service | PPL | 750 | 750 | 750 | 788 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b03_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b03_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 1/28/2003 |  | 1/28/2003 | N | No
B05 | Wayne-Homer City 345kV |  | PA | Indiana | In Service | PENELEC | 265 | 265 | 250 | 265 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b05_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 1/1/2002 |  | 1/1/2002 | N | No
B09A | Burlington 138kV | Burlington | NJ | Burlington | In Service | PSEG | 168 | 168 | 168 | 168 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b09a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b09a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b09a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b09a_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/10/1999 | N/A | N/A |  |  |  | 7/22/2000 |  | 7/22/2000 | N | No
B19 | Melrose 34.5kV | Middlesex Sewer | NJ | Middlesex | In Service | JCPL | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/1999 | N/A | N/A |  |  |  | 4/6/2001 |  | 4/6/2001 | N | No
B23 | Siegfried/Allentown 138kV | Northampton | PA | Northampton | In Service | PPL | 115 | 5 | 5 | 2 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/21/1999 | N/A | N/A |  |  |  | 6/10/2001 |  | 6/10/2001 | N | No
B23_W04 | Gans 138 kV | Gans 8 & 9 | PA | Fayette | In Service | APS | 88 | 88 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b23_w04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b23_w04_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/1999 | N/A | N/A |  |  |  | 12/1/2001 |  | 12/1/2001 | N | No
B26 | Hunlock Creek 66kV | Hunlock Creek 66kV | PA | Luzerne | In Service | UGI | 50 | 50 | 50 | 44.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b26_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/1999 | N/A | N/A |  |  |  | 5/26/2002 |  | 5/26/2002 | N | No
B28 | Muddy Run 230kV | Muddy Run | PA | York | In Service | PECO | 160 | 160 | 160 | 160 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b28_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b28_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 8/27/2003 |  | 8/27/2003 | N | No
B28_W07 | Backbone Mountain 138 kV | Backbone WF | WV | Tucker | In Service | APS | 90 | 90 | 18 | 66 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b28_w07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b28_w07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b28_w07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
B28_W08 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS | 15 | 15 |  | 15 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b28_w08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b28_w08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b28_w08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
B30 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 605 | 605 | 605 | 528 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b30_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b30_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/26/2003 | 11/22/1999 | N/A | N/A | 4/1/2004 |  |  | 6/29/2004 |  | 6/29/2004 | N | No
B34 | Seward 230kV | Seward 1 (Hay Road 5,6,7,8) | PA | Westmoreland | In Service | PENELEC | 525 | 525 | 304 | 325 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b34_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b34_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/1/2003 | 11/23/1999 | N/A | N/A | 3/10/2004 |  |  | 6/9/2006 |  | 6/9/2006 | N | No
B46 | Conowingo 230kV | Conowingo | MD | Harford | In Service | PECO | 548 | 36 | 36 | 36 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b46_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/1999 | N/A | N/A |  |  |  | 11/21/2003 |  | 11/21/2003 | N | No
B47 | Red Lion 500kV | Hay Road 5, 6, 7 | DE | New Castle | In Service | DPL | 545 |  | 545 | 545 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/b47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/b47_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/b47_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/b47_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/1999 | N/A | N/A |  |  |  | 7/22/2002 |  | 7/22/2002 | N | No
C01 | Linden 138kV | Linden 1, 2 & 3 | NJ | Union | In Service | PSEG | 1186 | 436 | 436 | 436 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c01_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c01_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/c01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/10/2004 | 12/17/1999 | N/A | N/A | 4/22/2005 |  |  | 5/1/2006 |  | 5/1/2006 | N | No
C07 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 1119 | 26 | 26 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c07_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c07_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/c07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2000 | N/A | N/A |  |  |  | 7/19/2001 |  | 7/19/2001 | N | No
C08 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1100 | 69 | 69 | 18 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/c08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/c08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/c08_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/c08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2000 | N/A | N/A |  |  |  | 8/1/2001 |  | 8/1/2001 | N | No
D01 | Engleside 69kV | Sight and Sound Theater | PA | Lancaster | In Service | PPL | 1.6 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/6/2000 | N/A | N/A |  |  |  | 5/31/2000 |  | 5/31/2000 | N | No
D02 | Edgemoor | Hay Road 1-4 | DE | New Castle | In Service | DPL | 521 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/7/2000 | N/A | N/A |  |  |  | 4/12/2000 |  | 4/12/2000 | N | No
D03 | Harwood 69kV | Haxelton Units 2-4 | PA | Luzerne | In Service | PPL | 99 | 99 | 99 | 60.8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d03_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d03_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2000 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
D04 | Peckville 69kV | Archbald | PA | Wayne | In Service | PPL | 20 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/26/2000 | N/A | N/A |  |  |  | 6/9/2000 |  | 6/9/2000 | N | No
D05 | East Carbondale 69kV | Waymart WF | PA | Wayne | In Service | PPL | 70 | 70 |  | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d05_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d05_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d05_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/d05_csa.pdf | Document Posted | N/A | N/A |  | 6/15/2000 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 | 12/1/2003 | N | No
D06 | Eclipse 115kV | Scrubgrass NUG | PA | Unknown | In Service | PENELEC | 85 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/19/2000 | N/A | N/A |  |  |  | 7/15/2000 |  | 7/15/2000 | N | No
D08 | Kearny 230kV | Kearny #12 | NJ | Hudson | In Service | PSEG | 168 | 168 | 168 | 168 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d08_fac2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/3/2000 | N/A | N/A |  |  |  | 8/4/2001 |  | 8/4/2001 | N | No
D09 | 9th St (sub 117) 13kV | Central Heating & Refrigeriation Facility 1 & 2 | DC | N/A | In Service | PEPCO | 11 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d09_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/15/2003 | 7/24/2000 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
D10 | NIH 13kV | NIH Unit 1 | MD | Montgomery | In Service | PEPCO | 25 | 25 |  | 25 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d10_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d10_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/30/2003 | 7/26/2000 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
D11 | Clayton 138kV | DEMEC/Smyrna 1 &2 | DE | Kent | In Service | DPL | 100 | 100 | 100 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/26/2000 | N/A | N/A |  |  |  | 5/1/2002 |  | 5/1/2002 | N | No
D18 | Hosensack 230kV | Conectiv Bethlem CT 6, ST2 | PA | Northampton | In Service | PPL | 350 | 350 | 350 | 304 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d18_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/d18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/d18_csa.pdf | Document Posted | N/A | N/A | 5/31/2003 | 7/28/2000 | N/A | N/A |  |  |  | 5/1/2004 |  | 5/1/2004 | N | No
D29 | Derwood 13kV |  | MD | Montgomery | In Service | PEPCO | 3 | 3 | 3 | 2.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/d29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/d29_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/d29_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2000 | N/A | N/A |  |  |  | 6/29/2001 |  | 6/29/2001 | N | No
E02 | N. Lebanon 69kV |  | PA | Lebanon | In Service | ME | 1.2 | 1.2 | 1.2 | 1.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e02_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2000 | N/A | N/A |  |  |  | 11/17/2000 |  | 11/17/2000 | N | No
E04_W20 | Guilford 138 kV |  | PA | Franklin | In Service | APS | 88 | 88 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e04_w20_fea.pdf | Document Posted |  | Not Required |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 9/6/2000 | N/A | N/A |  |  |  | 12/1/2002 |  | 12/1/2002 | N | No
E05 | Bethlehem Steel 33kV | Sparrow Point | MD | Baltimore County | In Service | BGE | 152.5 | 2.5 | 2.5 | 2.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/14/2000 | N/A | N/A |  |  |  | 1/1/2001 |  | 1/1/2001 | N | No
E07 | Montour 230kV | Montour #2 | PA | Montour | In Service | PPL | 766 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/6/2000 | N/A | N/A |  |  |  | 1/1/1999 |  | 5/6/2002 | N | No
E13 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC | 10 | 10 |  | 10 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/e13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/3/2000 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
E17_W27 | Ronco | Ronco CT1, CT2, STG | PA | Fayette | In Service | APS | 661 | 620 | 620 | 620 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e17_w27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e17_w27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e17_w27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2000 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
E20 | Croydon 230kV | Croydon #11,12,21,22,31,32,41,42 | PA | Bucks | In Service | PECO | 386.5 | 6.5 | 6.5 | 6.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/28/2000 | N/A | N/A |  |  |  | 12/20/2002 |  | 12/20/2002 | N | No
E28 | Motiva | Delaware City/Motiva Unit G6 | DE | New Castle | In Service | DPL | 75 | 60 | 60 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/e28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/e28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/e28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/30/2000 | N/A | N/A |  |  |  | 10/1/2003 |  | 10/1/2003 | N | No
F03 | Martins Creek 230kV | Martins Creek #3 | PA | Northampton | In Service | PPL | 850 | 30 | 30 | 30 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/f03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/13/2000 | N/A | N/A |  |  |  | 4/1/2001 |  | 4/1/2001 | N | No
F07 | Dickerson 230kV | Dickerson | MD | Montgomery | In Service | PEPCO | 20 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/f07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2001 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
F08 | Chalk Point 230kV | Chalk Point | MD | Prince George's | In Service | PEPCO | 20 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/f08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/f08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/f08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2001 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
G06 | Martins Creek #4 | Martins Creek #4 | PA | Northampton | In Service | PPL | 850 | 30 | 30 | 30 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/23/2001 | N/A | N/A |  |  |  | 3/1/2012 | 3/1/2012 | 3/1/2012 | N | No
G07_MTX1 | Sayreville 230kV | Neptune | NJ | Middlesex | In Service | JCPL | 790 | 790 |  |  | Energy | Merchant Transmission |  | DC | F/TWR 685; NF/TWR 105 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g07_mtx1_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/g07_mtx1_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/g07_mtx1_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/g07_mtx1_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/g07_mtx1_csa.pdf | Document Posted | N/A | N/A |  | 3/8/2001 | N/A | N/A | 1/4/2007 |  |  | 6/30/2007 |  | 6/30/2007 | S | No
G08 | Kearny | Kearny #12 | NJ | Hudson | In Service | PSEG | 215 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g08_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g08_fac2.pdf | Interim Study | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/13/2001 | N/A | N/A |  |  |  | 6/30/2001 |  | 6/30/2001 | N | No
G10 | Bergen | Bergen #2 | NJ | Bergen | In Service | PSEG | 550 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2001 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
G17 | Burlington | Burlington #10 | NJ | Burlington | In Service | PSEG | 261 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 7/19/2002 |  | 7/19/2002 | N | No
G18 | Linden | Linden 5 & 6 | NJ | Union | In Service | PSEG | 172 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 5/4/2004 |  | 5/4/2004 | N | No
G19 | Linden | Linden 7 & 8 | NJ | Union | In Service | PSEG | 168 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 5/4/2004 |  | 5/4/2004 | N | No
G20 | Essex | Essex 9 | NJ | Essex | In Service | PSEG | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G21 | Meyersdale North 115 kV | Meyersdale WF | PA | Somerset | In Service | PENELEC | 30 | 30 |  | 30 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g21_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g21_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g21_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g21_csa.pdf | Document Posted | N/A | N/A |  | 4/6/2001 | N/A | N/A |  |  |  | 12/3/2003 | 12/3/2003 | 12/3/2003 | N | No
G22 | North Wales 34.5 kV | Merck | PA | Montgomery | In Service | PECO | 38 | 38 | 38 | 38 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g22_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/6/2001 | N/A | N/A |  |  |  | 9/30/2002 |  | 9/30/2002 | N | No
G24 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 1.9 | 1.9 | 1.9 | 1.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g24_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g24_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/1/2001 | N/A | N/A |  |  |  | 6/8/2002 |  | 6/8/2002 | N | No
G25 | Marion 26.4kV | Baler LF | NJ | Bergen | In Service | PSEG | 3.8 | 3.8 | 3.8 | 3.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/1/2001 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
G30 | Perryman 115kV | Perryman 51 | MD | Harford | In Service | BGE | 152 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2001 | N/A | N/A |  |  |  | 6/1/2001 |  | 6/1/2001 | N | No
G30_W51 | Fort Martin 500 kV | Longview ST1 | WV | Monongalia | In Service | APS | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_w51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_w51_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g30_w51_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_w51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g30_w51_csa.pdf | Document Posted | N/A | N/A | 4/5/2009 | 5/21/2001 | N/A | N/A | 5/6/2011 |  |  | 4/22/2011 | 4/22/2011 | 6/1/2008 | N | No
G30_W52 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 354 | 54 | 54 | 15.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_w52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_w52_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_w52_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/g30_w52_csa.pdf | Document Posted | N/A | N/A |  | 5/23/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G30_W53 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 704 | 104 | 104 | 25.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g30_w53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g30_w53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g30_w53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/23/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G22_MTX5 | Linden 230kV | Linden VFT | NJ | Union | In Service | PSEG | 330 | 330 | 330 |  | Capacity | Merchant Transmission |  | AC | TWR 330 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/g22_mtx5_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/g22_mtx5_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/g22_mtx5_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/g22_mtx5_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/g22_mtx5_csa.pdf | Document Posted | N/A | N/A | 6/1/2009 | 6/2/2001 | N/A | N/A | 9/16/2009 |  |  | 11/1/2009 | 11/1/2009 | 11/1/2009 | S | No
G36 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 107 | 107 | 107 | 5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g36_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g36_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/16/2001 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
G46 | Peach Bottom 500kV | Peach Bottom 2 & 3 | PA | York | In Service | PECO | 2256 | 70 | 70 | 38 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g46_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2001 | N/A | N/A |  |  |  | 12/31/2001 | 12/31/2001 | 12/31/2001 | N | No
G51_W63 | Upton 34.5 kV | Upton | PA | Franklin | In Service | APS | 9.9 | 9.9 | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/g51_w63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/g51_w63_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/g51_w63_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/g51_w63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2001 | N/A | N/A |  |  |  | 4/1/2003 |  | 4/1/2003 | N | No
H02 | Susquehanna 230kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 9 | 9 | 9 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/20/2001 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
H03 | Susquehanna 500kV | Susquehanna #2 | PA | Columbia | In Service | PPL | 1153 | 9 | 9 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/21/2001 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 | 12/1/2003 | N | No
H06 | Chichester 230kV | Phillips Island | PA | Philadelphia | In Service | PECO | 750 | 25 | 25 | 25 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/h06_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2001 | N/A | N/A |  |  |  | 12/31/2004 |  | 12/31/2004 | N | No
H12 | Edgemoor 230kV | Hay Road 4 | DE | New Castle | In Service | DPL | 189 | 10 | 10 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/20/2001 | N/A | N/A |  |  |  | 12/1/2005 |  | 12/1/2005 | N | No
H13 | Dolfield | Owings Mills | MD | Baltimore County | In Service | BGE | 9 | 9 | 0 | 9 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/27/2001 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
H17 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 2336 | 115 | 115 | 83 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h17_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h17_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 6/18/2008 | 6/18/2008 | 6/1/2008 | N | No
H18 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1221 | 78 | 78 | 12 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h18_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 8/26/2008 | 8/26/2008 | 12/1/2007 | N | No
H19 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1221 | 43 | 43 | 43 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h19_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h19_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 8/26/2008 | 8/26/2008 | 12/1/2007 | N | No
H20 | Oak Grove 13.8kV |  | MD | Prince George's | In Service | PEPCO | 3.5 | 3.5 | 3.5 | 3.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/31/2003 | 1/21/2002 | N/A | N/A |  |  |  | 12/31/2003 | 12/31/2003 | 5/31/2003 | N | No
H21_W68 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS | 300 | 300 | 0 | 264 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h21_w68_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h21_w68_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h21_w68_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h21_w68_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/h21_w68_csa.pdf | Document Posted | N/A | N/A |  | 1/29/2002 | N/A | N/A |  |  |  | 9/25/2007 | 9/25/2007 | 9/30/2007 | N | No
H23_W70 | Kelso Gap 138 kV | Kelso Gap WF | MD | Garrett | In Service | APS | 100 | 100 |  | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h23_w70_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h23_w70_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/h23_w70_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h23_w70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/h23_w70_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2002 | N/A | N/A | 10/26/2010 |  |  | 10/26/2010 | 10/26/2010 | 11/6/2006 | N | No
H27 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 2.85 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/h27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/h27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/h27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2002 | N/A | N/A |  |  |  | 12/1/2002 |  | 12/1/2002 | N | No
I01 | Ontario 23kV | Jersey Atlantic WF | NJ | Atlantic | In Service | AEC | 7.5 | 7.5 |  | 7.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i01_csa.pdf | Document Posted | N/A | N/A | 7/1/2005 | 2/13/2002 | N/A | N/A | 12/20/2005 |  |  | 12/30/2005 |  | 12/30/2005 | N | No
I02_W73 | Harrison 500 kV | Harrison 1, 2, 3 | WV | Harrison | In Service | APS | 35 | 35 | 35 | 21 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i02_w73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i02_w73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i02_w73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/7/2002 | N/A | N/A |  |  |  | 9/22/2004 |  | 9/22/2004 | N | No
I06 | Greenwich Pumphousse 2.4kV | Repauno Unit 1 | NJ | Unknown | In Service | AEC | 1.7 | 1.7 |  | 1.7 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/8/2002 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
I10 | Bethesda (Sub 6) |  | MD | Montgomery | In Service | PEPCO | 2 | 2 |  | 2 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i10_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i10_csa.pdf | Document Posted | N/A | N/A | 7/1/2004 | 6/11/2002 | N/A | N/A | 9/20/2004 |  |  | 10/1/2004 |  | 10/1/2004 | N | No
I12 | Grand Point 69kV | Orchard Park Generating Station | PA | Franklin | In Service | APS | 30.5 | 23.3 | 23.3 | 23.3 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i12_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2002 | N/A | N/A |  |  |  | 1/1/2004 |  | 1/1/2004 | N | No
I13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 29.4 | 29.4 | 0 | 29.4 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/i13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i13_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2002 | N/A | N/A |  |  |  | 3/6/2008 | 3/6/2008 | 3/6/2008 | N | No
I14 | Upton 34.5kV | Upton | PA | Franklin | In Service | APS | 14 | 4.1 | 4.1 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/i14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/i14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/i14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/i14_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2002 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
J02_MTX13 | Keeney XFMR 230/138kV | Keeney Autotransformer AT20 | DE | New Castle | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/j02_mtx13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/j02_mtx13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/j02_mtx13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/16/2002 | N/A | N/A |  | 12/8/2003 |  | 5/31/2003 |  | 5/31/2003 | S | No
J05 | Huron 69kV | Borgata D1 / D2 | NJ | Atlantic | In Service | AEC | 8 | 8 | 8 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/25/2002 | N/A | N/A |  |  |  | 7/30/2003 |  | 7/30/2003 | N | No
J07_MTX12 | Cheswold XFMR 138/69kV |  | DE | Kent | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/j07_mtx12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/j07_mtx12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/j07_mtx12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2002 | N/A | N/A |  |  |  | 12/31/2003 |  | 12/31/2003 | S | No
J08 | Whiteoak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 6 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j08_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/j08_csa.pdf | Document Posted | N/A | N/A | 4/1/2004 | 12/12/2002 | N/A | N/A | 4/30/2004 |  |  | 8/15/2004 |  | 8/15/2004 | N | No
J09 | Harrisburg Authority | Harrisburg Municipal Solid Waste Authority | PA | Dauphin | In Service | PPL | 26 | 26 | 26 | 11 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/j09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/j09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/j09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/j09_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/j09_csa.pdf | Document Posted | N/A | N/A | 6/30/2005 | 1/31/2003 | N/A | N/A | 2/1/2006 |  |  | 4/24/2006 |  | 4/24/2006 | N | No
K02 | East Towanda-Moshannon 230kV | Laurel Hill | PA | Lycoming | In Service | PENELEC | 70 | 70 | 0 | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k02_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k02_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k02_csa.pdf | Document Posted | N/A | N/A | 9/17/2012 | 2/25/2003 | N/A | N/A | 9/19/2012 |  |  | 10/29/2012 | 10/29/2012 | 9/25/2012 | N | No
K04 | Camden 26kV | Pennsauken Sanitary Landfill / Aluminum Shapes | NJ | Camden | In Service | PSEG | 5.1 | 5.1 | 0 | 5.1 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k04_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k04_csa.pdf | Document Posted | N/A | N/A | 9/15/2004 | 4/15/2003 | N/A | N/A | 10/15/2004 |  |  | 6/30/2005 |  | 6/30/2005 | N | No
K06 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 10 | 5 | 5 | 4.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/6/2003 | N/A | N/A | 11/1/2004 |  |  | 11/1/2004 |  | 11/1/2004 | N | No
K07 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 10 | 5 | 5 | 4.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2003 | N/A | N/A | 11/1/2004 |  |  | 11/1/2004 |  | 11/1/2004 | N | No
K11 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS | 300 |  | 60 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k11_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2003 | N/A | N/A |  |  |  | 10/1/2007 | 10/1/2007 | 9/30/2007 | N | No
K13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 29.4 | 0 | 5.88 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/k13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k13_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2003 | N/A | N/A |  |  |  | 3/6/2008 | 3/6/2008 | 9/1/2007 | N | No
K19 | Backbone Mountain 138kV | Backbone WF | WV | Tucker | In Service | APS | 90 | 0 | 18 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 6/1/2001 |  | 11/12/2006 | N | No
K20 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS | 15 |  | 3 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 4/1/2002 |  | 7/28/2005 | N | No
K21 | East Carbondale 69kV | Waymart | PA | Wayne | In Service | PPL | 69 |  | 13 | 64.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k21_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k21_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K22 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC | 9 |  | 1.8 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k22_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
K23 | Meyersdale North 115 kV | Meyersdale WF | PA | Somerset | In Service | PENELEC | 30 | 0 | 5.1 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K28 | Kelso Gap 138kV | Kelso Gap WF | MD | Garrett | In Service | APS | 100 |  | 20 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/k28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/k28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/k28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/k28_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2003 | N/A | N/A | 10/26/2010 |  |  | 10/26/2010 | 10/26/2010 | 11/6/2006 | N | No
L02 | Pleasantville 12 kV | Pleasantville / AC LF Unit 1 | NJ | Atlantic | In Service | AEC | 1.5 | 1.5 | 1.4 | 0.07 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l02_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l02_csa.pdf | Document Posted | N/A | N/A |  | 9/10/2003 | N/A | N/A |  |  |  | 1/30/2005 |  | 1/30/2005 | N | No
L05_CE22 | Camp Grove | Camp Grove Wind Farm | IL | Stark | In Service | ComEd | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l05_ce22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l05_ce22_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l05_ce22_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l05_ce22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l05_ce22_csa.pdf | Document Posted | N/A | N/A |  | 10/15/2003 | N/A | N/A |  |  |  | 12/14/2007 | 12/14/2007 | 9/1/2006 | N | No
L08 | Holtwood 69kV | Holtwood | PA | Lancaster | In Service | PPL | 109 | 2 | 2 | 2 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l08_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/7/2003 | N/A | N/A |  |  |  | 10/1/2003 |  | 8/16/2004 | N | No
L09 | Montour #1 230kV | Montour #1 | PA | Montour | In Service | PPL | 761 | 2 | 2 | 2 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l09_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/7/2003 | N/A | N/A |  |  |  | 10/1/2003 |  | 8/16/2004 | N | No
L13 | Rockwood | Casselman WF1 | PA | Somerset | In Service | PENELEC | 40 | 40 | 8 | 40 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l13_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l13_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l13_csa.pdf | Document Posted | N/A | N/A |  | 12/19/2003 | N/A | N/A |  |  |  | 1/11/2008 | 1/11/2008 | 12/31/2007 | N | No
L13_CE25 | Geneva | City of Geneva Units 1-5 | IL | Kane | In Service | ComEd | 29 | 29 | 29 | 29 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l13_ce25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l13_ce25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l13_ce25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/26/2003 | N/A | N/A |  |  |  | 6/1/2005 |  | 6/1/2005 | N | No
L18 | Bear Creek | Bear Creek WF | PA | Luzerne | In Service | PPL | 26 | 26 | 5.2 | 24 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/l18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/l18_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/l18_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/l18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/l18_csa.pdf | Document Posted | N/A | N/A | 11/15/2005 | 1/28/2004 | N/A | N/A | 12/31/2005 |  |  | 2/26/2006 |  | 2/26/2006 | N | No
M04 | Calvert Cliffs | Clavert Cliffs 1 and 2 | MD | Calvert | In Service | BGE | 1740 | 63 |  | 63 | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/25/2004 | N/A | N/A |  |  |  | 6/30/2005 |  | 6/30/2005 | N | No
M05 | Black Oak - Bedington | Black Oak - Bedington Wave Traps 500kV | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/m05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/m05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/m05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/5/2004 | N/A | N/A |  |  |  | 12/31/2005 |  | 12/31/2005 | S | No
M07 | Peckville (Archbald) | Archbald | PA | Lackawanna | In Service | PPL | 50 | 6.3 | 6.3 | 6.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m07_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/12/2004 | N/A | N/A |  |  |  | 3/15/2004 |  | 3/15/2004 | N | No
M11 | Susquehanna #1 | Susquehanna #1 | PA | Luzerne | In Service | PPL | 2520 | 111 | 111 | 111 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m11_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2004 | N/A | N/A |  |  |  | 7/24/2010 | 7/24/2010 | 7/24/2010 | N | No
M12 | Susquehanna #2 | Susquehanna #2 | PA | Luzerne | In Service | PPL | 2520 | 107 | 107 | 107 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m12_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2004 | N/A | N/A |  |  |  | 8/18/2011 | 8/18/2011 | 8/18/2011 | N | No
M19 | Otter Point | Otter Point LF-1 | MD | Baltimore County | In Service | BGE | 4.5 | 4.5 |  | 4.5 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m19_csa.pdf | Document Posted | N/A | N/A |  | 6/25/2004 | N/A | N/A |  |  |  | 9/1/2006 |  | 9/1/2006 | N | No
M21 | Rochelle | City of Rochelle, IL | IL | Ogle | In Service | ComEd | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m21_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m21_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m21_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/23/2004 | N/A | N/A |  |  |  | 12/31/2006 | 12/31/2006 | 11/11/2005 | N | No
M24 | Grassy Falls | Beech Ridge / Field Mtn WF | WV | Greenbrier | In Service | APS | 186 | 186 | 37.2 | 132.5 | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m24_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m24_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/m24_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m24_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/m24_csa.pdf | Document Posted | N/A | N/A | 12/17/2009 | 7/27/2004 | N/A | N/A | 1/15/2010 |  |  | 12/1/2014 | 12/1/2014 | 11/1/2007 | N | No
M27 | Eddystone 138kV | Eddystone | PA | Delaware | In Service | PECO | 1408 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/m27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/m27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/m27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2004 | N/A | N/A |  |  |  | 6/17/2004 |  | 12/1/2006 | N | No
N03 | Edgemoor 69kV | Hay Road 2 | DE | New Castle | In Service | DPL | 121 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/25/2004 | N/A | N/A |  |  |  | 8/9/2004 |  | 6/1/2006 | N | No
N05 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 242 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/25/2004 | N/A | N/A |  |  |  | 8/9/2004 |  | 6/1/2006 | N | No
N06 | Hamilton 12kV | Pine Hurst Acres | PA | Northumberland | In Service | PPL | 0.047 | 0.047 |  | 0.047 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n06_csa.pdf | Document Posted | N/A | N/A |  | 9/16/2004 | N/A | N/A |  |  |  | 3/1/2005 |  | 3/1/2005 | N | No
N10 | Grangston 138 kV | Big Sandy Peaker Plant | WV | Wayne | In Service | AEP | 300 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/11/2004 | N/A | N/A |  |  |  | 6/1/2005 | 6/1/2005 | 6/1/2005 | N | No
N11 | Wolf Hills 138 kV | Wolf Hills Energy Plant | VA | Washington | In Service | AEP | 275 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/11/2004 | N/A | N/A |  |  |  | 6/1/2005 | 6/1/2005 | 6/1/2005 | N | No
N12 | North Haverhill 69 kV | North Haverhill | OH | Scioto | In Service | AEP | 75 | 75 | 75 | 75 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n12_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n12_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n12_csa.pdf | Document Posted | N/A | N/A |  | 10/13/2004 | N/A | N/A |  |  |  | 6/1/2009 | 6/1/2009 | 6/1/2009 | N | No
N13 | Beaver Valley |  | PA | Beaver | In Service | DL | 1652 | 1630 | 1630 | 1630 | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2004 | N/A | N/A |  |  |  | 1/1/2005 |  | 1/1/2005 | N | No
N14 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 24 | 5.4 | 24 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n14_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n14_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n14_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2004 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
N15 | LaSalle 138 kV | Grand Ridge Energy LLC | IL | Lasalle | In Service | ComEd | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n15_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n15_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n15_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n15_csa.pdf | Document Posted | N/A | N/A |  | 12/2/2004 | N/A | N/A |  |  |  | 11/1/2009 | 11/1/2009 | 11/1/2009 | N | No
N16 | Kent-Harrington 69kV | Central Landfill Units 1-4 | DE | New Castle | In Service | DPL | 4 | 4 |  | 4 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n16_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/9/2004 | N/A | N/A |  |  |  | 12/7/2006 | 12/7/2006 | 12/7/2006 | N | No
N17 | Laurel-Sussex 69kV | Southern Landfill Units 1-4 | DE | New Castle | In Service | DPL | 3 | 3 |  | 3 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n17_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/9/2004 | N/A | N/A |  |  |  | 10/24/2006 |  | 10/24/2006 | N | No
N26 | Daleville | SECCRA LF | PA | Chester | In Service | PECO | 1.74 | 1.74 | 1.7 | 1.7 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n26_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2005 | N/A | N/A |  |  |  | 12/31/2009 | 12/31/2009 | 12/31/2009 | N | No
N27 | Pequest River 34.5 kV | Warren County LF | NJ | Warren | In Service | JCPL | 3.6 | 3.6 | 3.6 | 3.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n27_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n27_csa.pdf | Document Posted | N/A | N/A |  | 1/27/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
N32 | Gans 138kV | South Chestnut WF | PA | Fayette | In Service | APS | 50.4 | 50.4 | 10.1 | 50.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n32_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n32_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n32_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 12/24/2011 | N | No
N34 | Motiva | Delaware City | DE | New Castle | In Service | DPL | 250 | 250 | 142 | 250 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n34_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 12/31/2005 | 12/31/2005 | 12/31/2005 | N | No
N39 | Johnstown-Altoona 230kV | Allegheny Ridge WF1 | PA | Cambria | In Service | PENELEC | 80 | 80 | 16 | 80 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n39_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n39_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n39_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n39_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n39_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 3/15/2007 | 3/15/2007 | 11/1/2006 | N | No
N47 | Beryl 138kV | Pinnacle WF | WV | Mineral | In Service | APS | 85 | 85 | 17 | 55.2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/n47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/n47_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/n47_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/n47_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/n47_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2005 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 11/16/2011 | N | No
O05 | Rochelle | City of Rochelle | IL | Ogle | In Service | ComEd | 22 | 22 | 2 | 22 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/22/2005 | N/A | N/A |  |  |  | 12/31/2006 | 12/31/2006 | 6/30/2005 | N | No
O06_DP01 | Altavista 115kV | Pittsylvania | VA | Pittsylvania | In Service | Dominion | 83.6 | 4 | 4 | 3.4 | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o06_dp01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o06_dp01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o06_dp01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/24/2005 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
O09 | Normandy | Walnut Ridge Wind, LLC | IL | Lee | In Service | ComEd | 212 | 212 | 42.4 | 212 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o09_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o09_csa.pdf | Document Posted | N/A | N/A |  | 3/7/2005 | N/A | N/A |  |  |  | 10/15/2018 | 10/15/2018 | 10/31/2018 | N | No
O10 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 242 | 7 | 7 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/14/2005 | N/A | N/A |  |  |  | 6/1/2005 |  | 6/1/2005 | N | No
O16 | Chichester-Linwood 230kV | FPL Energy Markus Hook | PA | Delaware | In Service | PECO | 230 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/o16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/o16_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2005 | N/A | N/A |  |  |  | 6/19/2005 |  | 6/19/2005 | S | No
O18 | Salix-Claysburg (Krayn) 115kV | Highland WF | PA | Somerset | In Service | PENELEC | 65 | 65 | 13 | 62.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o18_csa.pdf | Document Posted | N/A | N/A |  | 4/21/2005 | N/A | N/A | 1/14/2009 |  |  | 12/18/2008 | 12/18/2008 | 12/18/2008 | N | No
O20 | Lakehurst 34.5kV | Ocean Energy LF | NJ | Ocean | In Service | JCPL | 9.4 | 9.4 | 9.4 | 9.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o20_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/o20_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/4/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
O22 | Powerton-Goodings Grove 345kV | Top Crop WF 1 & 2 | IL | Livingston | In Service | ComEd | 300 | 300 | 60 | 300 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o22_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o22_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o22_csa.pdf | Document Posted | N/A | N/A | 10/17/2009 | 5/11/2005 | N/A | N/A | 10/23/2009 |  |  | 10/25/2010 | 10/25/2010 | 10/25/2010 | N | No
O25 | N. Salisbury 25kV | Newland Park LF | MD | Wicomico | In Service | DPL | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o25_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o25_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o25_csa.pdf | Document Posted | N/A | N/A |  | 5/12/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
O26 | Pine Grove 69kV | Guilford Mills LF | PA | Schuylkill | In Service | PPL | 8 | 8 | 8 | 6 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o26_csa.pdf | Document Posted | N/A | N/A |  | 5/12/2005 | N/A | N/A |  |  |  | 6/30/2008 | 6/30/2008 | 6/30/2008 | N | No
O29 | Normandy 138kV | Green River Wind Farm Phase 2 | IL | Lee | In Service | ComEd | 225 | 225 | 45 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o29_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o29_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o29_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o29_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o29_csa.pdf | Document Posted | N/A | N/A |  | 5/16/2005 | N/A | N/A | 10/1/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/25/2019 | N | No
O31 | Fries 12kV | Fries Hydorelectric Plant | VA | Grayson | In Service | AEP | 5.21 | 5.21 | 5.21 | 5.21 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o31_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o31_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o31_csa.pdf | Document Posted | N/A | N/A |  | 5/18/2005 | N/A | N/A |  |  |  | 12/31/2006 |  | 12/31/2006 | N | No
O32 | Mountaineer 765kV | Mountaineer #1 | WV | Mason | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/31/2005 | N/A | N/A |  |  |  | 5/31/2005 | 5/31/2005 | 5/31/2005 | N | No
O33 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 20 | 20 | 4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o33_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o33_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/o33_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/2/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
O35 | Providence Heights #1 138kV | Providence Heights WF | IL | Bureau | In Service | ComEd | 74 | 74 | 14.8 | 74 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o35_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o35_csa.pdf | Document Posted | N/A | N/A | 6/2/2008 | 6/6/2005 | N/A | N/A | 6/2/2008 |  |  | 6/26/2008 | 6/26/2008 | 6/30/2007 | N | No
O36 | Honey Brook 12kV | Honeybrook | PA | Chester | In Service | PPL | 1.6 | 1.6 | 0 | 1.6 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o36_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/o36_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/6/2005 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
O38 | Johnstown-Altoona 230kV | North Alleghney WF | PA | Cambria | In Service | PENELEC | 50 | 50 | 10 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o38_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o38_csa.pdf | Document Posted | N/A | N/A |  | 6/27/2005 | N/A | N/A |  |  |  | 9/1/2009 | 9/1/2009 | 12/15/2007 | N | No
O42 | Cook 345 kV | Cook #1 | MI | Berrien | In Service | AEP | 1100 | 84 | 84 | 84 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o42_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/6/2005 | N/A | N/A |  |  |  | 1/19/2007 | 1/19/2007 | 12/31/2006 | N | No
O43 | University Park | University Park North Energy Center | IL | Will | In Service | ComEd | 504 | 54 | 54 | 54 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o43_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o43_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/7/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 12/19/2011 | N | No
O46 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 2 | 0.4 | 2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o46_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o46_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o46_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o46_csa.pdf | Document Posted | N/A | N/A |  | 7/22/2005 | N/A | N/A |  |  |  | 12/1/2007 |  | 12/1/2007 | N | No
O48 | Hays Mill - Lookout 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 36 | 36 | 7.2 | 36 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o48_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o48_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o48_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o48_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2005 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
O50 | Powerton-Dresden 345kV | Minonk Wind Farm | IL | Woodford | In Service | ComEd | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o50_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o50_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o50_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o50_csa.pdf | Document Posted | N/A | N/A | 10/16/2012 | 7/26/2005 | N/A | N/A | 10/31/2012 |  |  | 12/31/2012 | 12/31/2012 | 10/31/2012 | N | No
O51 | Pontiac Midpoint-Wilton Center 345kV | Cayuga Ridge South WF | IL | Livingston | In Service | ComEd | 300 | 300 | 60 | 300 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o51_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/o51_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/o51_csa.pdf | Document Posted | N/A | N/A | 9/29/2009 | 7/27/2005 | N/A | N/A | 10/26/2009 |  |  | 5/6/2010 | 5/6/2010 | 12/31/2007 | N | No
O53 | Beaver Valley #1 | Beaver Valley 1 | PA | Beaver | In Service | DL | 902 | 81 | 81 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/27/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 9/15/2006 | N | No
O54 | Beaver Valley #2 | Beaver Valley 2 | PA | Beaver | In Service | DL | 908 | 77 | 77 | 54 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/o54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/o54_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/o54_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/27/2005 | N/A | N/A |  |  |  | 7/1/2008 | 7/1/2008 | 10/23/2006 | N | No
O66 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | JCPL | 670 | 670 | 320 |  | Capacity | Merchant Transmission |  | DC | NF/TWR 320/NFTWR 673 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/o66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/o66_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/o66_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/o66_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/o66_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2005 | N/A | N/A | 4/4/2013 |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
P03 | Frackville-Hauto #3 | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 1.3 | 1.3 | 1.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p03_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p03_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p03_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p03_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2005 | N/A | N/A |  |  |  | 12/31/2007 |  | 12/31/2007 | N | No
P04 | Peach Bottom 500kV | Delta | PA | York | In Service | PECO | 557 | 550 | 550 | 550 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p04_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p04_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p04_csa.pdf | Document Posted | N/A | N/A |  | 9/8/2005 | N/A | N/A | 12/21/2010 |  |  | 3/1/2011 | 3/1/2011 | 3/1/2011 | N | No
P06 | Cumberland 230 kV | Cumberland 2 | NJ | Cumberland | In Service | AEC | 225 | 225 | 225 | 100 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p06_csa.pdf | Document Posted | N/A | N/A | 2/6/2009 | 9/9/2005 | N/A | N/A | 5/4/2009 |  |  | 6/1/2016 | 6/1/2016 | 12/31/2008 | N | No
P09 | Kerr Dam 115kV | John H. Kerr Dam Hydro Units 1(15MW), 2-7(42MW) | VA | Mecklenburg | In Service | Dominion | 267 | 27 | 27 | 27 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p09_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p09_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/14/2005 | N/A | N/A |  |  |  | 1/19/2011 | 1/19/2011 | 1/19/2011 | N | No
P10 | LaSalle 138kV | Grand Ridge WF | IL | Lasalle | In Service | ComEd | 190.5 | 190.5 | 37.2 | 135 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p10_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p10_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p10_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p10_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2005 | N/A | N/A |  |  |  | 12/1/2013 | 12/1/2013 | 6/1/2010 | N | No
P11 | Kewanee 138kV | Bishop Hill WF | IL | Mercer | In Service | ComEd | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p11_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p11_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p11_csa.pdf | Document Posted | N/A | N/A | 2/1/2012 | 9/26/2005 | N/A | N/A | 2/16/2012 |  |  | 10/1/2011 | 10/1/2011 | 2/24/2012 | N | No
P14 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 80 | 80 | 16 | 80 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p14_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p14_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p14_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/12/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
P16 | Bath County | Bath County | VA | Bath | In Service | Dominion | 3030 | 340 | 340 | 340 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p16_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p16_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p16_csa.pdf | Document Posted | N/A | N/A |  | 10/19/2005 | N/A | N/A |  |  |  | 12/1/2009 | 12/1/2009 | 12/1/2009 | N | No
P22 | Johnstown Altoona 230kV | North Allegheny WF | PA | Cambria | In Service | PENELEC | 20 | 20 | 4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p22_csa.pdf | Document Posted | N/A | N/A |  | 10/28/2005 | N/A | N/A |  |  |  | 9/1/2009 | 9/1/2009 | 9/1/2009 | N | No
P26 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 9.5 | 9.5 | 1.9 | 9.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p26_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p26_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p26_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p26_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/7/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
P27 | Winchester 34.5 kV | Bethel LF | VA | Unknown | In Service | Dominion | 13 | 13 | 13 | 13 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p27_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p27_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p27_csa.pdf | Document Posted | N/A | N/A |  | 11/18/2005 | N/A | N/A |  |  |  | 1/25/2008 | 1/25/2008 | 1/25/2008 | N | No
P28 | Mehoopany 115kV | Mehoopany WF | PA | Wyoming | In Service | PENELEC | 150 | 150 | 30 | 148 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p28_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p28_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p28_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2005 | N/A | N/A |  |  |  | 1/21/2013 | 1/21/2013 | 1/9/2013 | N | No
P31 | Bath County |  | VA | Highland | In Service | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/p31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/p31_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/p31_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/p31_csa.pdf | Document Posted | N/A | N/A |  | 12/5/2005 | N/A | N/A |  |  |  | 12/1/2008 | 12/1/2008 | 12/1/2008 | S | No
P32 | White Oak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 19.5 | 19.5 |  | 19.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/7/2005 | N/A | N/A |  |  |  | 12/31/2007 |  | 12/31/2007 | N | No
P33 | Laurel - Sussex 69kV | Southern Landfill Units 1-4 | DE | Sussex | In Service | DPL | 4.25 | 1 |  | 1 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p33_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p33_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/8/2005 | N/A | N/A |  |  |  | 10/24/2006 |  | 10/24/2006 | N | No
P34 | Washington Landfill |  | PA | Washington | In Service | APS | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p34_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/p34_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/20/2005 | N/A | N/A |  |  |  | 3/17/2009 | 3/17/2009 | 12/31/2006 | N | No
P35 | Pleasantville | Pleasantville /AC LF Unit 2 | NJ | Atlantic | In Service | AEC | 4 | 2 | 2 | 1.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p35_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p35_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2005 | N/A | N/A |  |  |  | 7/31/2006 |  | 7/31/2006 | N | No
P36 | Nelson - Lee Co. EC 345kV | Big Sky | IL | Bureau | In Service | ComEd | 240 | 240 | 48 | 240 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p36_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p36_csa.pdf | Document Posted | N/A | N/A |  | 12/22/2005 | N/A | N/A |  |  |  | 8/31/2010 | 8/31/2010 | 8/31/2010 | N | No
P38 | Bremo 230kV | Bremo | VA | Buckingham | In Service | Dominion | 675 | 675 | 625 | 675 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p38_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p38_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p38_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p38_csa.pdf | Document Posted | N/A | N/A | 7/21/2010 | 12/22/2005 | N/A | N/A |  |  |  | 3/30/2011 | 3/30/2011 | 3/30/2011 | N | No
P43 | Weyerhaeuser 115kV | Domtar Paper Company Generating Units 7-10 | NC | Martin | In Service | Dominion | 62.5 | 62.5 | 50 | 62.5 | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p43_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p43_csa.pdf | Document Posted | N/A | N/A |  | 1/13/2006 | N/A | N/A |  |  |  | 10/1/2021 | 10/1/2021 | 1/1/2010 | N | No
P44 | City of Columbus | Columbus Floodwall | OH | Franklin | In Service | AEP | 7.47 | 7.47 | 7 | 7 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p44_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p44_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p44_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/16/2006 | N/A | N/A |  |  |  | 12/31/2006 |  | 12/31/2006 | N | No
P46 | Lena 138kV | EcoGrove WF (67 WT) | IL | JoDaviess | In Service | ComEd | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p46_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p46_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p46_csa.pdf | Document Posted | N/A | N/A | 2/11/2009 | 1/23/2006 | N/A | N/A | 2/11/2009 |  |  | 3/11/2009 | 3/11/2009 | 10/1/2007 | N | No
P47 | Mansfield-S. Troy 115kV | Armenia Mountain WF | PA | Bradford | In Service | PENELEC | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p47_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p47_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p47_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p47_csa.pdf | Document Posted | N/A | N/A | 10/23/2009 | 1/25/2006 | N/A | N/A | 11/4/2009 |  |  | 12/16/2009 | 12/16/2009 | 12/16/2009 | N | No
P49 | Adkins 345kV | Darby Generating Station | OH | Pickaway | In Service | Dayton | 564 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P50 | Greenville 69kV | Greenville Electric Generating Station | OH | Darke | In Service | Dayton | 236 | 14 | 14 | 14 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P51 | Stuart 345kV | Stuart Electric Generating Station | OH | Adams | In Service | Dayton | 2362 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p51_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P59 | Belington 138kV | Laurel Mountain WF | WV | Barbour | In Service | APS | 97.6 | 97.6 | 19.52 | 97.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p59_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p59_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A | 5/23/2011 |  |  | 6/15/2011 | 6/15/2011 | 12/31/2008 | N | No
P60 | New Baltimore 115kV (Stony Creek) | Stony Creek WF | PA | Somerset | In Service | PENELEC | 52.5 | 52.5 | 10.5 | 52.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p60_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/p60_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p60_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p60_csa.pdf | Document Posted | N/A | N/A | 10/22/2009 | 1/31/2006 | N/A | N/A | 10/23/2009 |  |  | 3/1/2010 | 3/1/2010 | 3/1/2010 | N | No
P61 | Gavin #1 765kV | Gavin 1 | OH | Adams | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p61_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p61_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p61_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p61_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A |  |  |  | 1/1/2010 | 1/1/2010 | 5/1/2007 | N | No
P62 | Gavin #2 765kV | Gavin 2 | OH | Adams | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/p62_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/p62_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/p62_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/p62_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A |  |  |  | 5/1/2009 | 5/1/2009 | 5/1/2009 | N | No
Q01 | Olive-Dequine 345kv | Fowler Ridge WF | IN | Benton | In Service | AEP | 500 | 500 | 100 | 500 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q01_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q01_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2006 | N/A | N/A |  |  |  | 7/1/2009 | 7/1/2009 | 12/1/2008 | N | No
Q03 | Olive-Dequine 345kV | Fowler Ridge 4 WF | IN | Benton | In Service | AEP | 250 | 250 | 50 | 250 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/13/2006 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 12/3/2015 | N | No
Q09 | Emporia | Emporia Hydro | VA | Greensville | In Service | Dominion | 2.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q09_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q09_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q09_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/21/2006 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
Q10 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 238 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/23/2006 | N/A | N/A |  |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
Q18 | Moser 34.5kV | Pottstown LF Units 1 & 2 | PA | Montgomery | In Service | PECO | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/8/2006 | N/A | N/A |  |  |  | 11/6/2007 | 11/6/2007 | 11/6/2007 | N | No
Q20 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 249 | 140 | 140 | 140 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q20_csa.pdf | Document Posted | N/A | N/A |  | 3/17/2006 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 10/30/2010 | N | No
Q22 | Columbia 34.5kV | Great Bear Hydro | NJ | Warren | In Service | JCPL | 0.5 | 0.5 | 0.5 | 0.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q22_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q22_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q22_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/20/2006 | N/A | N/A |  |  |  | 5/5/2009 | 5/5/2009 | 12/26/2006 | N | No
Q27 | Frackville-Shennandoah 69kV | Locust Ridge II WF | PA | Schuylkill | In Service | PPL | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q27_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q27_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2006 | N/A | N/A | 10/23/2008 |  |  | 4/29/2009 | 4/29/2009 | 4/29/2009 | N | No
Q31 | Wagner 34kV | Hawkins Point | MD | Baltimore City | In Service | BGE | 10 | 10 | 0 | 10 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q31_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q31_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q31_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/11/2006 | N/A | N/A |  |  |  | 4/24/2007 | 4/24/2007 | 6/1/2006 | N | No
Q36 | Philipsburg - Tyrone North 115kV | Sandy Ridge WF | PA | Centre | In Service | PENELEC | 50 | 50 | 10 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q36_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2006 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 4/17/2012 | N | No
Q43 | Clinch River 138kV | Virginia City Hybrid Energy Center - 1 Unit | VA | Wise | In Service | AEP | 534 | 534 | 534 | 534 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q43_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q43_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q43_csa.pdf | Document Posted | N/A | N/A | 11/12/2010 | 6/7/2006 | N/A | N/A |  |  |  | 3/1/2012 |  | 3/22/2012 | N | No
Q44 | Elizabethtown | Elizabethtown | PA | Lancaster | In Service | PPL | 0.3 | 0.3 | 0 | 0.3 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q44_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q44_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/q44_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/9/2006 | N/A | N/A |  |  |  | 7/1/2006 |  | 7/1/2006 | N | No
Q45 | North Lebanon 13.2kV | GLRA LF | PA | Lebanon | In Service | ME | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q45_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q45_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q45_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q45_csa.pdf | Document Posted | N/A | N/A |  | 6/14/2006 | N/A | N/A |  |  |  | 9/25/2007 | 9/25/2007 | 9/25/2007 | N | No
Q47 | Peach Bottom | Peach Bottom - Units 2 & 3 | PA | York | In Service | PECO | 2532 | 140 | 140 | 140 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q47_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q47_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q47_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 4/1/2013 | 4/1/2013 | 11/12/2012 | N | No
Q49 | Dresden 345kV | Dresden Nuclear Generating Station U2 | IL | Grundy | In Service | ComEd | 957 | 70 | 70 | 70 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 11/14/2011 | N | No
Q50 | Dresden 345kV | Dresden Nuclear Station Unit 3 | IL | Grundy | In Service | ComEd | 957 | 70 | 70 | 70 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 12/12/2012 | N | No
Q51 | Quad City 345kV | Quad Cities - Units 1 & 2 | IL | Rock Island | In Service | ComEd | 1914 | 140 | 140 | 140 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q51_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 9/25/2011 | N | No
Q53 | Summit-West Fall 115kV | Chestnut Flats WF | PA | Blair | In Service | PENELEC | 38 | 38 | 7.6 | 38 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q53_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q53_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q53_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q53_csa.pdf | Document Posted | N/A | N/A |  | 6/23/2006 | N/A | N/A |  |  |  | 5/20/2011 | 5/20/2011 | 5/20/2011 | N | No
Q57 | Steward-Waterman 138kV | Lee - DeKalb Wind Energy Center | IL | Lee | In Service | ComEd | 240 | 240 | 48 | 237.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q57_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q57_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q57_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q57_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q57_csa.pdf | Document Posted | N/A | N/A |  | 7/6/2006 | N/A | N/A |  |  |  | 6/1/2010 | 6/1/2010 | 11/14/2014 | N | No
Q59 | S. Reading-Birdsboro 64kV | Pioneer Crossing LF | PA | Berks | In Service | ME | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q59_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q59_csa.pdf | Document Posted | N/A | N/A |  | 7/7/2006 | N/A | N/A |  |  |  | 5/30/2008 | 5/30/2008 | 5/30/2008 | N | No
Q63 | Seneca 230kV | Seneca Pumped Storage Generating Station Unit 1 | PA | Warren | In Service | PENELEC | 468 | 16 | 16 | 16 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/11/2006 | N/A | N/A |  |  |  | 8/11/2010 | 8/11/2010 | 8/11/2010 | N | No
Q69 | Shackleford 34.5kV | King - Queen | VA | Brunswick | In Service | Dominion | 10 | 10 | 10 | 10 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q69_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q69_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q69_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q69_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2006 | N/A | N/A |  |  |  | 2/7/2008 | 2/7/2008 | 2/7/2008 | N | No
Q70 | Lawrenceville 34.5kV | Brunswick | VA | King and Queen | In Service | Dominion | 11 | 11 | 11 | 11 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q70_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q70_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q70_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2006 | N/A | N/A |  |  |  | 11/1/2007 | 11/1/2007 | 11/1/2007 | N | No
Q71 | Cranes Corner 13.2kV | Strafford Regional LF | VA | Stafford | In Service | Dominion | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q71_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q71_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q71_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q71_csa.pdf | Document Posted | N/A | N/A | 2/3/2009 | 7/26/2006 | N/A | N/A | 2/6/2009 |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
Q79 | Ft. Martin - Kammer 500kV | Longview ST1 | WV | Monongalia | In Service | APS | 700 | 100 | 100 | 100 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q79_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q79_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/5/2009 | 7/31/2006 | N/A | N/A | 5/6/2011 |  |  | 4/22/2011 | 4/22/2011 | 9/1/2010 | N | No
Q90 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 650 | 650 | 650 | 650 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/q90_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/q90_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/q90_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/q90_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/q90_csa.pdf | Document Posted | N/A | N/A | 7/1/2014 | 7/31/2006 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 8/11/2014 | N | No
R12 | Bedington - Nipetown |  | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/r12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/r12_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/r12_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2006 | N/A | N/A |  |  |  | 4/4/2008 | 4/4/2008 | 6/1/2008 | S | No
R14 | Tait 69kV | Tait Generating Units 4-7 | OH | Montgomery | In Service | Dayton | 376 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r14_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r14_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2006 | N/A | N/A |  |  |  | 5/1/2007 | 5/1/2007 | 5/1/2007 | N | No
R15 | Adkins 345kV | Darby Generation Station Units 1-6 | OH | Pickaway | In Service | Dayton | 564 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r15_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r15_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r15_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2006 | N/A | N/A |  |  |  | 5/1/2007 | 5/1/2007 | 5/1/2007 | N | No
R18 | Blackhawk | Winnebago Energy Center | IL | Boone | In Service | ComEd | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r18_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r18_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/r18_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/2/2006 | N/A | N/A |  |  |  | 1/3/2008 | 1/3/2008 | 1/3/2008 | N | No
R19 | Ladysmith 230kV | Ladysmith CT Units 3 & 4 | VA | Caroline | In Service | Dominion | 720 | 340 | 340 | 340 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r19_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r19_csa.pdf | Document Posted | N/A | N/A |  | 10/3/2006 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
R20 | Rock Springs | Rock Springs Units 3 & 4 | MD | Cecil | In Service | ODEC | 330 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/4/2006 | N/A | N/A |  |  |  | 7/1/2010 | 7/1/2010 | 1/1/2007 | N | No
R23 | Lakewood 230kV | Ocean Peaking Power (Lakewood CT1, CT2) | NJ | Ocean | In Service | JCPL | 375.6 | 20 | 20 | 19.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r23_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/16/2006 | N/A | N/A |  |  |  | 1/1/2007 |  | 1/1/2007 | N | No
R32 | Salix - Claysburg 115kV | Highland North | PA | Cambria | In Service | PENELEC | 75 | 75 | 15 | 75 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r32_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r32_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r32_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2006 | N/A | N/A | 10/23/2010 |  |  | 3/31/2012 | 3/31/2012 | 3/23/2012 | N | No
R33 | Nelson 345 kV | Nelson Energy Center | IL | Unknown | In Service | ComEd | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r33_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r33_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r33_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r33_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r33_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2006 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 5/8/2015 | N | No
R40 | Rockwood - Meyersdale 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 1.8 | 1.8 | 0.36 | 1.8 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r40_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r40_csa.pdf | Document Posted | N/A | N/A |  | 11/15/2006 | N/A | N/A |  |  |  | 6/30/2008 | 6/30/2008 | 6/30/2008 | N | No
R49 | Haviland - Milan 138kV | Timber Road II WF | OH | Paulding | In Service | AEP | 99 | 150 | 30 | 99 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r49_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r49_csa.pdf | Document Posted | N/A | N/A | 6/9/2011 | 12/6/2006 | N/A | N/A | 6/13/2011 |  |  | 12/31/2012 | 12/31/2012 | 7/15/2011 | N | No
R60 | Convoy-East Lima 345kV | Blue Creek WF | OH | Van Wert | In Service | AEP | 350 | 350 | 70 | 304 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r60_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r60_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r60_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/15/2011 | 1/8/2007 | N/A | N/A | 10/7/2011 |  |  | 4/1/2012 | 4/1/2012 | 4/1/2012 | N | No
R62 | Big Sandy 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r62_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r62_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r62_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/8/2007 | N/A | N/A |  |  |  | 6/1/2009 | 6/1/2009 | 5/31/2016 | N | No
R63 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 356 | 19 | 19 | 19 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
R66 | Fairlawn 138kV | Marcal Paper | NJ | Bergen | In Service | PSEG | 67 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r66_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r66_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r66_csa.pdf | Document Posted | N/A | N/A |  | 1/12/2007 | N/A | N/A |  |  |  | 5/1/2009 | 5/1/2009 | 3/1/2007 | N | No
R73 | Indian River 138kV | Indian River Units #3 & #4 | DE | Sussex | In Service | DPL | 170 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/18/2007 | N/A | N/A |  |  |  | 12/10/2008 | 12/10/2008 | 12/10/2008 | N | No
R74 | Carlls Corner | Shoreham Energy Units 1-3 | NJ | Atlantic | In Service | AEC | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r74_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/r74_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/19/2007 | N/A | N/A |  |  |  | 11/14/2008 | 11/14/2008 | 11/14/2008 | N | No
R76 | Kanawha 138kV | Hawks Nest Hydro | WV | Fayette | In Service | AEP | 54.159 | 54.159 | 5.5 | 6.159 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r76_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r76_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r76_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/r76_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r76_csa.pdf | Document Posted | N/A | N/A |  | 1/23/2007 | N/A | N/A |  |  |  | 1/23/2017 | 1/23/2017 | 3/1/2009 | N | No
R80 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 640 | 0 | 60 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r80_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r80_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r80_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/26/2007 | N/A | N/A |  |  |  | 1/26/2017 | 1/26/2017 | 4/30/2015 | N | No
R81 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 1268 | 101 | 101 | 101 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r81_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r81_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/r81_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r81_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r81_csa.pdf | Document Posted | N/A | N/A |  | 1/26/2007 | N/A | N/A |  |  |  | 2/8/2010 | 2/8/2010 | 2/8/2010 | N | No
R82 | Kanawha #1 | Kanawna River #1 | WV | Kanawha | In Service | AEP | 200 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r82_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r82_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r82_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R83 | Kanawha #2 | Kanawna River #2 | WV | Kanawha | In Service | AEP | 200 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r83_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r83_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r83_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R84 | Picway #5 | Pickway #5 | OH | Pickaway | In Service | AEP | 95 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r84_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r84_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r84_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R85 | Tanners Creek #1 | Tanners Creek #1 | IN | Dearborn | In Service | AEP | 145 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r85_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r85_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R86 | Tanners Creek #2 | Tanners Creek #2 | IN | Dearborn | In Service | AEP | 145 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r86_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r86_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R87 | Muskingum River #5 | Muskingum River #5 | OH | Washington | In Service | AEP | 585 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r87_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r87_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r87_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R89 | Conowingo | Conowingo Hydro Station | MD | Harford | In Service | PECO | 572 | 24 | 24 | 12 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r89_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r89_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r89_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/30/2007 | N/A | N/A |  |  |  | 12/1/2010 | 12/1/2010 | 12/1/2010 | N | No
R91 | Columbus-NJ |  | NJ | Burlington | In Service | PSEG | 0.37 | 0.37 | 0 | 0.25 | Energy | Generation Interconnection | Methane |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r91_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/r91_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2007 | N/A | N/A |  |  |  | 10/15/2008 | 10/15/2008 | 6/1/2007 | N | No
R97 | Rockport 765kV | Rockport Unit 1 | IN | Spencer | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/r97_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/r97_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/r97_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2007 | N/A | N/A |  |  |  | 11/1/2011 | 11/1/2011 | 11/1/2011 | N | No
S03 | Edgemoor 230kV | Edgemoor #5 | DE | New Castle | In Service | DPL | 450 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s03_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/13/2007 | N/A | N/A |  |  |  | 12/31/2007 | 12/31/2007 | 12/31/2007 | N | No
S05 | Seneca #2 230kV | Seneca Pumped Generating Station Unit 2 | PA | Warren | In Service | PENELEC | 468 | 16 | 16 | 16 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s05_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/27/2007 | N/A | N/A |  |  |  | 8/11/2010 | 8/11/2010 | 8/11/2010 | N | No
S06 | Olive-DeQuine 345kV | Meadow Lake | IN | White | In Service | AEP | 202 | 202 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s06_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s06_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2007 | N/A | N/A |  |  |  | 10/6/2009 | 10/6/2009 | 12/1/2009 | N | No
S13 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 238 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s13_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/19/2007 | N/A | N/A |  |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
S27 | Blue Mound I | Twin Groves I WF | IL | McLean | In Service | ComEd | 198 | 0 | 39.6 | 198 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s27_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2007 | N/A | N/A |  |  |  | 6/24/2010 | 6/24/2010 | 6/24/2010 | N | No
S28 | Blue Mound II | Twin Groves II WF | IL | McLean | In Service | ComEd | 198 | 0 | 39.6 | 198 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s28_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2007 | N/A | N/A |  |  |  | 6/24/2010 | 6/24/2010 | 6/24/2010 | N | No
S30 | Gould | Sun Paper | MD | Baltimore City | In Service | BGE | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s30_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s30_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/s30_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2007 | N/A | N/A |  |  |  | 8/8/2008 | 8/8/2008 | 12/31/2007 | N | No
S32 | Perryman | Perryman 6 Units 1-4 | MD | Harford | In Service | BGE | 130 | 130 | 130 | 130 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s32_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s32_csa.pdf | Document Posted | N/A | N/A | 5/6/2015 | 5/3/2007 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 5/9/2015 | N | No
S34 | Handsome Lake Energy 345kV | Handsome Lake | PA | Venango | In Service | PENELEC | 270 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s34_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s34_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/1/2007 |  | 6/1/2007 | N | No
S35 | Beverly 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 620 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s35_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s35_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/27/2007 | 6/27/2007 | 6/1/2008 | N | No
S36 | Kankakee 138 kV | Kankakee Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 175 | 35 | 175 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s36_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s36_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s36_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s36_csa.pdf | Document Posted | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/30/2015 | 6/30/2015 | 7/28/2015 | N | No
S37 | Kankakee 138kV | Kelly Creek Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 175 | 35 | 175 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s37_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s37_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s37_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s37_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s37_csa.pdf | Document Posted | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 11/9/2016 | N | No
S40 | Hegins | Commonwealth LF | PA | Schuylkill | In Service | PPL | 10.5 | 10.5 | 10.5 | 10.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s40_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s40_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s40_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s40_csa.pdf | Document Posted | N/A | N/A | 12/23/2008 | 5/10/2007 | N/A | N/A | 1/22/2009 |  |  | 1/21/2009 | 1/21/2009 | 1/21/2009 | N | No
S43 | Vineland | Vineland Unit #9 | NJ | Cumberland | In Service | AEC | 17 | 17 | 17 | 17 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s43_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s43_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s43_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/15/2007 | N/A | N/A |  |  |  | 11/12/2007 | 11/12/2007 | 11/12/2007 | N | No
S50 | Occoquan 230kV | Ogden Martin | VA | Fairfax | In Service | Dominion | 98 | 18 | 18 | 18 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s50_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/24/2007 | N/A | N/A |  |  |  | 6/30/2007 |  | 6/30/2007 | N | No
S55 | Zion 345kV | Zion Energy Center | IL | Lake | In Service | ComEd | 585 | 585 | 495 | 585 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s55_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/6/2007 | N/A | N/A |  |  |  | 2/25/2011 | 2/25/2011 | 12/19/2011 | N | No
S59 | Sharpsburg 12kV | Wenning Poultry | OH | Mercer | In Service | Dayton | 1.89 | 1.89 | 0 | 1.5 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s59_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/s59_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/25/2007 | N/A | N/A |  |  |  | 11/1/2007 |  | 10/30/2008 | N | No
S61 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s61_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s61_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s61_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/27/2007 | N/A | N/A |  |  |  | 10/11/2011 | 10/11/2011 | 10/11/2011 | N | No
S63 | Tait 69kV | Tait Generating Station | OH | Montgomery | In Service | Dayton | 376 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s63_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/5/2007 | N/A | N/A |  |  |  | 6/29/2007 |  | 10/5/2007 | N | No
S70 | Eureka 138kV | Willow Island Hydro Generation Project | WV | Wetzel | In Service | APS | 36.4 | 36.4 | 36.4 | 36.4 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s70_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s70_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s70_csa.pdf | Document Posted | N/A | N/A |  | 7/27/2007 | N/A | N/A |  |  |  | 7/31/2015 | 7/31/2015 | 11/15/2015 | N | No
S71 | Bluff Point 138kV | Bluff Point | IN | Jay | In Service | AEP | 120 | 120 | 24 | 120 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s71_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s71_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s71_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s71_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s71_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2007 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 9/15/2017 | N | No
S100 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 614 | 80 | 80 | 80 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s100_csa.pdf | Document Posted | N/A | N/A | 11/12/2010 | 7/31/2007 | N/A | N/A |  |  |  | 3/1/2012 |  | 3/22/2012 | N | No
S101 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 580 | 580 | 580 | 580 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s101_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s101_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 10/22/2011 | 10/22/2011 | 10/22/2011 | N | No
S102 | Ladysmith 230kV | Ladysmith Combustion Turbine Unit 5 | VA | Caroline | In Service | Dominion | 950 | 170 | 170 | 170 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s102_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 3/31/2009 | 3/31/2009 | 3/31/2009 | N | No
S103 | Warren 115kV | Warren Generating Station | PA | Warren | In Service | PENELEC | 57 | 57 | 57 | 57 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/s103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s103_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A | 4/5/2011 |  |  | 4/5/2011 | 4/5/2011 | 4/5/2011 | N | No
S108 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 1023 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/18/2010 | 5/18/2010 | 5/18/2010 | N | No
S109 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 1030 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/2/2010 | 5/2/2010 | 5/2/2010 | N | No
S110 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 1023 | 65 | 65 | 65 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/2/2010 | 5/2/2010 | 5/2/2010 | N | No
S111 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s111_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S112 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 1030 | 65 | 65 | 65 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/18/2010 | 5/18/2010 | 5/18/2010 | N | No
S113 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S114 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 75 | 75 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s114_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 6/13/2012 | N | No
S115 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 75 | 75 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s115_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s115_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 7/1/2011 | 7/1/2011 | 7/1/2011 | N | No
S121 | Vineland 69kV | Howard M. Down Power Plant Unit 11 | NJ | Cumberland | In Service | AEC | 63 | 63 | 63 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s121_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s121_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 4/18/2012 | N | No
S74 | Mount Storm 500kV | Mount Storm Unit 2 | WV | Grant | In Service | Dominion | 585 | 38 | 25 | 38 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s74_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s74_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S76 | Mount Storm 500kV | Mount Storm Unit 1 | WV | Grant | In Service | Dominion | 585 | 38 | 25 | 38 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s76_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s76_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s76_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/6/2013 | N | No
S79 | Chesterfield 230kV | Chesterfield Unit #6 | VA | Chesterfield | In Service | Dominion | 691 | 27 | 27 | 27 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s79_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s79_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 12/1/2010 | 12/1/2010 | 12/1/2010 | N | No
S80 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 356 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s80_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s80_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s80_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S82 | Surry 230kV | Gravel Neck Gas Turbine #3 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s82_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s82_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s82_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s82_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S83 | Surry 230kV | Gravel Neck Gas Turbine #4 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s83_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s83_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s83_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s83_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S84 | Surry 230kV | Gravel Neck Gas Turbine #5 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s84_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s84_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s84_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s84_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S85 | Surry 230kV | Gravel Neck Gas Turbine #6 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s85_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s85_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/s85_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S86 | Darbytown 230kV | Darbytown GT1 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s86_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s86_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S87 | Darbytown 230kV | Darbytown GT2 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s87_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s87_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s87_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S88 | Darbytown 230kV | Darbytown GT3 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s88_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s88_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s88_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S89 | Darbytown 230kV | Darbytown GT4 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s89_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s89_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s89_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S90 | Elizabeth River 230kV | Elizabeth River GT1 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s90_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s90_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s90_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S91 | Elizabeth River 230kV | Elizabeth River GT2 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s91_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s91_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s91_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S92 | Elizabeth River 230kV | Elizabeth River GT3 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s92_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s92_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s92_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S93 | Remington 230kV | Remington GT1 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s93_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s93_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s93_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S94 | Remington 230kV | Remington GT2 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s94_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s94_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s94_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S95 | Remington 230kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s95_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s95_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s95_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S96 | Remington 230kV | Remington GT4 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/s96_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/s96_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/s96_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
T10 | Cranes Corner 34.5KV | Stafford Regional LF | VA | Stafford | In Service | Dominion | 3 | 3 | 3 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t10_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 2/3/2009 | 8/15/2007 | N/A | N/A | 2/6/2009 |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
T11 | Laurel-Sussex 69kV | Southern LF Units 1-5 | DE | Sussex | In Service | DPL | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2007 | N/A | N/A |  |  |  | 5/21/2010 | 5/21/2010 | 5/21/2010 | N | No
T12 | Kent-Harrington 69kV | Central LF Units 1-4 | DE | Kent | In Service | DPL | 4.25 | 4 | 4 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t12_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2007 | N/A | N/A |  |  |  | 8/14/2007 |  | 10/1/2007 | N | No
T16 | Kelso Gap 138kV | Fair Wind Project | MD | Garrett | In Service | APS | 30 | 30 | 6 | 30 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t16_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t16_csa.pdf | Document Posted | N/A | N/A |  | 8/20/2007 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 11/15/2015 | N | No
T20 | Falls | Exelon Epuron Solar Energy Center | PA | Bucks | In Service | PECO | 3.3 | 3.3 | 1.1 | 3.3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t20_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t20_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2007 | N/A | N/A |  |  |  | 12/23/2008 | 12/23/2008 | 4/28/2008 | N | No
T41 | Kearny 138kV | Kearny #13 | NJ | Hudson | In Service | PSEG | 178 | 178 | 178 | 178 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t41_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t41_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t41_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t41_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t41_csa.pdf | Document Posted | N/A | N/A |  | 9/19/2007 | N/A | N/A |  |  |  | 8/31/2012 | 8/31/2012 | 5/7/2012 | N | No
T42 | Kearny 138kV | Kearny #14 | NJ | Hudson | In Service | PSEG | 89 | 89 | 89 | 89 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t42_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t42_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t42_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t42_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t42_csa.pdf | Document Posted | N/A | N/A |  | 9/19/2007 | N/A | N/A |  |  |  | 8/31/2012 | 8/31/2012 | 5/7/2012 | N | No
T49 | Steel City | Bethlehem Gen Facility Units 1 - 8 | PA | Northampton | In Service | PPL | 1134 | 42 | 42 | 42 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t49_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/6/2009 | 5/6/2009 | 5/6/2009 | N | No
T51 | Hay Road | Hay Road Units 1, 2, 3, 4 | DE | New Castle | In Service | DPL | 565 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t51_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t51_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/26/2010 | 5/26/2010 | 5/26/2010 | N | No
T52 | Red Lion 500kV | Hay Road Units 5, 6, 7, 8 | DE | New Castle | In Service | DPL | 565 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t52_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t52_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t52_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/1/2008 | 5/1/2008 | 5/1/2008 | N | No
T53 | Delaware City | Delaware City Unit #10 | DE | New Castle | In Service | DPL | 23.3 | 7.3 | 7.3 | 7.3 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t53_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 6/1/2008 |  | 6/1/2008 | N | No
T54 | Cumberland 138kV | Cumberland Unit 1 | NJ | Cumberland | In Service | AEC | 93.4 | 9.4 | 9.4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t54_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t54_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t54_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 8/12/2010 | 8/12/2010 | 8/12/2010 | N | No
T55 | Sherman Ave | Sherman Avenue Unit 1 | NJ | Cumberland | In Service | AEC | 93.4 | 12.4 | 12.4 | 12.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t55_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t55_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/3/2010 | 5/3/2010 | 5/3/2010 | N | No
T56 | Christiana | Christiana Units #11 & 14 | DE | New Castle | In Service | DPL | 53.4 | 8.4 | 8.4 | 8.4 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t56_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t56_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t56_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/31/2009 | 5/31/2009 | 5/31/2009 | N | No
T59 | Mickleton |  | NJ | Gloucester | In Service | AEC | 73.4 | 14.4 | 14.4 | 7.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t59_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t59_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 7/7/2011 | 7/7/2011 | 7/7/2011 | N | No
T66 | Tasley | Tasley | VA | Accomack | In Service | DPL | 33 | 6.7 | 6.7 | 6.7 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t66_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t66_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t66_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 3/26/2009 | 3/26/2009 | 3/26/2009 | N | No
T67 | West | West #1 | DE | New Castle | In Service | DPL | 20.3 | 5.3 | 5.3 | 5.3 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t67_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t67_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t67_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 4/1/2009 | 4/1/2009 | 4/1/2009 | N | No
T68 | Edgemoor | Edgemoor #10 | DE | New Castle | In Service | DPL | 18.2 | 5.2 | 5.2 | 5.2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t68_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t68_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t68_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 4/1/2009 | 4/1/2009 | 4/1/2009 | N | No
T73 | Hanging Rock 765kV | Hanging Rock CC2 | OH | Lawrence | In Service | AEP | 1240 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t73_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
T74 | Elgin | Elgin Energy Center | IL | Kane | In Service | ComEd | 484 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t74_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t74_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t74_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2007 | N/A | N/A |  |  |  | 9/1/2007 |  | 1/8/2013 | N | No
T75 | South River 230kV | South River | NJ | Middlesex | In Service | JCPL | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t75_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t75_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t75_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t75_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2007 | N/A | N/A |  |  |  | 4/16/2009 | 4/16/2009 | 11/15/2012 | N | No
T76 | South River 230 kV | South River | NJ | Middlesex | In Service | JCPL | 307 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t76_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t76_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t76_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t76_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2007 | N/A | N/A |  |  |  | 6/15/2009 |  | 11/15/2012 | N | No
T77 | Linden 230kV | Linden 1 & 2 | NJ | Union | In Service | PSEG | 1570 | 44 | 44 | 44 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t77_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t77_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 6/1/2008 | N | No
T78 | Arnolds Corner 34.5kV | King George Renewable Energy Facility | VA | King George | In Service | Dominion | 9.8 | 9.8 | 8.5 | 9.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t78_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t78_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t78_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t78_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 5/4/2010 | 5/4/2010 | 5/4/2010 | N | No
T79 | Shacklefords 34.5kv | Middle Pennisula Gas to Energy Power Plant | VA | Gloucester | In Service | Dominion | 6.2 | 6.2 | 6.2 | 6.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t79_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t79_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t79_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 10/1/2009 | 10/1/2009 | 10/1/2009 | N | No
T85 | Roxbury-Blain 23kV | Cumberland County LF | PA | Cumberland | In Service | PENELEC | 6.4 | 6.4 | 6 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t85_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t85_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t85_csa.pdf | Document Posted | N/A | N/A | 1/26/2009 | 10/16/2007 | N/A | N/A | 1/27/2009 |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
T86 | Bradford 34.5kV | North Tier LF | PA | Bradford | In Service | PENELEC | 1.6 | 1.6 | 1.5 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t86_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t86_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t86_csa.pdf | Document Posted | N/A | N/A |  | 10/16/2007 | N/A | N/A | 1/9/2009 |  |  | 7/1/2008 | 7/1/2008 | 7/1/2008 | N | No
T94 | Cook-Palesades 345kV |  | MI | Van Buren | In Service | ITCI | 1035 | 1035 | 1035 | 1035 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t94_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t94_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t94_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t94_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t94_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2007 | N/A | N/A |  |  |  | 6/30/2016 | 6/30/2016 | 6/1/2016 | N | No
T102 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 160 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t102_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/13/2007 | N/A | N/A |  |  |  | 10/30/2007 |  | 9/2/2008 | N | No
T103 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 160 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/13/2007 | N/A | N/A |  |  |  | 10/30/2007 |  | 9/2/2008 | N | No
T107 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 675 | 625 | 625 | 625 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t107_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 11/21/2007 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
T108 | Archbald 69kV | Archbald Generating Station | PA | Lackawanna | In Service | PPL | 9.2 | 9.2 | 9.2 | 9.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t108_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t108_csa.pdf | Document Posted | N/A | N/A |  | 11/29/2007 | N/A | N/A | 11/13/2009 |  |  | 1/25/2010 | 1/25/2010 | 1/25/2010 | N | No
T109 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 918 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/3/2007 | N/A | N/A |  |  |  | 8/23/2010 | 8/23/2010 | 8/23/2010 | N | No
T110 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 916 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/3/2007 | N/A | N/A |  |  |  | 8/23/2010 | 8/23/2010 | 8/23/2010 | N | No
T111 | Buchanan Hydro-Niles 69kV | Southeast Berrien LF | MI | Berrien | In Service | AEP | 6.4 | 6.4 | 6.4 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t111_csa.pdf | Document Posted | N/A | N/A |  | 12/12/2007 | N/A | N/A |  |  |  | 5/29/2009 | 5/29/2009 | 5/29/2009 | N | No
T117 | Hunlock Creek 69kV | Hunlock Creek | PA | Luzerne | In Service | UGI | 126 | 126 | 126 | 126 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t117_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t117_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t117_csa.pdf | Document Posted | N/A | N/A |  | 12/17/2007 | N/A | N/A |  |  |  | 6/30/2011 | 6/30/2011 | 1/31/2011 | N | No
T118 | Linwood 230kV | Phillips Island CT1, CT2, CT3, CT4 | PA | Delaware | In Service | PECO | 840 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t118_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t118_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/19/2007 | N/A | N/A |  |  |  | 9/30/2009 | 9/30/2009 | 9/30/2009 | N | No
T126 | Olive-Dequine 345kV | Meadow Lake WF II, Meadow Lake WF III | IN | Benton | In Service | AEP | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t126_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t126_csa.pdf | Document Posted | N/A | N/A |  | 1/2/2008 | N/A | N/A |  |  |  | 10/28/2010 | 10/28/2010 | 10/28/2010 | N | No
T127 | Olive-Dequine 345kV | Meadow Lake WF 4 - 5 | IN | White | In Service | AEP | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/2/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 10/30/2010 | N | No
T129 | Printz 230kV | Liberty | PA | Delaware | In Service | PECO | 541 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t129_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t129_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/8/2008 | N/A | N/A |  |  |  | 12/1/2008 | 12/1/2008 | 12/1/2008 | N | No
T131 | Lincoln-Sterling 138kV | Timber Road III | OH | Paulding | In Service | AEP | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t131_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t131_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t131_csa.pdf | Document Posted | N/A | N/A |  | 1/9/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/23/2016 | N | No
T147 | Perryman | Perryman Generating Unit 51 | MD | Harford | In Service | BGE | 183 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t147_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t147_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t147_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/24/2008 | N/A | N/A |  |  |  | 6/1/2008 |  | 6/1/2008 | N | No
T155 | Belknap 25kV | Mahoning Creek Dam Hydro Project | PA | Armstrong | In Service | APS | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t155_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/t155_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2008 | N/A | N/A |  |  |  | 3/1/2014 | 3/1/2014 | 12/26/2013 | N | No
T157 | New Creek Mountain 500kV | New Creek Mountain Wind Farm | WV | Mineral | In Service | Dominion | 102.5 | 102.5 | 20.5 | 102.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t157_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t157_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t157_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t157_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2008 | N/A | N/A |  |  |  | 12/18/2016 | 12/18/2016 | 12/26/2016 | N | No
T164 | Muskingum River | Muskingum River #5 | OH | Washington | In Service | AEP | 600 | 15 | 15 | 15 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t164_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t164_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t164_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 2/1/2008 | N | No
T174 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 930 | 930 | 900 | 930 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/t174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/t174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/t174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/t174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/t174_csa.pdf | Document Posted | N/A | N/A | 3/22/2018 | 1/31/2008 | N/A | N/A | 9/25/2018 |  |  | 3/1/2019 | 3/1/2019 | 11/18/2018 | N | No
U1-010 | Peach Bottom | Delta | PA | York | In Service | PECO | 575 | 18 | 18 | 18 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/7/2008 | N/A | N/A | 12/21/2010 |  |  | 3/1/2011 | 3/1/2011 | 3/1/2011 | N | No
U1-044 | Frederick County VA Regional Landfill | Fredrick County Regional LF | VA | Frederick | In Service | APS | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u1044_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/18/2008 | N/A | N/A |  |  |  | 11/4/2010 | 11/4/2010 | 1/1/2009 | N | No
U1-054 | Calumet | River Energy Center | IL | Cook | In Service | ComEd | 327 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/26/2008 | N/A | N/A |  |  |  | 3/28/2008 |  | 1/25/2013 | N | No
U1-059 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 48.3 | 48.3 | 9.6 | 48.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u1059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_059_csa.pdf | Document Posted | N/A | N/A |  | 4/2/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/15/2017 | N | No
U1-067 | Honey Brook | Granger of Honeybrook | PA | Lancaster | In Service | PPL | 3.2 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_067_csa.pdf | Document Posted | N/A | N/A |  | 4/9/2008 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
U1-093 | Ladysmith 230kV | Ladysmith Unit 3 | VA | Caroline | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1093_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_093_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 4/8/2008 | 4/8/2008 | 10/1/2009 | N | No
U1-094 | Ladysmith 230kV | Ladysmith Unit 4 | VA | Caroline | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1094_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1094_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_094_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_094_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 4/8/2008 | 4/8/2008 | 10/1/2009 | N | No
U1-095 | Ladysmith 230kV | Ladysmith Unit 5 | VA | Caroline | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u1095_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u1_095_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u1_095_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 3/31/2009 | 3/31/2009 | 3/31/2009 | N | No
U2-013 | Northeast 34.5kV | Richmond Energy Facility | VA | Henrico | In Service | Dominion | 8 | 8 | 8 | 6.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_013_csa.pdf | Document Posted | N/A | N/A | 9/15/2011 | 5/16/2008 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 12/29/2011 | N | No
U2-028 | Meadow Brook Capacitor |  | VA | Frederick | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IARR 64.5 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u2028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/u2028_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/u2_028_csa.pdf | Document Posted | N/A | N/A |  | 5/30/2008 | N/A | N/A |  |  |  | 10/26/2009 | 10/26/2009 | 6/1/2009 | S | No
U2-030 | Four Mile Ridge Wind 138kV | Four Mile Ridge WF - 24 WT | MD | Garrett | In Service | APS | 60 | 60 | 7.8 | 40 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2030_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_030_csa.pdf | Document Posted | N/A | N/A | 11/20/2014 | 6/5/2008 | N/A | N/A | 11/20/2014 |  |  | 12/23/2017 | 12/23/2017 | 11/21/2014 | N | No
U2-059 | Foul Rift 13kV | Belvidere SP | NJ | Warren | In Service | JCPL | 2 | 2 | 0.76 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u2059_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/7/2008 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 12/12/2011 | N | No
U2-061 | Garrett County | Roth Rock WF | MD | Garrett | In Service | APS | 50 | 50 | 6.5 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_061_csa.pdf | Document Posted | N/A | N/A | 11/23/2010 | 7/7/2008 | N/A | N/A | 12/5/2010 |  |  | 1/5/2011 | 1/5/2011 | 12/1/2009 | N | No
U2-063 | Croydon 230kV | Croydon Generating Station | PA | Bucks | In Service | PECO | 391 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2063_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_063_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/10/2008 | N/A | N/A |  |  |  | 7/1/2008 |  | 1/2/2014 | N | No
U2-067 | Eldred-Pine Grove 69kV | Westwood Generation | PA | Bucks | In Service | PPL | 32.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/15/2008 | N/A | N/A |  |  |  | 7/1/2008 |  | 12/29/2008 | N | No
U2-072 | East Lima-Marysville 345kV | Scioto Ridge Wind Farm | OH | Hardin | In Service | AEP | 250 | 250 | 32.5 | 250 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u2072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_072_csa.pdf | Document Posted | N/A | N/A | 4/1/2020 | 7/23/2008 | N/A | N/A | 12/17/2020 |  |  | 5/31/2021 | 5/31/2021 | 12/17/2020 | N | No
U2-073 | Frostburg 138kV II | Twin Ridges Wind Farm | PA | Somerset | In Service | APS | 139.4 | 139.4 | 18.1 | 139 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2073_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_073_csa.pdf | Document Posted | N/A | N/A |  | 7/23/2008 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/21/2012 | N | No
U2-077 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 300 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 300; NF/TWR 330 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/u2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/u2077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/u2_077_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/25/2008 | N/A | N/A |  |  |  | 10/1/2009 |  | 6/1/2011 | S | No
U2-090 | Desoto-Tanners Creek 345kV | HeadwatersWF | IN | Randolph | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u2090_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u2_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u2_090_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2008 | N/A | N/A |  |  |  | 10/31/2014 | 10/31/2014 | 10/27/2014 | N | No
U3-002 | Deer Creek-Fisher Body-Mullin 138kV | Wildcat Wind Farm I | IN | Madison | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3002_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_002_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u3_002_csa.pdf | Document Posted | N/A | N/A | 6/1/2012 | 8/13/2008 | N/A | N/A | 10/8/2012 |  |  | 12/31/2012 | 12/31/2012 | 12/26/2012 | N | No
U3-029 | Beaver Valley #1 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 950 | 48 | 37 | 48 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u3_029_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2008 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 11/15/2013 | N | No
U3-030 | Beaver Valley #2 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 951 | 43 | 38 | 43 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u3_030_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2008 | N/A | N/A |  |  |  | 11/1/2012 | 11/1/2012 | 11/7/2012 | N | No
U3-031 | Lincoln Generating Facility | Lincoln Generating Facility | IL | Will | In Service | ComEd | 616 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u3031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u3031_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u3_031_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2008 | N/A | N/A |  |  |  | 10/31/2009 |  | 1/24/2013 | N | No
U4-008 | South Central Power | Suburban LF | OH | Perry | In Service | AEP | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4008_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/u4008_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2008 | N/A | N/A |  |  |  | 1/7/2011 | 1/7/2011 | 1/7/2011 | N | No
U4-009 | Louisa 230kV | Louisa Gas Turbines Units 1 through 5 | VA | Orange | In Service | Dominion | 144 | 3 | 3 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4009_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_009_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/17/2008 | N/A | N/A |  |  |  | 5/26/2009 | 5/26/2009 | 5/26/2009 | N | No
U4-014 | Siegfried-Hauto 69kV | PA SP | PA | Carbon | In Service | PPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4014_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/u4014_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_014_csa.pdf | Document Posted | N/A | N/A |  | 11/24/2008 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 11/6/2012 | N | No
U4-015 | Rock Springs 500kV | Rocks Springs 1 & 2 | MD | Cecil | In Service | ODEC | 475 | 8.7 | 8.7 | 8.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/25/2008 | N/A | N/A |  |  |  | 5/7/2009 | 5/7/2009 | 5/31/2009 | N | No
U4-030 | Sabrooke 138kV | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 153 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_030_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/26/2008 | N/A | N/A |  |  |  | 6/23/2010 | 6/23/2010 | 6/23/2010 | N | No
U4-033 | University Park North |  | IL | Will | In Service | ComEd | 540 | 36 | 36 | 36 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4033_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_033_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/31/2008 | N/A | N/A |  |  |  | 6/1/2009 |  | 1/21/2014 | N | No
U4-036 | Gloucester 26.4kV | Paradise SP | NJ | Gloucester | In Service | PSEG | 5.1 | 5.1 | 1.9 | 5.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/u4036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/u4036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/u4_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/u4_036_csa.pdf | Document Posted | N/A | N/A | 12/22/2010 | 1/28/2009 | N/A | N/A | 12/22/2010 |  |  | 1/4/2011 | 1/4/2011 | 12/31/2009 | N | No
V1-011 | Haviland 138kV | Trishe Wind Ohio, LLC | OH | Paulding | In Service | AEP | 100 | 100 | 13 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1011_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1011_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_011_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v1_011_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2009 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 9/10/2018 | N | No
V1-021 | Cape May County 12kV | Cape May County Municipal Utiltities Authority (CM | NJ | Cape May | In Service | AEC | 1.9 | 1.9 | 1.7 | 1.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/23/2009 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 10/22/2013 | N | No
V1-023 | Bridge 12kV | Charlston LF | WV | Kanawha | In Service | AEP | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1023_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v1023_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/6/2009 | N/A | N/A |  |  |  | 12/7/2010 | 12/7/2010 | 12/7/2010 | N | No
V1-024 | LaSalle 1 | LaSalle Nuclear Station Unit 1 | IL | Lasalle | In Service | ComEd | 1188 | 20 | 11.9 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1024_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1024_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_024_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 11/1/2010 |  | 5/21/2015 | N | No
V1-025 | LaSalle 2 | LaSalle Nuclear Station Unit 2 | IL | Lasalle | In Service | ComEd | 1191 | 20 | 10.9 | 2.5 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v1025_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_025_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 3/1/2011 |  | 5/21/2015 | N | No
V1-028 | North Wales | Morris Road | PA | Montgomery | In Service | PECO | 10 | 2 | 2 | 2 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v1_028_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/16/2009 | N/A | N/A | 4/30/2012 |  |  | 5/31/2009 |  | 5/2/2012 | N | No
V1-030 | PSE&G Area |  | NJ | Various | In Service | PSEG | 52 | 52 | 19.8 | 46.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v1030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v1030_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2009 | N/A | N/A |  |  |  | 6/22/2010 | 6/22/2010 | 12/27/2011 | N | No
V1-034 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | JCPL | 673 | 3 | 0 |  | Energy | Merchant Transmission |  | DC | NF/TWR 673 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/v1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/v1034_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/v1034_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/v1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/v1_034_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2009 | N/A | N/A |  |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
V2-019 | Mansfield-S. Troy 115kV | AES Armenia Mountain Wind, LLC | PA | Bradford | In Service | PENELEC | 100.5 | 0.5 | 0 | 0.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/22/2010 | 6/18/2009 | N/A | N/A |  |  |  | 8/19/2010 |  | 8/19/2010 | N | No
V2-025 | Turnpike 13.8kV | Kearny SP | NJ | Hudson | In Service | PSEG | 5 | 5 | 1.9 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2025_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/30/2009 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 3/1/2012 | N | No
V2-030 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 950 | 950 | 875 | 950 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v2030_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_030_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 7/14/2009 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
V2-035 | Pittsgrove | Pittsgrove Solar, LLC | NJ | Salem | In Service | AEC | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2035_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v2035_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_035_csa.pdf | Document Posted | N/A | N/A |  | 7/20/2009 | N/A | N/A |  |  |  | 4/14/2014 | 4/14/2014 | 4/19/2014 | N | No
V2-037 | White Oak | White Oak | MD | Montgomery | In Service | PEPCO | 24 | 4.5 | 0 | 4.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/24/2009 | N/A | N/A |  |  |  | 5/3/2010 | 5/3/2010 | 3/31/2010 | N | No
V2-040 | Mountain Road 34.5kV | Henrico County Landfill | VA | Henrico | In Service | Dominion | 4 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v2_040_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2009 | N/A | N/A |  |  |  | 9/23/2010 | 9/23/2010 | 9/23/2010 | N | No
V2-041 | Clayville 12kV | Vineland-Mays Landing | NJ | Cumberland | In Service | AEC | 4 | 4 | 1.52 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2041_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2009 | N/A | N/A |  |  |  | 9/30/2011 | 9/30/2011 | 9/30/2011 | N | No
V2-046 | Pilesgrove Township 12kV | Pilesgrove SP | NJ | Salem | In Service | AEC | 19.9 | 19.9 | 7 | 18.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v2046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v2046_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/31/2009 | N/A | N/A |  |  |  | 7/31/2011 | 7/31/2011 | 7/31/2011 | N | No
V3-007 | Desoto-Tanners Creek #1 345kV | Headwaters II | IN | Randolph | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3007_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3007_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3007_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_007_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_007_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 8/10/2009 | N/A | N/A | 1/26/2021 |  |  | 9/1/2021 | 9/1/2021 | 1/26/2021 | N | No
V3-017 | Morgantown-Oak Grove | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_017_csa.pdf | Document Posted | N/A | N/A |  | 8/24/2009 | N/A | N/A |  |  |  | 11/1/2016 | 11/1/2016 | 11/25/2016 | N | No
V3-024 | Devils Brook 13.2kV | RE Cranbury Solar I, LLC | NJ | Middlesex | In Service | PSEG | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3024_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3024_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2009 | N/A | N/A |  |  |  | 9/27/2011 | 9/27/2011 | 9/27/2011 | N | No
V3-028 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | In Service | AEP | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_028_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2009 | N/A | N/A | 10/13/2020 |  |  | 6/1/2021 | 6/1/2021 | 9/29/2020 | N | No
V3-030 | St. Benedict-Patton 46kV | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 30.6 | 30.6 | 3.98 | 30.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_030_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2009 | N/A | N/A |  |  |  | 6/30/2013 | 6/30/2013 | 12/24/2012 | N | No
V3-036 | Ontario 23kV | Midtown Thermal Control Center | NJ | Atlantic | In Service | AEC | 5.5 | 5.5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3036_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_036_csa.pdf | Document Posted | N/A | N/A |  | 9/14/2009 | N/A | N/A |  |  |  | 12/1/2011 | 12/1/2011 | 12/1/2011 | N | No
V3-037 | Naval Academy Junction 13kV | Millersville Landfill & Resource Recovery Facility | MD | Anne Arundel | In Service | BGE | 4 | 4 | 4 | 3.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_037_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_037_csa.pdf | Document Posted | N/A | N/A |  | 9/14/2009 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 6/13/2012 | N | No
V3-041 | Daleville | SECCRA Units 1, 2 & 3 | PA | Chester | In Service | PECO | 4 | 2 | 3.2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_041_csa.pdf | Document Posted | N/A | N/A |  | 9/21/2009 | N/A | N/A |  |  |  | 11/1/2011 | 11/1/2011 | 12/15/2010 | N | No
V3-045 | Zimmer-Spurlock 345kV | Meldahl Hydroelectric Plant | OH | Butler | In Service | DEOK | 112 | 112 | 112 | 112 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v3045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_045_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2009 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 11/1/2015 | N | No
V3-051 | Letort | Turkey Hill Dairy WF | PA | Lancaster | In Service | PPL | 3.2 | 3.2 | 0.4 | 3.2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_051_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_051_csa.pdf | Document Posted | N/A | N/A |  | 10/16/2009 | N/A | N/A |  |  |  | 1/17/2011 | 1/17/2011 | 1/17/2011 | N | No
V3-052 | NI HUB-DC Cook |  | N/A | N/A | In Service | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v3052_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v3052_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v3052_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/21/2009 | N/A | N/A |  |  |  | 2/1/2013 | 2/1/2013 | 5/2/2012 | EE | No
V3-058 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3058_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_058_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_058_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/24/2011 | N | No
V3-059 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3059_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v3_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v3_059_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/24/2011 | N | No
V3-065 | Clay St. 4kV (Barringer) | Clay ST SP | NJ | Essex | In Service | PSEG | 0.549 | 0.549 | 0.21 | 0.549 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3065_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/1/2010 | N | No
V3-066 | Cook Road 13.8kV (Park) | Cook Rd SP | NJ | Essex | In Service | PSEG | 0.432 | 0.432 | 0.16 | 0.432 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3066_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 12/31/2010 | 12/31/2010 | 11/17/2010 | N | No
V3-067 | Norfolk St. 4kV (Central) | Newark I SP | NJ | Essex | In Service | PSEG | 0.773 | 0.773 | 0.29 | 0.773 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3067_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3067_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 3/16/2011 | 3/16/2011 | 2/16/2011 | N | No
V3-068 | Norfolk St. 4kV (New Central HS) | Newark II SP | NJ | Essex | In Service | PSEG | 0.425 | 0.425 | 0.16 | 0.425 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3068_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3068_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 12/20/2010 | 12/20/2010 | 12/31/2010 | N | No
V3-069 | Woodbridge 13kV (Matrix Bldg) | Woodbridge SP | NJ | Middlesex | In Service | PSEG | 2.308 | 2.308 | 0.877 | 2.308 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3069_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3069_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/31/2010 | 10/31/2010 | 1/26/2011 | N | No
V3-070 | J. Rinco 34.5kV | Lilac Site | NJ | Hunterdon | In Service | JCPL | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v3070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v3070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v3070_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 1/2/2012 | N | No
V4-001 | Lebanon 34.5kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4001_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/2/2009 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 1/2/2012 | N | No
V4-005 | Southampton 13.8kV | Lumberton SP | NJ | Burlington | In Service | PSEG | 2.9 | 2.9 | 1.1 | 2.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4005_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4005_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/11/2009 | N/A | N/A |  |  |  | 11/10/2011 | 11/10/2011 | 8/1/2010 | N | No
V4-006 | Byron 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4006_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4006_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4006_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 2/18/2012 |  | 12/12/2011 | EE | No
V4-007 | Quad City 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4007_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4007_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4007_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-011 | Granger Electric | Granger Electric of Hancock County | OH | Hancock | In Service | AEP | 3.2 | 3 | 0 | 3 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4011_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2009 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 3/31/2015 | N | No
V4-018 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 1425 | 475 | 415 | 475 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4018_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4018_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_018_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 11/25/2009 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
V4-019 | Bergen 230kV | Bergen Generating Station | NJ | Bergen | In Service | PSEG | 1209 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/25/2009 | N/A | N/A |  |  |  | 6/1/2013 |  | 5/31/2013 | N | No
V4-027 | Quarryville | Keystone Solar | PA | Lancaster | In Service | PPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/7/2009 | N/A | N/A |  |  |  | 12/30/2012 | 12/30/2012 | 9/17/2012 | N | No
V4-030 | Byron 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4030_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4030_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4030_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-031 | Quad 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/v4031_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/v4031_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/v4031_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-038 | Friendship Manor 34.5kV | Alpha Ridge Landfill | MD | Carroll | In Service | BGE | 1 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4038_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4038_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_038_csa.pdf | Document Posted | N/A | N/A |  | 12/16/2009 | N/A | N/A |  |  |  | 2/28/2013 | 2/28/2013 | 7/31/2012 | N | No
V4-045 | Peach Bottom | Peach Bottom Units 2 & 3 | PA | York | In Service | PECO | 2665.8 | 133.8 | 206 | 133.8 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 10/3/2015 |  | 1/6/2016 | N | No
V4-046 | Byron 1 | Byron Nuclear Generating Station, Unit 1 | IL | Ogle | In Service | ComEd | 1232 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4046_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_046_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-047 | Byron 2 | Byron Nuclear Generating Station, Unit 2 | IL | Ogle | In Service | ComEd | 1210 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_047_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-048 | Braidwood 1 | Braidwood Nuclear Generating Station, Unit 1 | IL | Will | In Service | ComEd | 1240 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-049 | Braidwood 2 | Braidwood Nuclear Generating Station, Unit 2 | IL | Will | In Service | ComEd | 1214 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4049_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4049_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_049_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-052 | West Reading | The Reading Hospital and Medical Center | PA | Berks | In Service | ME | 10 | 10 | 6 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4052_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4052_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/28/2009 | N/A | N/A |  |  |  | 7/12/2011 |  | 7/12/2011 | N | No
V4-054 | Fairfield Township 12kV | NJ Oak Solar | NJ | Cumberland | In Service | AEC | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4054_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/v4054_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_054_csa.pdf | Document Posted | N/A | N/A |  | 12/31/2009 | N/A | N/A |  |  |  | 12/20/2011 | 12/20/2011 | 12/20/2011 | N | No
V4-068 | Murphy's 34.5kV |  | NC | Hertford | In Service | Dominion | 5 | 5 | 3.23 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/v4_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/v4_068_csa.pdf | Document Posted | N/A | N/A | 8/1/2011 | 1/29/2010 | N/A | N/A | 8/1/2011 |  |  | 12/31/2011 | 12/31/2011 | 12/29/2011 | N | No
V4-069 | Frenchtown 34.5kV | Frenchtown 1 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4069_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4069_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 3/1/2011 | 3/1/2011 | 12/31/2011 | N | No
V4-070 | Frenchtown 12.5kV | Frenchtown 2 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4070_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 1/2/2012 | N | No
V4-073 | Yankee 12.5kV |  | OH | Montgomery | In Service | Dayton | 2.5 | 2.5 | 0.95 | 0.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/v4073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/v4073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/v4073_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 5/28/2010 | 5/28/2010 | 5/28/2010 | N | No
W1-001 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 15 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 15 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-isa/w1_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/2/2010 | N/A | N/A |  |  |  | 3/31/2010 |  | 6/1/2011 | S | No
W1-003 | Oak Hall | Oak Hall Project A | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1003_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1003_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_003_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
W1-004 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1004_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1004_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_004_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
W1-005 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1005_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_005_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
W1-006 | Oak Hall | Oak Hall Project D | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_006_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
W1-024 | Manalapan 12.5kV | Village at Manalapan Solar Farm | NJ | Monmouth | In Service | JCPL | 4 | 4 | 1.5 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1024_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_024_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_024_csa.pdf | Document Posted | N/A | N/A |  | 2/24/2010 | N/A | N/A |  |  |  | 6/30/2012 | 6/30/2012 | 12/14/2011 | N | No
W1-029 | Winfall 230kV | Desert Wind Farm | NC | Pasquotank | In Service | Dominion | 208 | 208 | 27 | 208 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1029_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1029_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_029_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 3/2/2017 | N | No
W1-032 | Millhurst 12.5kV | Millhurst Solar Farm | NJ | Monmouth | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1032_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_032_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_032_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 2/2/2016 | N | No
W1-045 | Roxbury 23 kV | Roxbury Solar Project | PA | Franklin | In Service | PENELEC | 13.5 | 13.5 | 5.13 | 13.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_045_csa.pdf | Document Posted | N/A | N/A |  | 3/4/2010 | N/A | N/A | 12/13/2019 |  |  | 12/31/2019 | 12/31/2019 | 12/31/2019 | N | No
W1-054 | South Akron-Prince | Dart Container | PA | Lancaster | In Service | PPL | 11.4 | 11.4 | 11.4 | 11.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_054_csa.pdf | Document Posted | N/A | N/A |  | 3/16/2010 | N/A | N/A |  |  |  | 12/31/2011 |  | 10/6/2012 | N | No
W1-056 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 66.7 | 18.4 | 2.4 | 18.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_056_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2010 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/15/2017 | N | No
W1-062 | Clayton 138kV | Smyrna Units 1 & 2 | DE | Kent | In Service | DPL | 101 | 53 | 53 | 53 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_062_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2010 | N/A | N/A |  |  |  | 5/31/2012 | 5/31/2012 | 6/15/2012 | N | No
W1-072A_AT5 | Lemoyne | Troy Energy | OH | Wood | In Service | ATSI | 640 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1072a_at5_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1072a_at5_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1072a_at5_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_072a_at5_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 4/11/2014 | N | No
W1-077 | Shacklefords 34.5kV | King and Queen | VA | King and Queen | In Service | Dominion | 14 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_077_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 9/1/2011 | N | No
W1-078 | Sammis-Wylie Ridge 345kV |  | OH | Jefferson | In Service | APS |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w1078_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/w1_078_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 5/30/2012 | S | No
W1-101 | Bayonne 13kV | Bayonne SP | NJ | Hudson | In Service | PSEG | 1.4 | 1.4 | 0.532 | 1.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1101_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1101_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 3/14/2011 | 3/14/2011 | 3/14/2011 | N | No
W1-108 | Grays Ferry 230kV | Grays Ferry Cogeneration Partnership | PA | Philadelphia | In Service | PECO | 163 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 7/29/2013 | N | No
W1-111 | Harwood-Berwick 69kV | Beacon Power Flywheel Station | PA | Luzerne | In Service | PPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1111_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1111_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_111_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 7/24/2014 | N | No
W1-112 | Holmdel | Holmdel SP | NJ | Monmouth | In Service | JCPL | 4 | 4 | 1.52 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1112_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 3/1/2013 | 3/1/2013 | 3/1/2013 | N | No
W1-113 | Millstone 2 | Northpark Solar Farm #1 | NJ | Monmouth | In Service | JCPL | 8 | 8 | 3 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_113_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 3/22/2016 | N | No
W1-116 | Emmitsburg 34kV | Mount St. Mary's PV Park | MD | Frederick | In Service | APS | 14 | 14 | 5.32 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1116_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_116_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 4/30/2012 | 4/30/2012 | 7/5/2012 | N | No
W1-119 | Pemberton Township 1 34.5 kV | Greenburg Solar | NJ | Burlington | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1119_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1119_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 6/16/2017 | N | No
W1-120 | Pemberton Township 2 34.5 kV | Perez Solar | NJ | Burlington | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1120_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1120_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 6/15/2017 | N | No
W1-121 | Crosswicks 13kV | Property #6 | NJ | Mercer | In Service | PSEG | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1121_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1121_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1121_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 1/1/2012 | 1/1/2012 | 12/14/2011 | N | No
W1-124 | Tinton Falls 34.5kV | Tinton Falls Solar | NJ | Monmouth | In Service | JCPL | 16.9 | 16.9 | 6.4 | 16.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1124_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_124_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_124_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 8/1/2014 | 8/1/2014 | 12/6/2012 | N | No
W1-127 | Phillipsburg 12.47kV | Harmony Solar Farm | NJ | Warren | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_127_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_127_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 6/30/2015 | N | No
W1-129 | Cookstown 34.5kV | Jacobstown Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1129_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w1_129_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w1_129_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 5/29/2014 | 5/29/2014 | 9/20/2014 | N | No
W1-130 | Vine Road 12kV | Cedar Branch Solar Farm | NJ | Cumberland | In Service | AEC | 9.2 | 9.2 | 3.5 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w1130_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1130_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 10/27/2016 | N | No
W1-132 | Pittstown | Paunch Solar | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w1132_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w1132_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 12/6/2013 | N | No
W2-010 | Conemaugh Unit 1 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 870 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2010 | N/A | N/A |  |  |  | 6/30/2013 |  | 7/9/2012 | N | No
W2-011 | Conemaugh Unit 2 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 870 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2011_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_011_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2010 | N/A | N/A |  |  |  | 6/30/2013 |  | 7/9/2012 | N | No
W2-014 | Richmond |  | PA | Philadelphia | In Service | PECO | 98 | 2 | 2 | 2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/25/2010 | N/A | N/A |  |  |  | 11/25/2010 |  | 6/24/2014 | N | No
W2-016 | Frenchtown 34.5kV | Barbertown-Point Breeze Solar Farm | NJ | Hunterdon | In Service | JCPL | 15 | 15 | 5.7 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2016_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2016_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/25/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 12/31/2013 | N | No
W2-018 | Cumberland County Landfill | Cumberland County Landfill | PA | Cumberland | In Service | PENELEC | 11.2 | 4.8 | 4.8 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 4/22/2012 | N | No
W2-019 | Wrightstown 34.5kV | Shemesh Solar Farm | NJ | Burlington | In Service | JCPL | 6 | 6 | 2.3 | 4.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_019_csa.pdf | Document Posted | N/A | N/A | 9/22/2016 | 5/28/2010 | N/A | N/A | 10/1/2016 |  |  | 9/30/2016 | 9/30/2016 | 10/24/2016 | N | No
W2-030 | Egg Harbor Township | 1307 Doughty Road | NJ | Atlantic | In Service | AEC | 9.6 | 9.6 | 3.65 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2030_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2030_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/3/2010 | N/A | N/A |  |  |  | 9/30/2016 | 9/30/2016 | 10/4/2016 | N | No
W2-036 | Polhemus Lane 13kV | Central SP | NJ | Somerset | In Service | PSEG | 0.749 | 0.749 | 0.284 | 0.749 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2036_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2036_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/18/2010 | N/A | N/A |  |  |  | 3/21/2010 | 3/21/2010 | 3/21/2011 | N | No
W2-038 | East Frankfort-Crete | Powerton – Joliet SPS | IL | Will | In Service | ComEd | 800 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/w2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/w2038_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/w2_038_csa.pdf | Document Posted | N/A | N/A |  | 6/22/2010 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 10/5/2011 | S | No
W2-039 | Clayville 69kV | Clayville Unit #1 | NJ | Cumberland | In Service | AEC | 63 | 63 | 63 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2039_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2039_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_039_csa.pdf | Document Posted | N/A | N/A |  | 6/28/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 11/1/2015 | N | No
W2-048 | Brokaw-Lanesville | Hilltopper Wind, LLC | IL | Logan | In Service | ComEd | 62.5 | 62.5 | 0 | 62.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_048_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2010 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 11/1/2018 | N | No
W2-049 | Reedy Creek 115kV | South Boston Energy Facility | VA | Halifax | In Service | Dominion | 47.4 | 47.4 | 47.4 | 47.4 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2049_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w2049_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_049_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2010 | N/A | N/A |  |  |  | 5/30/2013 |  | 9/24/2013 | N | No
W2-050 | Flemington | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 10 | 0 | 8 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_050_csa.pdf | Document Posted | N/A | N/A | 4/1/2016 | 7/13/2010 | N/A | N/A |  |  |  | 4/1/2016 | 4/1/2016 | 3/22/2016 | N | No
W2-052 | Pierson Avenue 13kV |  | NJ | Middlesex | In Service | PSEG | 0.592 | 0.592 | 0.225 | 0.592 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2052_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2052_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/19/2010 | N/A | N/A |  |  |  | 3/14/2011 | 3/14/2011 | 3/14/2011 | N | No
W2-056 | Lumberton 13kV | Reeves Station Road Solar | NJ | Burlington | In Service | PSEG | 11 | 11 | 4.18 | 11 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2056_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2056_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/23/2010 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 10/16/2012 | N | No
W2-057 | Laurel Mountain | Laurel Mountain BT | WV | Barbour | In Service | APS | 125 | 27.4 | 0 | 27.4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_057_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/28/2010 | N/A | N/A |  |  |  | 7/30/2011 | 7/30/2011 | 9/21/2011 | N | No
W2-061 | Ringoes 12kV | Everitt Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2061_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2061_wmpa.pdf |  | Not Required | N/A | N/A | 5/23/2016 | 7/29/2010 | N/A | N/A | 5/23/2016 |  |  | 1/18/2017 | 1/18/2017 | 6/1/2016 | N | No
W2-071 | Mt. Laurel 13kV |  | NJ | Burlington | In Service | PSEG | 2.8 | 2.8 | 1.06 | 2.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2071_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 10/31/2011 | 10/31/2011 | 12/15/2011 | N | No
W2-075 | Tolna Unit 2 | Tolna Unit 2 | PA | York | In Service | ME | 20 | 0.9 | 0.9 | 0 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2075_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_075_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 8/31/2010 |  | 7/28/2011 | N | No
W2-078 | Applegarth 12.5kV | Northpark Solar Farm #2 | NJ | Monmouth | In Service | JCPL | 9 | 9 | 3.4 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2078_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 3/22/2016 | N | No
W2-080 | Stanton 12kV | Fisher Solar Farm | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0.8 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2080_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 6/25/2017 | 6/25/2017 | 5/30/2017 | N | No
W2-082 | Fort Dix-McGuire 34.5kV | North Hanover Solar Farm | NJ | Burlington | In Service | JCPL | 8 | 17 | 3 | 8.25 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2082_wmpa.pdf |  | Not Required | N/A | N/A | 3/17/2017 | 7/30/2010 | N/A | N/A | 3/17/2017 |  |  | 1/17/2017 | 1/17/2017 | 3/17/2017 | N | No
W2-091 | Broadway-Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 10 | 10 | 0 | 8 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2091_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w2091_wmpa.pdf |  | Not Required | N/A | N/A | 5/20/2016 | 7/30/2010 | N/A | N/A | 5/20/2016 |  |  | 6/13/2016 | 6/13/2016 | 5/31/2016 | N | No
W2-102 | Mt. Holly 26.4kV | West Pemberton Solar | NJ | Burlington | In Service | PSEG | 7 | 7 | 2.66 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w2102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w2_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w2_102_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 7/3/2014 | N | No
W3-002 | Occoquan 34.5kV | I-95 Landfill Phase 2 | VA | Fairfax | In Service | Dominion | 3.2 | 3.2 | 2.9 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3002_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_002_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/2/2010 | N/A | N/A |  |  |  | 4/1/2011 | 4/1/2011 | 4/1/2011 | N | No
W3-003 | East Flemington-Frenchtown 34.5kV | Quakertown Solar Farm #1 | NJ | Hunterdon | In Service | JCPL | 10 | 10 | 0 | 10 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_003_csa.pdf | Document Posted | N/A | N/A |  | 8/3/2010 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 10/30/2018 | N | No
W3-029 | Buckeye-Ringoes 34.5kV | Ringoes Solar Farm | NJ | Hunterdon | In Service | JCPL | 8.4 | 8.4 | 3.2 | 8.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3029_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/30/2010 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 6/4/2018 | N | No
W3-032A | Cartanza 230kV | Garrison Energy Center | DE | New Castle | In Service | DPL | 309.2 | 309.2 | 309.2 | 309.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3032a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3032a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3032a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_032a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_032a_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 5/21/2015 | N | No
W3-044 | Washington 34.5kV | McCullough Road Solar Farm | NJ | Warren | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3044_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3044_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A | 6/27/2019 |  |  | 6/30/2019 | 6/30/2019 | 6/27/2019 | N | No
W3-047 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 1464 | 39 | 60 | 39 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w3_047_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 8/31/2010 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
W3-048 | Hope Creek 500kV | Hope Creek Generating Station | NJ | Salem | In Service | PSEG | 1275 | 50 | 50 | 50 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3048_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A |  |  |  | 6/1/2012 |  | 1/23/2013 | N | No
W3-077 | Broadway-Stewartsville 34.5kV | Franklin Township Solar Farm | NJ | Warren | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3077_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A | 12/4/2019 |  |  | 1/31/2020 | 1/31/2020 | 1/10/2020 | N | No
W3-079 | Allenwood-Larabee 34.5kV | Lakewood-Farmingdale Road Solar Farm | NJ | Monmouth | In Service | JCPL | 7 | 7 | 2.6 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3079_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3079_wmpa.pdf |  | Not Required | N/A | N/A | 3/11/2016 | 9/30/2010 | N/A | N/A |  |  |  | 10/6/2016 | 10/6/2016 | 4/19/2016 | N | No
W3-080 | Burlington 26kV | Cedar Lane | NJ | Burlington | In Service | PSEG | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3080_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A |  |  |  | 11/15/2016 | 11/15/2016 | 12/29/2016 | N | No
W3-106 | Sussex-Wykertown 34.5kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 9.9 | 9.9 | 0 | 9.9 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3106_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w3106_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3106_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 1/22/2016 | N | No
W3-110 | Sussex | Wantage Solar Farm | NJ | Sussex | In Service | JCPL | 7.5 | 7.5 | 2.85 | 7.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3110_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3110_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 11/15/2013 | N | No
W3-124 | Devils Brook 13kV | Matrix-Stults Road | NJ | Middlesex | In Service | PSEG | 2.85 | 2.85 | 1.08 | 2.85 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3124_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3124_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w3124_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 6/30/2011 | 6/30/2011 | 6/17/2011 | N | No
W3-162 | Baker 345kV | Riverside Generating Stations | KY | Lawrence | In Service | AEP | 993 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w3162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w3162_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w3_162_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 2/8/2010 | 2/8/2010 | 9/9/2011 | N | No
W4-004B_AT11 | Perry 345kV | Perry Nuclear Power Plant | OH | Lake | In Service | ATSI | 1297.8 | 16 | 16 | 16 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4004b_at11_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4004b_at11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_004B_at11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2010 | N/A | N/A | [5 empty] | 4/26/2013 | N | No
W4-005 | Blue Mound-Latham | Radford's Run Wind Farm | IL | Macon | In Service | ComEd | 306 | 306 | 39.8 | 306 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4005_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_005_csa.pdf | Document Posted | N/A | N/A |  | 11/17/2010 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 12/14/2017 | N | No
W4-009 | Raritan River 230kV | Woodbridge Energy Center | NJ | Middlesex | In Service | JCPL | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/w4009_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_009_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_009_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 12/4/2015 | N | No
W4-010 | White Oak |  | MD | Montgomery | In Service | PEPCO | 53 | 29.1 | 0 | 29.1 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_010_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 5/8/2014 | N | No
W4-015 | Mickleton 230kV 1 | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 860 | 210 | 136 | 210 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 1/16/2015 | N | No
W4-025 | Cookstown-Fort Dix 34.5kV | North Run Solar | NJ | Burlington | In Service | JCPL | 7 | 7 | 2.6 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_025_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2010 | N/A | N/A |  |  |  | 5/29/2014 | 5/29/2014 | 2/4/2015 | N | No
W4-046 | Washington-Mobile Chemical 34.5kV | Hengst Solar Farm | NJ | Warren | In Service | JCPL | 10 | 10 | 3.8 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4046_wmpa.pdf |  | Not Required | N/A | N/A | 6/17/2016 | 1/11/2011 | N/A | N/A | 6/29/2016 |  |  | 11/28/2016 | 11/28/2016 | 7/13/2016 | N | No
W4-058 | Lawrence 13kV | Rider University | NJ | Mercer | In Service | PSEG | 0.702 | 0.702 | 0.267 | 0.702 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4058_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 12/16/2011 | N | No
W4-059 | Kuller Road 13kV | Metro Division Headquarters | NJ | Passaic | In Service | PSEG | 0.6 | 0.6 | 0.228 | 0.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4059_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 6/30/2012 | 6/30/2012 | 7/5/2012 | N | No
W4-060 | Midland-Werner 34.5kV | Old Bridge Solar Farm | NJ | Middlesex | In Service | JCPL | 10 | 10 | 3.8 | 8.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4060_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4060_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 3/31/2018 | 3/31/2018 | 8/4/2018 | N | No
W4-064 | N. Newton 12kV | Augusta Solar Farm | NJ | Sussex | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4064_wmpa.pdf |  | Not Required | N/A | N/A | 5/10/2016 | 1/31/2011 | N/A | N/A | 5/13/2016 |  |  | 6/12/2016 | 6/12/2016 | 5/31/2016 | N | No
W4-073 | Phillipsburg 34.5kV | Hamptons at Pohatcong Solar Farm | NJ | Warren | In Service | JCPL | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4073_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A | 12/31/2019 |  |  | 12/31/2019 | 12/31/2019 | 1/10/2020 | N | No
W4-097 | Hawks 12.5kV | Wetteland Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4097_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4097_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 7/31/2016 | 7/31/2016 | 1/6/2016 | N | No
W4-102 | Lappans 34.5kV | Lappans 34.5kV Project | MD | Washington | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/w4_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/w4_102_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 11/29/2012 | N | No
W4-103 | Burlington 26kV | North American Solar | NJ | Burlington | In Service | PSEG | 7 | 7 | 2.66 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/w4103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/w4103_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/w4103_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 8/15/2016 | 8/15/2016 | 3/3/2016 | N | No
X1-012 | Branchville-Sussex 34.5kV | Frankford Solar Farm | NJ | Sussex | In Service | JCPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1012_wmpa.pdf |  | Not Required | N/A | N/A | 3/2/2016 | 2/22/2011 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 3/3/2016 | N | No
X1-032 | Costen 25kV | Somerset Solar Project | MD | Worcester | In Service | DPL | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1032_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/16/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 1/9/2013 | N | No
X1-037 | Howell | Howell Solar Farm | NJ | Middlesex | In Service | JCPL | 17 | 17 | 6.46 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1037_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/28/2011 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 11/20/2014 | N | No
X1-038 | Union Camp 115kV | Franklin Mill Power Facility | VA | City of Franklin | In Service | Dominion | 35 | 35 | 0 | 35 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_038_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 6/6/2012 | N | No
X1-039 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 190 | 22.9 | 22.9 | 22.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 9/6/2012 | 9/6/2012 | 9/6/2012 | N | No
X1-042 | Watervliet | Orchard Hills | MI | Berrien | In Service | AEP | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1042_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 11/30/2012 | 11/30/2012 | 3/4/2013 | N | No
X1-045 | Dresden | Dresden Nuclear Generation Station, Units 2 & 3 | IL | Grundy | In Service | ComEd | 1917 | 3 | 3 | 3 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  |  |  | 12/1/2012 |  | 8/13/2013 | N | No
X1-068 | Red Oak 230kV | Red Oak | NJ | Middlesex | In Service | JCPL | 776 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_068_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/20/2011 | N/A | N/A |  |  |  | 4/19/2011 |  | 12/3/2012 | N | No
X1-070 | Levittown 138kV | Mill Creek | NJ | Burlington | In Service | PSEG | 3.5 | 3.5 | 1.33 | 3.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1070_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/25/2011 | N/A | N/A |  |  |  | 1/9/2012 | 1/9/2012 | 9/15/2011 | N | No
X1-071 | Cinnaminson 138kV | Southern Division Headquarters | NJ | Burlington | In Service | PSEG | 0.93 | 0.93 | 0.35 | 0.93 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1071_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/25/2011 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 10/7/2013 | N | No
X1-072 | Hackensack 4kV | Hackensack Solar Farm | NJ | Bergen | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1072_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/26/2011 | N/A | N/A |  |  |  | 3/31/2013 | 3/31/2013 | 1/11/2013 | N | No
X1-084 | Altavista 115kV | Altavista Power Station | VA | Campbell | In Service | Dominion | 60 | 60 | 60 | 60 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2011 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 5/7/2013 | N | No
X1-085 | Hornerstown-Windsor 34kV | Upper Freehold Solar | NJ | Monmouth | In Service | JCPL | 5 | 5 | 1.9 | 2.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1085_wmpa.pdf |  | Not Required | N/A | N/A | 5/12/2016 | 4/29/2011 | N/A | N/A | 5/13/2016 |  |  | 2/29/2016 | 2/29/2016 | 5/18/2016 | N | No
X1-095 | Bernardsville 12kV | Bernards Township Solar Farm | NJ | Somerset | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x1095_wmpa.pdf |  | Not Required | N/A | N/A | 9/8/2016 | 4/29/2011 | N/A | N/A | 9/8/2016 |  |  | 9/20/2017 | 9/20/2017 | 10/3/2016 | N | No
X1-097 | Red Lion 138kV | Red Lion Energy Center | DE | New Castle | In Service | DPL | 24.9 | 24.9 | 23.3 | 24.9 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_097_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_097_csa.pdf | Document Posted | N/A | N/A | 12/12/2012 | 4/29/2011 | N/A | N/A | 12/12/2012 |  |  | 3/15/2013 | 3/15/2013 | 12/12/2012 | N | No
X1-108 | Martins Creek 230kV | Lower Mount Bethel | PA | Northampton | In Service | PPL | 600 | 33 | 33 | 33 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1108_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1108_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 1/31/2013 | 1/31/2013 | 12/15/2012 | N | No
X1-109 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 850 | 850 | 765 | 850 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x1109_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x1109_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x1_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x1_109_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 2/29/2016 | 2/29/2016 | 3/28/2016 | N | No
X2-006 | Baker 345kV | Riverside Generating Station | KY | Lawrence | In Service | AEP | 999 | 0 | 0 | 0 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_006_csa.pdf | Document Posted | N/A | N/A |  | 5/6/2011 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
X2-012 | Clinton 230kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 850 | 850 | 765 | 850 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2012_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2012_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/x2_012_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_012_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 7/30/2016 | 7/30/2016 | 7/13/2016 | N | No
X2-013 | Thorofare 13kV | Mantua Creek Frequency Regularor | NJ | Gloucester | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_013_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 1/17/2013 | N | No
X2-022 | Brokaw-Lanesville | Hilltopper Wind Farm | IL | Logan | In Service | ComEd | 250 | 187.5 | 0 | 187.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2022_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2022_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_022_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 11/1/2018 | N | No
X2-025 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 416 | 416 | 416 | 416 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2025_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2025_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_025_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/18/2018 | N | No
X2-052 | Dumont-Olive 345kV | St. Joseph Energy Center, LLC | IN | St. Joseph | In Service | AEP | 675 | 675 | 675 | 675 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2052_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2052_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_052_csa.pdf | Document Posted | N/A | N/A | 7/1/2017 | 6/29/2011 | N/A | N/A | 12/28/2017 |  |  | 4/29/2018 | 4/29/2018 | 4/1/2018 | N | No
X2-060 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | City of Covington | In Service | Dominion | 30 | 30 | 0 | 30 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_060_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2011 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 10/15/2013 | N | No
X2-075 | Flemington | Junction Road Solar Farm | NJ | Hunterdon | In Service | JCPL | 6 | 6 | 2.28 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2075_wmpa.pdf |  | Not Required | N/A | N/A | 5/3/2016 | 7/26/2011 | N/A | N/A | 5/18/2016 |  |  | 6/12/2017 | 6/12/2017 | 5/19/2016 | N | No
X2-076 | Carson-Wake 500kV | Brunswick Combined Cycle Power Station | VA | Brunswick | In Service | Dominion | 1525.5 | 1525.5 | 1376 | 1525.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x2_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x2_076_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2011 | N/A | N/A |  |  |  | 5/1/2016 | 5/1/2016 | 3/7/2016 | N | No
X2-083 | Newark 12kV | Brookside Energy Center | DE | New Castle | In Service | DPL | 3 | 3 | 3 | 3 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2083_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x2083_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2083_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 8/15/2012 | 8/15/2012 | 6/21/2012 | N | No
X2-087 | Doremus 13kV | Food Bank Solar | NJ | Union | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2087_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2087_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 8/18/2012 | N | No
X2-088 | Devils Brook 13kV | Black Rock Solar | NJ | Middlesex | In Service | PSEG | 2.356 | 2.356 | 0.895 | 2.356 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2088_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2088_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 3/26/2012 | N | No
X2-089 | Pierson Avenue 13kV | Summit Associates Solar | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0.76 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x2089_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x2089_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 12/31/2011 | N | No
X3-003 | Mehoopany II 115 kV | Mehoopany Plant | PA | Wyoming | In Service | PENELEC | 64 | 20 | 0 | 20 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3003_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_003_csa.pdf | Document Posted | N/A | N/A |  | 8/3/2011 | N/A | N/A |  |  |  | 10/17/2013 | 10/17/2013 | 11/15/2013 | N | No
X3-004 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 710 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3004_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_004_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 8/8/2011 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
X3-005 | Wildwood 12kV | City Solar | IL | Cook | In Service | ComEd | 9 | 9 | 3.4 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3005_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3005_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_005_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/8/2011 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 9/26/2013 | N | No
X3-008 | Todd 69kV | Dorchester County Solar 1 Project | MD | Anne Arundel | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3008_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3008_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3008_wmpa.pdf |  | Not Required | N/A | N/A | 3/15/2021 | 8/12/2011 | N/A | N/A | 3/15/2021 |  |  | 7/31/2021 | 7/31/2021 | 4/8/2021 | N | No
X3-029 | Belvidere | CHP Belvidere Generation Facility | NJ | Warren | In Service | JCPL | 11.15 | 11.15 | 0 | 11.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3029_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_029_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2011 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 12/17/2013 | N | No
X3-052 | Essex 26.4kV | Essex County Correctional Facility | NJ | Essex | In Service | PSEG | 6.2 | 3 | 0 | 3 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x3_052_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2011 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 9/10/2014 | N | No
X3-066 | Church Hill 69kV | Church Hill Solar Farm | MD | Queen Anne's | In Service | DPL | 6 | 6 | 2.28 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3066_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x3066_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3066_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/13/2011 | N/A | N/A |  |  |  | 9/1/2015 | 9/1/2015 | 5/19/2016 | N | No
X3-070 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 72 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3070_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x3_070_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 12/12/2013 | N | No
X3-075 | Runnemede 13kV | Owens Corning Solar | NJ | Camden | In Service | PSEG | 3 | 3 | 0 | 3 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x3075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x3075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x3075_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  |  |  | 2/16/2017 | 2/16/2017 | 5/11/2017 | N | No
X4-005 | Raritan River 230kV |  | NJ | Middlesex | In Service | JCPL | 785 | 60 | 0 | 60 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4005_fea.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4005_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_005_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2011 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 12/4/2015 | N | No
X4-006 | Kelson Ridge 230kV | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 785 | 60 | 0 | 35 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_006_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2011 | N/A | N/A |  |  |  | 11/1/2016 | 11/1/2016 | 1/28/2017 | N | No
X4-015 | Cookstown-Fort Dix 34kV | Jacobstown III Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4015_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4015_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/28/2011 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 9/28/2015 | N | No
X4-019 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 643 | 227 | 227 | 227 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4019_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4019_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_019_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/18/2018 | N | No
X4-027 | Linwood 230kV | Phillips Island CT1, CT2,CT3 & ST4 | PA | Delaware | In Service | PECO | 852 | 12 | 35 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/8/2011 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 6/1/2018 | N | No
X4-031 | Bennett-Farmingdale 34kV | Skudera Solar Farm | NJ | Monmouth | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4031_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4031_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/30/2011 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 6/17/2015 | Y | No
X4-035 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | In Service | PEPCO | 735.5 | 735.5 | 735.5 | 735.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4035_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4035_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_035_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2012 | N/A | N/A |  |  |  | 6/15/2018 | 6/15/2018 | 5/21/2018 | N | No
X4-039 | Pleasant View-Brambleton 230kV | Stonewall Energy Park | VA | Loudoun | In Service | Dominion | 800 | 800 | 750 | 800 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4039_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4039_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_039_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2012 | N/A | N/A |  |  |  | 10/1/2017 | 10/1/2017 | 4/28/2017 | N | No
X4-044 | Aldene 230kV | EF Kenilworth LLC | NJ | Union | In Service | PSEG | 17.9 | 17.9 | 9.9 | 17.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_044_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 5/1/2015 | 5/1/2015 | 6/11/2015 | N | No
X4-046 | E Street (Sub 18) 13kV |  | DC | N/A | In Service | PEPCO | 19.5 | 19.5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/x4046_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 9/1/2015 | 9/1/2015 | 2/4/2019 | N | No
X4-048 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1000 | 1000 | 1000 | 1000 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/x4048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/x4048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/x4048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/x4_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/x4_048_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 3/8/2018 | N | No
Y1-012 | Geneva | Geneva Renewable Energy Facility | OH | Ashtabula | In Service | ATSI | 6.48 | 6.48 | 6.48 | 6.48 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1012_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/23/2012 | N/A | N/A |  |  |  | 8/1/2013 | 8/1/2013 | 7/22/2013 | N | No
Y1-020 | Sussex 34kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 9.9 | 0 | 3.72 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1020_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1020_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/28/2012 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 1/22/2016 | N | No
Y1-026 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 0 | 160 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1026_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1026_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/29/2012 | N/A | N/A |  |  |  | 3/1/2012 |  | 6/1/2018 | N | No
Y1-033 | Penn Mar-Rock Wood 115kV |  | PA | Somerset | In Service | PENELEC | 38.3 | 38.3 | 4.98 | 38.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_033_csa.pdf | Document Posted | N/A | N/A |  | 2/29/2012 | N/A | N/A |  |  |  | 3/27/2017 | 3/27/2017 | 12/14/2016 | N | No
Y1-044 | Belmont 138kV | Willow Island Hydro Generation Project | WV | Pleasants | In Service | APS | 43.2 | 6.8 | 6.8 | 6.8 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2012 | N/A | N/A |  |  |  | 7/31/2015 | 7/31/2015 | 11/15/2015 | N | No
Y1-047 | North Meshoppen 34.5kV | Roundtop Energy Project | PA | Wyoming | In Service | PENELEC | 15.4 | 15.4 | 15.4 | 15.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1047_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1047_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_047_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2012 | N/A | N/A |  |  |  | 4/1/2015 | 4/1/2015 | 10/15/2015 | N | No
Y1-049 | Wurno 34.5kV | New River Resource Authority Waste Management Facility IRD LEG-E | VA | Pulaski | In Service | AEP | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1049_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_049_csa.pdf | Document Posted | N/A | N/A |  | 4/6/2012 | N/A | N/A |  |  |  | 3/31/2013 | 3/31/2013 | 12/1/2014 | N | No
Y1-054 | Rochelle 138kV | Rochelle Plant | OH | Hamilton | In Service | DEOK | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/16/2012 | N/A | N/A |  |  |  | 5/1/2013 |  | 5/30/2013 | N | No
Y1-065 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 834.1 | 834.1 | 805 | 834.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1065_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1065_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_065_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 9/21/2017 | 9/21/2017 | 7/26/2017 | N | No
Y1-066 | Four Rivers 115kV | Four Rivers NUG CC-1 | VA | Hanover | In Service | Dominion | 182 | 0 | 13.3 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1066_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1066_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_066_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 9/1/2013 | N | No
Y1-068 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | Unknown | In Service | Dominion | 50 | 20 | 0 | 20 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_068_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 10/15/2013 | N | No
Y1-069 | Bay Shore-Fostoria Central 345kV & Bayshore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 799 | 799 | 799 | 799 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_069_csa.pdf | Document Posted | N/A | N/A | 3/15/2016 | 4/27/2012 | N/A | N/A | 3/9/2017 |  |  | 5/15/2017 | 5/15/2017 | 6/23/2017 | N | No
Y1-072 | Glen Gardner 12kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 2 | 0 | 0.76 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1072_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 12/23/2011 |  | 5/30/2013 | N | No
Y1-075 | Medford 13kV | Reeve's Station South | NJ | Burlington | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1075_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 12/19/2013 | N | No
Y1-079 | Wye Mills 69kV | Wye Mills Solar Site | MD | Talbot | In Service | DPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1079_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1079_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 7/29/2016 | 7/29/2016 | 8/24/2016 | N | No
Y1-080 | Dorchester 12kV | Constellation Solar Maryland II, LLC Solar Facility | MD | Dorchester | In Service | DPL | 3.38 | 3.38 | 1.28 | 3.38 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y1080_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 4/30/2015 | 4/30/2015 | 4/30/2015 | N | No
Y1-082 | Longwood-Wye Mills 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y1082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y1082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/y1_082_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 5/2/2016 | S | No
Y1-086 | Morgans Corner | Morgan's Corner Solar | NC | Pasquotank | In Service | Dominion | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y1086_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y1086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y1_086_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 1/30/2016 | 1/30/2016 | 12/26/2015 | N | No
Y2-018 | Pequest River 34.5kV | Warren County Landfill | NJ | Warren | In Service | JCPL | 3.8 | 3.8 | 2.3 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2012 | N/A | N/A |  |  |  | 5/31/2016 | 5/31/2016 | 5/12/2014 | N | No
Y2-019 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 755 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_019_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 6/21/2012 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
Y2-042 | Oxbow 34.5 kV | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 18.3 | 18.3 | 18.3 | 18.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2042_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/23/2012 | N/A | N/A | 10/31/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/16/2019 | N | No
Y2-045 | Baker 345kV | Riverside Generating Station | KY | Lawrence | In Service | AEP | 999 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/2/2012 | N/A | N/A |  |  |  | 7/8/2015 | 7/8/2015 | 1/8/2016 | N | No
Y2-050 | Tidd–Canton Central | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 742 | 742 | 672 | 742 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2050_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_050_csa.pdf | Document Posted | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 11/1/2017 | 11/1/2017 | 9/25/2017 | N | No
Y2-051 | Brick-Lane Mill 34.5kV | French's Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2051_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2051_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/22/2014 | N | Yes
Y2-054 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 354 | 13.7 | 13.7 | 13.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/10/2014 | N | No
Y2-060 | North Meshoppen 34.5kv II | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 18.9 | 3.5 | 3.5 | 3.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_060_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2012 | N/A | N/A |  |  |  | 4/1/2015 | 4/1/2015 | 10/15/2015 | N | No
Y2-064 | Printz | Liberty Electric | PA | Delaware | In Service | PECO | 606.5 | 65.5 | 19 | 65.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_064_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/24/2012 | N/A | N/A |  |  |  | 9/30/2014 | 9/30/2014 | 10/5/2015 | N | No
Y2-067 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 626 | 12 | 12 | 12 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2012 | N/A | N/A |  |  |  | 11/1/2012 |  | 3/28/2014 | N | No
Y2-074 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 401 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2074_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2074_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_074_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/19/2012 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/1/2013 | N | No
Y2-076 | Clover 230kV | Clover Power Station Unit 1 | VA | Halifax | In Service | Dominion | 445 | 4 | 13.7 | 4 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_076_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/22/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 6/1/2014 | N | No
Y2-077 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 401 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_077_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/23/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 12/20/2017 | N | No
Y2-078 | Lakewood #1 230kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2078_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_078_csa.pdf | Document Posted | N/A | N/A |  | 10/25/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 6/1/2015 | N | No
Y2-079 | Lakewood #2 230kV | Ocean Peaking Power | NJ | Ocean | In Service | JCPL | 395.6 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_079_csa.pdf | Document Posted | N/A | N/A |  | 10/25/2012 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 6/1/2015 | N | No
Y2-081 | Deptford 13kV | Deptford (Kinsley Solar)13kV | NJ | Gloucester | In Service | PSEG | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y2081_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2012 | N/A | N/A |  |  |  | 11/1/2014 | 11/1/2014 | 1/14/2015 | N | Yes
Y2-089 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1370 | 370 | 370 | 370 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y2_089_csa.pdf | Document Posted | N/A | N/A | 9/30/2017 | 10/31/2012 | N/A | N/A | 3/1/2018 |  |  | 4/1/2019 | 4/1/2019 | 10/2/2018 | N | No
Y2-100 | Otter Point 34.5kV | Eastern Landfill Gas | MD | Baltimore County | In Service | BGE | 4 | 4 | 4 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_100_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  |  |  | 4/30/2013 | 4/30/2013 | 11/18/2016 | N | No
Y2-105 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 253 | 63 | 50 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2105_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y2105_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_105_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 3/25/2015 | N | No
Y2-109 | Bayview 25kV | Bayview | VA | Northampton | In Service | ODEC | 12.5 | 0.5 | 0.5 | 0.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 7/19/2013 | 7/19/2013 | 7/19/2013 | N | No
Y2-113 | Morris 138kV | Morris Cogen | IL | Grundy | In Service | ComEd | 120 | 12.6 | 12.6 | 12.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y2113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y2_113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 10/31/2012 |  | 3/14/2014 | N | No
Y3-012 | Huron 69kV | Marina Thermal Facility | NJ | Atlantic | In Service | AEC | 15.5 | 7.5 | 0 | 7.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3012_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_012_csa.pdf | Document Posted | N/A | N/A |  | 12/21/2012 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 1/31/2014 | N | Yes
Y3-013 | Zion Energy Center | Zion Energy Center | IL | Lake | In Service | ComEd | 585 | 0 | 90 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_013_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/27/2012 | N/A | N/A |  |  |  | 9/1/2021 | 9/1/2021 | 1/12/2021 | N | No
Y3-023 | Country Side 12kV | Wabash Valley Power Association, Inc. | IN | Elkhart | In Service | AEP | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3023_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3023_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/18/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/1/2015 | N | Yes
Y3-024 | Bluff Point 12kV | Wabash Valley Power Association, Inc. | IN | Jay | In Service | AEP | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3024_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3024_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3024_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/18/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/1/2015 | N | Yes
Y3-025 | Bridge-South Park 12kV | Charleston Clean Energy | WV | Kanawha | In Service | AEP | 3.18 | 3.18 | 3.18 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_025_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/22/2013 | N/A | N/A |  |  |  | 5/29/2015 | 5/29/2015 | 5/29/2019 | N | No
Y3-026 | Burlington 26kV | Burlington (L&D Solar) 26kV | NJ | Burlington | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_026_csa.pdf | Document Posted | N/A | N/A |  | 1/25/2013 | N/A | N/A |  |  |  | 9/24/2015 | 9/24/2015 | 1/26/2016 | N | Yes
Y3-034 | Eldred-Pine Grove 690kV | Stonegate Renewable Energy | PA | Schuylkill | In Service | PPL | 10.5 | 0 | 1.8 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_034_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/20/2013 | N/A | N/A |  |  |  | 12/31/2013 |  | 12/26/2013 | N | No
Y3-036 | Gavin Unit 2 | Gavin Unit #2 | OH | Gallia | In Service | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_036_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A | 10/1/2020 |  |  | 12/31/2014 | 12/31/2014 | 1/14/2015 | N | No
Y3-037 | Amos Unit 3 | John Amos Generating Plant Unit No. 3 | WV | Putnam | In Service | AEP | 1336 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 4/1/2015 | N | No
Y3-038 | Rockport Unit 1 | Rockport Unit #1 | IN | Spencer | In Service | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 6/30/2017 | N | No
Y3-039 | Clinch River Unit 1 | Clinch River Power Plant | VA | Russell | In Service | AEP | 250 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 4/15/2016 | 4/15/2016 | 5/27/2016 | N | No
Y3-040 | Clinch River Unit 2 | Clinch River Power Plant | VA | Russell | In Service | AEP | 250 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/6/2016 | 6/6/2016 | 5/23/2016 | N | No
Y3-043 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 760 | 760 | 760 | 760 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_043_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/11/2018 | N | No
Y3-044 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 206 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-045 | Bergen | Bergen Genertating Station | NJ | Bergen | In Service | PSEG | 1235 | 0 | 5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3045_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3045_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3045_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/29/2015 | N | No
Y3-048 | Burlington | Burlington Generating Station | NJ | Burlington | In Service | PSEG | 207 | 2 | 3 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3048_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3048_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-050 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 497 | 24 | 21 | 24 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3050_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-051 | Linden | Linden Generating Station | NJ | Union | In Service | PSEG | 1626 | 47 | 4 | 47 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3051_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3051_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 8/29/2016 | N | No
Y3-052 | Bergen |  | NJ | Bergen | In Service | PSEG | 1285 | 50 | 10 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3052_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3052_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_052_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/29/2015 | N | No
Y3-053 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 537 | 40 | 13 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3053_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3053_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_053_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/21/2015 | N | No
Y3-056 | Pioneer Crossing 69kV | Pioneer Crossing | PA | Berks | In Service | ME | 8 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/12/2013 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 9/1/2013 | N | No
Y3-058 | Rockawalkin 69kV | Rockfish Solar Power Plant | MD | Wicomico | In Service | DPL | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3058_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/13/2013 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 2/22/2016 | N | No
Y3-064 | Pierce-Beckjord 138kV |  | OH | Clermont | In Service | DEOK | 160 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 155 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y3064_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y3064_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/y3_064_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2013 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/20/2019 | S | No
Y3-074 | Ashton 480V |  | MD | Montgomery | In Service | BGE | 0.372 | 0.372 | 0 | 0.37 | Energy | Generation Interconnection | Hydro |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/y3074_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/12/2013 | N/A | N/A |  |  |  | 7/1/2014 | 7/1/2014 | 10/1/2014 | Y | No
Y3-082 | Easton-Trappe Tap 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/y3082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/y3082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/y3082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/y3_082_csa.pdf | Document Posted | N/A | N/A |  | 4/19/2013 | N/A | N/A |  |  |  | 6/1/2014 |  | 1/29/2016 | S | No
Y3-087 | Beaverbrook 13kV | Beaverbrook (Kinsley Solar) | NJ | Gloucester | In Service | PSEG | 3.8 | 3.8 | 1.44 | 3.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3087_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_087_csa.pdf | Document Posted | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 6/30/2015 |  | 1/14/2015 | N | No
Y3-088 | Kendall I | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1158.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_088_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-089 | Kendall II | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1178.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-090 | Kendall III | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1198.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_090_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-091 | Kendall IV | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1218.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3091_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3091_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3091_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_091_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-099 | Beckjord 2 MW-1 | Beckjord Battery #1 | OH | Clermont | In Service | DEOK | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_099_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2013 | N/A | N/A |  |  |  | 5/1/2015 | 5/1/2015 | 1/21/2015 | N | No
Y3-102 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 1000 | 166 | 135 | 166 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_102_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 8/21/2017 | 8/21/2017 | 7/27/2017 | N | No
Y3-103 | Valley-Raccoon 138kV | Pennsylvania Chemicals Generating Facility | PA | Beaver | In Service | DL | 205 | 205 | 97 | 205 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3103_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3103_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/y3_103_csa.pdf | Document Posted | N/A | N/A | 11/12/2019 | 4/30/2013 | N/A | N/A | 6/1/2021 |  |  | 11/30/2021 | 11/30/2021 | 6/22/2021 | N | No
Y3-106 | Belleville-Rutland 138kV | Belleville Hydroelectric Plant | WV | Wood | In Service | AEP | 49 | 7 | 7 | 3 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3106_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_106_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 12/31/2014 | N | No
Y3-107 | Bergen 230kV |  | NJ | Bergen | In Service | PSEG | 1220 | 35 | 45 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/y3107_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/y3107_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/y3107_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/y3_107_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 4/1/2015 |  | 10/29/2015 | N | No
Z1-015 | Springdale 3, 4, 5 | Springdale | PA | Allegheny | In Service | APS | 590 | 0 | 26 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/21/2015 | N | No
Z1-036 | WinFall-Chowan 230kV | Timbermill Wind Farm | NC | Perquimans | In Service | Dominion | 189 | 189 | 24.5 | 189 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1036_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1036_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_036_csa.pdf | Document Posted | N/A | N/A | 11/5/2024 | 7/23/2013 | N/A | N/A | 11/8/2024 |  |  | 3/31/2025 | 3/31/2025 | 12/13/2024 | N | No
Z1-041 | Rock Springs 500kV | Rock Springs Units #1 & #2 | MD | Cecil | In Service | Essential Power | 327 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_041_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/14/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 5/28/2015 | N | No
Z1-050 | Kittatinny 230kV | Yards Creek Pumped Storage Hydro-electric Generating Station | NJ | Warren | In Service | JCPL | 420 | 20 | 20 | 20 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 3/1/2014 |  | 5/1/2014 | N | No
Z1-051 | D.C. Cook Unit 2 | D.C. Cook Generating Plant Unit No. 2 | MI | Berrien | In Service | AEP | 1192 | 102 | 83 | 102 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1051_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 11/18/2016 | 11/18/2016 | 1/14/2017 | N | No
Z1-052 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | In Service | PEPCO | 800 | 64.5 | 44.5 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_052_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 8/15/2018 | 8/15/2018 | 7/23/2018 | N | No
Z1-055 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 714 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1055_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_055_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/11/2013 | N/A | N/A |  |  |  | 6/1/2016 |  | 1/31/2017 | N | No
Z1-056 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 720 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/11/2013 | N/A | N/A |  |  |  | 6/1/2016 |  | 1/31/2017 | N | No
Z1-057 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 252 | 0 | 15.9 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_057_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 10/1/2013 |  | 5/6/2014 | N | No
Z1-058 | Linden 1 - 138kV | Linden Generating Station | NJ | Union | In Service | PSEG | 491 | 23 | 36 | 23 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1058_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1058_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 8/29/2016 | N | No
Z1-059 | Linden 2 - 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 800 | 23 | 18 | 23 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_059_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/29/2016 | N | No
Z1-065 | Wiley 34.5kV | Willey Energy Storage Project | OH | Hamilton | In Service | DEOK | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_065_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2013 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/1/2015 | N | Yes
Z1-066 | Arnold 115kV | Green Mountain Battery | PA | Somerset | In Service | PENELEC | 10.4 | 10.4 | 0 | 8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1066_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2013 | N/A | N/A |  |  |  | 3/1/2016 | 3/1/2016 | 12/30/2015 | N | No
Z1-068 | Birdneck 34.5kV |  | VA | City of Virginia Beach | In Service | Dominion | 12 | 12 | 1.5 | 12 | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1068_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1068_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/10/2013 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 | 9/26/2020 | N | Yes
Z1-069 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 70 | 70 | 13.3 | 70 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_069_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2013 | N/A | N/A | 8/22/2019 |  |  | 10/31/2019 | 10/31/2019 | 11/20/2019 | N | No
Z1-072 | Crescent Ridge | Crescent Ridge Wind Farm | IL | Bureau | In Service | ComEd | 54.45 | 0 | 9.7 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 6/1/2016 | N | No
Z1-073 | Mendota Hills |  | IL | Lee | In Service | ComEd | 50.4 | 0 | 5.2 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1073_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1073_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_073_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 8/5/2015 | N | No
Z1-079 | Todhunter-Foster 345kV | Middletown Energy Center | OH | Butler | In Service | DEOK | 513 | 513 | 513 | 513 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_079_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 6/1/2018 |  | 2/6/2018 | N | No
Z1-080 | Clinton County 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1080_fea.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_080_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 8/29/2016 | N | Yes
Z1-086 | Heritage-Carson | Greensville Generating Facility | VA | Greensville | In Service | Dominion | 1681 | 1681 | 1630 | 1681 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1086_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_086_csa.pdf | Document Posted | N/A | N/A | 1/21/2018 | 10/30/2013 | N/A | N/A | 7/20/2018 |  |  | 6/1/2019 | 6/1/2019 | 12/8/2018 | N | No
Z1-087 | Glade 230kV | Seneca Pumped Storage Generating Station | PA | Warren | In Service | PENELEC | 485 | 17 | 17 | 13 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_087_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 4/21/2017 | N | No
Z1-088 | Allegheny Dam 5 | Allegheny River Lock & Dam # 5 | PA | Armstrong | In Service | APS | 8 | 0 | 5 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1088_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_088_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 3/25/2015 | N | No
Z1-089 | Allegheny Dam 6 138kV | Allegheny River Lock & Dam #6 | PA | Armstrong | In Service | APS | 9 | 0 | 5 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1089_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 3/25/2015 | N | No
Z1-090 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 1024 | 381 | 381 | 381 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_090_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/24/2018 | N | No
Z1-082 | Lawnside 13kV | Lawnside Battery | NJ | Camden | In Service | PSEG | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1082_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 8/1/2014 | 8/1/2014 | 1/13/2015 | Y | Yes
Z1-092 | Milan 34kV | Milan Energy | PA | Lackawanna | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1092_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1092_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_092_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A | 2/20/2017 |  |  | 2/2/2017 | 2/2/2017 | 2/20/2017 | N | No
Z1-096 | Trenton 26kV | Parkland Solar | NJ | Burlington | In Service | PSEG | 7.84 | 7.84 | 2.98 | 7.84 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1096_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1096_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/15/2014 |  | 1/14/2015 | N | Yes
Z1-097 | Adkins 345kV | Darby Generating Station Unites, 1,2,3,4,5,6 | OH | Madison | In Service | AEP | 564 | 0 | 30 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_097_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 12/15/2014 | N | No
Z1-099 | North Street 69kV | City of Dover Generating Facilities | DE | Kent | In Service | DPL | 182 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1099_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 9/22/2016 | N | No
Z1-100 | Oak Hall | Oak Hal lProject A | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_100_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
Z1-101 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1101_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_101_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
Z1-102 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1102_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1102_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_102_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
Z1-103 | Oak Hall |  | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z1_103_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
Z1-108 | McHenry 34kV | McHenry Energy Storage | IL | McHenry | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1108_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1108_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/17/2015 | N | Yes
Z1-110 | Grover 34kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z1110_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/5/2016 | 10/31/2013 | N/A | N/A | 5/5/2016 |  |  | 12/31/2016 | 12/31/2016 | 6/7/2016 | N | No
Z1-113 | West Winchester 13kV | HP Hood Generation Facility | VA | Rockingham | In Service | APS | 12 | 12 | 5 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z1113_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 3/30/2015 | 3/30/2015 | 5/11/2015 | N | Yes
Z1-127 | University Park |  | IL | Will | In Service | ComEd | 320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z1_127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 2/10/2014 | N | No
Z2-002 | Linden 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 1049 | 61 | 54 | 61 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2002_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2002_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2002_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_002_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 5/16/2018 | N | No
Z2-011 | Canton 34.5kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2011_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2011_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2011_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_011_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_011_csa.pdf | Document Posted | N/A | N/A | 2/20/2017 | 12/30/2013 | N/A | N/A | 2/27/2017 |  |  | 6/30/2017 | 6/30/2017 | 2/27/2017 | N | No
Z2-012 | Weirwood-Eastville 69kV | Hecate Energy Cherrydale | VA | Northampton | In Service | ODEC | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2012_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_012_csa.pdf | Document Posted | N/A | N/A |  | 12/31/2013 | N/A | N/A |  |  |  | 4/1/2017 | 4/1/2017 | 9/7/2017 | N | No
Z2-013 | Frostburg 138kV | Twin Ridges Wind Farm | PA | Somerset | In Service | APS | 139.4 | 0 | 4.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_013_csa.pdf | Document Posted | N/A | N/A |  | 1/9/2014 | N/A | N/A |  |  |  | 12/31/2014 |  | 12/15/2014 | N | No
Z2-014 | St. Benedict-Patton | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 30.6 | 0 | 1.35 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/9/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 2/13/2015 | N | No
Z2-017 | Bristers Ox 500kV |  | VA | Unknown | In Service | Dominion | 237 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 733 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/z2017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/z2017_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/z2_017_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 3/25/2015 | S | No
Z2-027 | Pasquotank 34.5kV | Elizabeth City Solar Park | NC | Pasquotank | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2027_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_027_csa.pdf | Document Posted | N/A | N/A |  | 2/20/2014 | N/A | N/A |  |  |  | 2/15/2015 | 2/15/2015 | 12/31/2014 | N | No
Z2-028 | Highland-Sammis 345kV & Highland-Mansfield 345kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 800 | 800 | 800 | 800 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2028_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2028_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_028_csa.pdf | Document Posted | N/A | N/A | 9/12/2017 | 2/21/2014 | N/A | N/A | 12/22/2017 |  |  | 12/28/2018 | 12/28/2018 | 8/15/2018 | N | No
Z2-030 | Double Toll Gate 34.5kV | Double Tollgate Solar Project | VA | Clarke | In Service | APS | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2030_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/26/2014 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 7/12/2017 | N | No
Z2-039 | PF Hydro | Warren Hydro Station; Newport Hydro Station; Luray Hydro Station; Shenandoah Hydro Station | VA | Warren | In Service | APS | 4.61 | 0 | 2.82 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2039_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2039_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/27/2014 | N/A | N/A |  |  |  | 5/31/2015 | 5/31/2015 | 5/13/2015 | N | No
Z2-040 | PF Hydro | Dam 4 Hydro Generation Facility; Dam 5 Hydro Generation Facility; Millville Hydroelectric Facility | WV | Jefferson | In Service | APS | 5.75 | 0 | 3.5 | 5.75 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/27/2014 | N/A | N/A |  |  |  | 3/31/2014 |  | 4/17/2015 | N | No
Z2-043 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2043_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2043_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_043_csa.pdf | Document Posted | N/A | N/A |  | 3/5/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | Yes
Z2-044 | Whitakers 34.5kV | Whitakers Solar Park | NC | Nash | In Service | Dominion | 12 | 12 | 8.4 | 12 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_044_csa.pdf | Document Posted | N/A | N/A |  | 3/5/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | Yes
Z2-046 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1050 | 1050 | 900 | 1050 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2046_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2046_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2046_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_046_csa.pdf | Document Posted | N/A | N/A |  | 3/14/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 2/20/2018 | N | No
Z2-056 | Crossmans-Werner 34.5kV |  | NJ | Middlesex | In Service | JCPL | 20 | 0.5 | 0 | 0.5 | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 8/4/2016 | Y | No
Z2-062 | Gloucester 26kV | Camden County Energy Recovery Associates | NJ | Camden | In Service | PSEG | 24.5 | 0 | 3 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_062_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/2/2014 | N/A | N/A |  |  |  | 5/1/2015 |  | 11/19/2014 | N | No
Z2-076 | Worcester South 25kV | Worcester South | MD | Worcester | In Service | DPL | 2.64 | 2.64 | 1.76 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2076_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2076_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/22/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 5/29/2019 | N | Yes
Z2-077 | Worcester North 25kV | Worcester North | MD | Worcester | In Service | DPL | 5 | 5 | 3.33 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2077_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2077_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2077_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/22/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 3/15/2019 | N | No
Z2-081 | Streator 34.5kV | Livingston Landfill Gas to Energy Facility | IL | Livingston | In Service | ComEd | 13.3 | 13.3 | 13.3 | 12 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2081_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_081_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2014 | N/A | N/A |  |  |  | 12/1/2014 |  | 4/4/2017 | N | No
Z2-083 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 1104 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2083_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_083_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
Z2-085 | Mahoning Valley Hydro 25kV | Mahoning Creek Hydroelectric Plant | PA | Clarion | In Service | APS | 7.5 | 1.5 | 1.5 | 7.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2085_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_085_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2014 | N/A | N/A |  |  |  | 11/1/2014 | 11/1/2014 | 10/10/2014 | N | No
Z2-087 | Pontiac MidPoint-Brokaw 345kV | Bright Stalk Wind Farm | IL | Livingston | In Service | ComEd | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_087_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2014 | N/A | N/A | 12/16/2019 |  |  | 12/30/2019 | 12/30/2019 | 12/16/2019 | N | No
Z2-088 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 80 | 80 | 30.4 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_088_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/21/2015 | N | No
Z2-089 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 568 | 568 | 541 | 568 | Capacity | Generation Interconnection | Natural Gas; Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/z2089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2_089_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 5/2/2018 | N | No
Z2-102 | Argonne-New Lisbon 34.5kV | Dix Solar Farm | NJ | Burlington | In Service | JCPL | 13 | 13 | 4.94 | 13 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2102_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2102_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 8/24/2017 | 8/24/2017 | 7/13/2017 | N | No
Z2-103 | North Meshoppen 34.5kV III | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 19.9 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2103_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 1/28/2016 | N | No
Z2-104 | Oxbow 34.5 kV II | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 19.9 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2104_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2104_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2104_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A | 10/30/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/16/2019 | N | No
Z2-108 | Meyersdale North 115kV | Meyersdale Wind Farm & Battery Energy Storage System | PA | Somerset | In Service | PENELEC | 48 | 18 | 0 | 18 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/17/2015 | N | No
Z2-112 | Waterford 345kV |  | OH | Washington | In Service | AEP | 1007 | 97 | 64.5 | 97 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/z2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 6/15/2015 | N | No
Z2-113 | Watervliet 12.47kV | Watervliet Solar Facility | MI | Berrien | In Service | AEP | 4.6 | 4.6 | 2.3 | 4.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2113_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2113_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/15/2016 | 12/15/2016 | 11/8/2016 | N | Yes
Z2-114 | Olive 12.47kV | Olive Solar Facility | IN | St. Joseph | In Service | AEP | 5 | 5 | 2.5 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2114_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2114_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/15/2016 | 12/15/2016 | 8/26/2016 | N | Yes
Z2-115 | Deer Creek 12.47kV | Deer Creek Solar Facility | IN | Grant | In Service | AEP | 2.5 | 2.5 | 1.25 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2115_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 3/1/2016 | 3/1/2016 | 1/6/2016 | N | Yes
Z2-116 | Twin Branch 12.47kV | Twin Branch Solar Facility | IN | St. Joseph | In Service | AEP | 2.6 | 2.6 | 1.3 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/z2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/z2116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/z2116_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/z2116_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 7/31/2016 | 7/31/2016 | 8/18/2016 | N | No
AA1-006 | Erie County Landfill | Erie County Landfill | OH | Erie | In Service | ATSI | 2.3 | 0.8 | 0.8 | 0.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa1006_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/2/2014 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 12/31/2015 | N | No
AA1-013 | Hanging Rock 765kV | Cornu | OH | Lawrence | In Service | AEP | 1250 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1013_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_013_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
AA1-014 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 625 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
AA1-015 | Fayette II | Fayette Energy Facility | PA | Fayette | In Service | APS | 661 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 1/1/2016 | 1/1/2016 | 12/14/2015 | N | No
AA1-018 | Powerton-Goodings Grove | Otter Creek Wind Farm | IL | Livingston | In Service | ComEd | 150 | 150 | 19.5 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1018_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1018_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_018_csa.pdf | Document Posted | N/A | N/A |  | 6/25/2014 | N/A | N/A | 12/20/2019 |  |  | 1/17/2020 | 1/17/2020 | 1/9/2020 | N | No
AA1-025 | Oak Hall A |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_025_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
AA1-026 | Oak Hall B |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_026_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
AA1-027 | Oak Hall C |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_027_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
AA1-028 | Oak Hall D |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1028_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_028_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
AA1-034 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 880 | 120 | 70 | 72.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1034_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_034_csa.pdf | Document Posted | N/A | N/A |  | 7/24/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/11/2018 | N | No
AA1-037 | Piney Hydro 34.5kV | Piney Station (Piney 1-3) | PA | Clarion | In Service | PENELEC | 33.26 | 5.26 | 5.26 | 5.26 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/13/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 6/19/2015 | N | No
AA1-040 | Morris | Morris Cogen | IL | Grundy | In Service | ComEd | 140 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/27/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/28/2016 | N | No
AA1-043 | Ontelaunee 230kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 591.1 | 34.1 | 19.6 | 34.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/aa1_043_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_043_csa.pdf | Document Posted | N/A | N/A |  | 8/27/2014 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 9/30/2017 | N | No
AA1-044 | Shenango-Hoytdale 345kV | Hickory Run Energy Station | PA | Lawrence | In Service | ATSI | 1000 | 1000 | 870 | 1000 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_044_csa.pdf | Document Posted | N/A | N/A | 4/22/2019 | 8/27/2014 | N/A | N/A | 11/15/2019 |  |  | 3/30/2020 | 3/30/2020 | 10/31/2019 | N | No
AA1-050 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 80 | 0 | 25.6 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1050_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1050_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_050_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2014 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/21/2015 | N | No
AA1-056 | Bay Shore-Fostoria 345kV & Bay Shore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 960 | 161 | 46 | 8.8571 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1056_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_056_isa.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/15/2016 | 9/10/2014 | N/A | N/A | 6/22/2017 |  |  | 5/15/2017 | 5/15/2017 | 6/23/2017 | N | No
AA1-060 | Great Adventure 34.5kV | Plumsted Energy Storage Facility | NJ | Monmouth | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_060_csa.pdf | Document Posted | N/A | N/A |  | 9/22/2014 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 12/11/2018 | N | Yes
AA1-063A | Carolina–Seaboard 115kV | Spuds Lane Solar Park | NC | Northhampton | In Service | Dominion | 74.9 | 74.9 | 50.9 | 74.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1063a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1063a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1063a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_063a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_063a_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2014 | N/A | N/A |  |  |  | 8/17/2018 | 8/17/2018 | 11/8/2018 | N | No
AA1-065 | Earleys 230kV | Aulander Holloman Solar Park | NC | Hertford | In Service | Dominion | 80 | 80 | 53.6 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_065_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A | 1/9/2019 |  |  | 12/31/2018 | 12/31/2018 | 1/9/2019 | N | No
AA1-066 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1050 | 0 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_066_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 8/31/2018 | N | No
AA1-067 | Everetts 34.5kV | Williamston Speight Solar | NC | Martin | In Service | Dominion | 15 | 15 | 10.5 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1067_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_067_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 1/24/2017 | N | No
AA1-072 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 23.1 | 3.1 | 2.1 | 3.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1072_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_072_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/13/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | No
AA1-076 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 1050 | 1050 | 1000 | 1050 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_076_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2014 | N/A | N/A | 9/13/2019 |  |  | 3/1/2021 | 3/1/2021 | 9/22/2019 | N | No
AA1-077 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1483 | 113 | 34 | 113 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1077_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1077_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_077_csa.pdf | Document Posted | N/A | N/A |  | 10/23/2014 | N/A | N/A |  |  |  | 4/1/2019 | 4/1/2019 | 1/21/2019 | N | No
AA1-078 | University Park North | University Park North Energy Center | IL | Will | In Service | ComEd | 560 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1078_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/23/2014 | N/A | N/A |  |  |  | 10/14/2015 |  | 6/1/2016 | N | No
AA1-079 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 1342 | 74 | 74 | 74 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_079_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 9/13/2016 | N | No
AA1-082 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 907.5 | 57.5 | 0 | 57.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_082_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  |  |  | 1/29/2016 | 1/29/2016 | 8/25/2016 | N | No
AA1-083 | Four Rivers 230kV | Doswell Facility | VA | Hanover | In Service | Dominion | 746 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1083_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_083_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2014 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/31/2015 | N | No
AA1-084 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 252 | 0 | 10 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2014 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 6/19/2015 | N | No
AA1-095 | Halfway-Marlowe 34.5kV | Pinesburg Solar Project | MD | Washington | In Service | APS | 4.25 | 4.25 | 2.9 | 4.25 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1095_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_095_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_095_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A | 4/24/2020 |  |  | 1/16/2020 | 1/16/2020 | 5/27/2020 | N | Yes
AA1-099 | Clinton Co. 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 10 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_099_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 8/29/2016 | N | No
AA1-109 | Cotoctin-Troutville Junction 34.5kV | Frederick Road Solar | MD | Frederick | In Service | APS | 9 | 9 | 4.5 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_109_csa.pdf | Document Posted | N/A | N/A | 10/13/2017 | 10/31/2014 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 10/23/2017 | N | Yes
AA1-123 | Highland-Sammis 345kV | South Field Energy Power Plant | OH | Columbiana | In Service | ATSI | 1152 | 1152 | 1105 | 1152 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1123_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1123_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_123_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_123_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A | 4/1/2021 |  |  | 7/29/2021 | 7/29/2021 | 6/14/2021 | N | No
AA1-139 | Hickory-Shawboro 230kV | Summit Farms Solar and Ranchland Solar | NC | Currituck | In Service | Dominion | 120 | 120 | 84 | 120 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1139_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_139_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 2/28/2018 | 2/28/2018 | 3/6/2018 | N | No
AA1-145 | Four Rivers 230kV | Doswell SC Units 2 & 3 | VA | Hanover | In Service | Dominion | 340 | 340 | 340 | 340 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1145_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1145_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_145_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 7/1/2018 | 7/1/2018 | 5/30/2018 | N | No
AA1-146 | Nelson | Invenergy Nelson Expansion LLC | IL | Lee | In Service | ComEd | 190 | 190 | 157 | 190 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa1146_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa1146_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa1146_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa1_146_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa1_146_csa.pdf | Document Posted | N/A | N/A | 10/17/2022 | 11/1/2014 | N/A | N/A | 3/17/2023 |  |  | 5/31/2023 | 5/31/2023 | 5/20/2023 | N | No
AA2-008 | Saegers 230 kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 907 | 57 | 0 | 57 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2008_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/aa2_008_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/6/2014 | N/A | N/A |  |  |  | 9/1/2016 | 9/1/2016 | 9/1/2016 | N | No
AA2-030 | Nelson | Invenergy Nelson Expansion LLC | IL | Lee | In Service | ComEd | 380 | 190 | 157 | 190 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2030_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2030_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_030_csa.pdf | Document Posted | N/A | N/A | 10/31/2022 | 12/24/2014 | N/A | N/A | 3/31/2023 |  |  | 5/31/2023 | 5/31/2023 | 5/20/2023 | N | No
AA2-048 | Allenwood-Larrabee 34kV | Lakewood-Farmingdale Road Solar Farm & Storage Facility | NJ | Monmouth | In Service | JCPL | 7 | 7 | 0 | 7 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2048_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2048_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2048_wmpa.pdf |  | Not Required | N/A | N/A | 10/3/2022 | 2/19/2015 | N/A | N/A | 10/30/2022 |  |  | 8/31/2022 | 8/31/2022 | 3/17/2023 | N | No
AA2-052 | Essex 26kV |  | NJ | Essex | In Service | PSEG | 3 | 0 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_052_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 2/20/2015 | N/A | N/A |  |  |  | 2/12/2015 |  | 9/11/2015 | N | No
AA2-053 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 74.9 | 74.9 | 52.4 | 74.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2053_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2053_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2053_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_053_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_053_csa.pdf | Document Posted | N/A | N/A |  | 2/23/2015 | N/A | N/A | 7/10/2019 |  |  | 6/19/2019 | 6/19/2019 | 7/10/2019 | N | No
AA2-054 | Pumphrey 230kV |  | MD | Anne Arundel | In Service | BGE | 155 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 65.7 | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-feas_docs/aa2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/aa2054_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/aa2_054_csa.pdf | Document Posted | N/A | N/A |  | 2/23/2015 | N/A | N/A |  |  |  | 1/1/2016 |  | 6/7/2017 | S | No
AA2-057 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 66 | 66 | 44.7 | 66 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2057_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2057_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_057_csa.pdf | Document Posted | N/A | N/A | 9/1/2019 | 2/26/2015 | N/A | N/A | 11/18/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/26/2019 | N | No
AA2-061 | Branchville-Sussex #2 34.5kV | Roy Road Battery Storage Facility | NJ | Sussex | In Service | JCPL | 14 | 8 | 0 | 8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_061_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2015 | N/A | N/A | 7/17/2023 |  |  | 7/31/2023 | 7/31/2023 | 8/14/2023 | N | No
AA2-066 | Penns Neck 13kV | Princeton Hospital NRG Energy Center | NJ | Mercer | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2066_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 8/16/2017 | Y | No
AA2-058 | Mount Rose 13kV | Hopewell Valley Solar | NJ | Mercer | In Service | PSEG | 1 | 1 | 0.3 | 2.9 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2058_wmpa.pdf |  | Not Required | N/A | N/A | 11/30/2015 | 2/28/2015 | N/A | N/A | 12/15/2015 |  |  | 5/1/2016 | 5/1/2016 | 12/30/2015 | N | No
AA2-060 | Branchville-Sussex #1 34kV | Roy Road Battery Storage Facility | NJ | Sussex | In Service | JCPL | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2060_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_060_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2015 | N/A | N/A | 7/17/2023 |  |  | 7/31/2023 | 7/31/2023 | 8/14/2023 | N | No
AA2-070 | Smith Mountain 138kV | Smith Mountain Hydro | VA | Henry | In Service | AEP | 649 | 34 | 34 | 34 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2070_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_070_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
AA2-072 | Kingsville 13kV | Kingsville Solar | MD | Harford | In Service | BGE | 1.1 | 1.1 | 0 | 1.1 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2072_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/9/2015 | N/A | N/A |  |  |  | 5/1/2016 | 5/1/2016 | 6/14/2016 | Y | No
AA2-076 | Linwood 230kV | Phillips Island CT1, CT2, CT3 & ST4 | PA | Delaware | In Service | PECO | 852 | 0 | 18 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2076_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_076_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2015 | N/A | N/A |  |  |  | 4/27/2021 |  |  | N | No | This project slid to the next queue
AA2-079 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 668 | 28 | 0 | 28 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2079_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_079_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2015 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 7/27/2016 | N | No
AA2-082 | Alpha 34.5kV | Alpha Battery Storage Facility | NJ | Warren | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2082_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_082_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  |  |  | 10/20/2018 | 10/20/2018 | 1/28/2019 | N | No
AA2-088 | Boykins-Handsome 115kV | Newsoms Solar | VA | Southampton | In Service | Dominion | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_088_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  |  |  | 12/1/2017 | 12/1/2017 | 12/15/2017 | N | No
AA2-099 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 568 | 0 | 32 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2099_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2099_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_099_csa.pdf | Document Posted | N/A | N/A |  | 4/21/2015 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 6/5/2018 | N | No
AA2-100 | Brown 34.5kV | Bio Energy Landfill Facility | OH | Brown | In Service | DEOK | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2100_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2100_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2100_wmpa.pdf | Not Required | N/A | N/A |  | 4/22/2015 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 5/10/2017 | N | No
AA2-115 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 450 | 450 | 450 | 450 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2115_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2115_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_115_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_115_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2015 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 2/7/2019 | N | No
AA2-116 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | In Service | AEP | 994 | 994 | 994 | 994 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2116_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2116_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_116_csa.pdf | Document Posted | N/A | N/A | 6/24/2021 | 4/28/2015 | N/A | N/A | 12/27/2021 |  |  | 3/15/2022 | 3/15/2022 | 12/27/2021 | N | No
AA2-123 | Marengo 34kV | Marengo Battery Storage | IL | McHenry | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2123_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/aa2123_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2015 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 | 11/19/2018 | N | No
AA2-127 | Bear Garden 230kV | Bear Garden Facility | VA | Buckingham | In Service | Dominion | 682 | 7 | 32.2 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2127_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 5/1/2016 | N | No
AA2-131 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 354 | 0 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2131_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_131_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 3/30/2018 | 3/30/2018 | 5/25/2018 | N | No
AA2-133 | Wyalusing 34.5kV | Wyalusing 34.5kV | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_133_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 2/21/2019 | N | No
AA2-137 | Hanging Rock 765kV - Power Block 1 | Cornu | OH | Lawrence | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2137_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_137_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2019 |  | 12/2/2016 | N | No
AA2-138 | Hanging Rock 765kV - Power Block 2 | Cornu | OH | Lawrence | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2138_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_138_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2019 | 5/1/2019 | 12/2/2016 | N | No
AA2-139 | Ronco 500kV | Fayette Energy Facility | PA | Fayette | In Service | APS | 706 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2139_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_139_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 10/1/2017 | 10/1/2017 | 4/21/2017 | N | No
AA2-140 | Printz 230kV | Liberty Electric | PA | Delaware | In Service | PECO | 641.5 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2140_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_140_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2016 |  | 6/30/2017 | N | No
AA2-141 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2141_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 8/31/2016 | 8/31/2016 | 12/2/2016 | N | No
AA2-165 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 74.9 | 8.9 | 5.3 | 8.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2165_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2165_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_165_csa.pdf | Document Posted | N/A | N/A | 9/1/2019 | 4/30/2015 | N/A | N/A | 11/18/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/26/2019 | N | No
AA2-171 | Sunbury #1 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 1121 | 97 | 60 | 97 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2171_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2171_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_171_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 3/15/2018 | 3/15/2018 | 6/1/2018 | N | No
AA2-173 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 515 | 515 | 515 | 515 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2173_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2173_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_173_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 3/16/2021 |  |  | 5/9/2021 | 5/9/2021 | 4/1/2021 | N | No
AA2-174 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 79.9 | 5 | 2.4 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_174_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 7/10/2019 |  |  | 4/22/2019 | 4/22/2019 | 7/10/2019 | N | No
AA2-178 | Mackeys 230kV | Ablemarle Beach Solar | NC | Washington | In Service | Dominion | 80 | 80 | 56 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2178_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/aa2178_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_178_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_178_csa.pdf | Document Posted | N/A | N/A | 10/27/2020 | 4/30/2015 | N/A | N/A | 12/23/2020 |  |  | 4/20/2021 | 4/20/2021 | 12/23/2020 | N | No
AA2-184 | Atlantic-Red Bank 34kV | Atlantic-RedBank 34.5kV Solar | NJ | Monmouth | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/aa2184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/aa2184_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/aa2_184_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/aa2_184_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 11/30/2019 |  |  | 12/5/2019 | 12/5/2019 | 12/31/2019 | N | No
AB1-001 | Absecon 12 kV | Oak Street Landfill Solar Project | NJ | Atlantic | In Service | AEC | 2.3 | 2.3 | 0.87 | 2.3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1001_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1001_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1001_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1001_wmpa.pdf | Not Required | N/A | N/A |  | 5/1/2015 | N/A | N/A | 9/22/2020 |  |  | 3/30/2020 | 3/30/2020 | 9/30/2020 | Y | No
AB1-006 | Meadow Lake 345kV | Meadow Lake Wind Farm VI | IN | White | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1006_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1006_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_006_csa.pdf | Document Posted | N/A | N/A |  | 5/22/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/21/2018 | N | No
AB1-014 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | In Service | DEOK | 125 | 125 | 47.5 | 125 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1014_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1014_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_014_csa.pdf | Document Posted | N/A | N/A | 8/19/2020 | 6/8/2015 | N/A | N/A | 11/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/18/2020 | N | No
AB1-015 | Evergreen 138kV | Warren Natural Gas Generation Faciility | OH | Trumbull | In Service | ATSI | 16.5 | 16.5 | 0 | 16.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1015_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_015_csa.pdf | Document Posted | N/A | N/A |  | 6/16/2015 | N/A | N/A | 10/10/2016 |  |  | 10/1/2017 | 10/1/2017 | 10/10/2016 | N | No
AB1-017 | Highland-Sammis 345 kV & Highland-Mansfield 345 kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 940 | 140 | 64 | 140 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_017_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/18/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 8/11/2018 | N | No
AB1-021 | West Caldwell 13kV | West Caldwell Solar | NJ | Essex | In Service | PSEG | 2 | 2 | 0.3 | 0.3 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/29/2015 | N/A | N/A | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 6/1/2018 | N | No
AB1-025 | Lumberton 13kV | Lumberton Solar | NJ | Burlington | In Service | PSEG | 6.8 | 6.8 | 2.6 | 6.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/AB1025_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/21/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 8/22/2016 | N | No
AB1-027 | Old Church 34.5 KV | Mechanicsville Solar | VA | Hanover | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1027_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1027_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_027_csa.pdf | Document Posted | N/A | N/A |  | 7/22/2015 | N/A | N/A | 8/20/2020 |  |  | 12/1/2020 | 12/1/2020 | 9/23/2020 | N | No
AB1-033 | North Wales 34.5kV | Morris Road | PA | Montgomery | In Service | PECO | 6 | 4 | 4.1 | 4 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_033_csa.pdf | Document Posted | N/A | N/A |  | 8/12/2015 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 9/3/2020 | N | No
AB1-058 | Gavin Unit #1 765kV | Gavin #1 | OH | Gallia | In Service | AEP | 1331 | 11 | 11 | 11 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1058_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 12/31/2017 | N | No
AB1-063 | Locust St. 13kV | Cooper Solar | NJ | Camden | In Service | PSEG; PSEG | 0.4 | 0.4 | 0 | 0.2 | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1063_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/1/2015 | N/A | N/A | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 2/15/2017 | N | No
AB1-080 | Dumont-Olive 345kV | St. Joseph's Energy Center, LLC | IN | St. Joseph | In Service | AEP | 715 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1080_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1080_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_080_csa.pdf | Document Posted | N/A | N/A | 7/1/2017 | 9/30/2015 | N/A | N/A | 12/28/2017 |  |  | 4/29/2018 | 4/29/2018 | 4/1/2018 | N | No
AB1-081 | Anaconda-Mayo Dunbar 115kV | Harts Mill Solar | NC | Edgecombe | In Service | Dominion | 80 | 80 | 56 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1081_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1081_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_081_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_081_csa.pdf | Document Posted | N/A | N/A | 11/23/2020 | 9/30/2015 | N/A | N/A | 12/21/2020 |  |  | 12/7/2020 | 12/7/2020 | 12/21/2020 | N | No
AB1-095 | Rona 12kV | Dovetail Biogas Facility | OH | Greene | In Service | ATSI | 0.85 | 0.85 | 0 | 0.85 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1095_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1095_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/6/2015 | N/A | N/A | 9/30/2016 |  |  | 12/31/2016 | 12/31/2016 | 9/30/2016 | Y | No
AB1-096 | Carroll-Mt. Airy 34.5kV | Union Bridge Solar Facility | MD | Carroll | In Service | APS | 8.166 | 8.166 | 3.134 | 8.166 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1096_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1096_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_096_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_096_csa.pdf | Document Posted | N/A | N/A |  | 10/7/2015 | N/A | N/A | 1/28/2022 |  |  | 2/28/2022 | 2/28/2022 | 4/21/2022 | N | No
AB1-106 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 940 | 10 | 40 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1106_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1106_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1106_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_106_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/22/2015 | N/A | N/A |  |  |  | 3/1/2019 | 3/1/2019 | 11/18/2018 | N | No
AB1-112 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 535 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1112_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1112_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_112_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_112_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2015 | N/A | N/A | 3/16/2021 |  |  | 5/9/2021 | 5/9/2021 | 4/1/2021 | N | No
AB1-116 | Egg Harbor Road 12kV |  | NJ | Atlantic | In Service | AEC | 0.787 | 0.787 | 0 | 0.79 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1116_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 2/1/2018 | Y | No
AB1-119 | Tansboro Road 12kV | Tansboro Road | NJ | Camden | In Service | AEC | 0.735 | 0.735 | 0 | 0.735 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1119_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1119_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1119_wmpa.pdf | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  |  |  | 7/1/2017 | 7/1/2017 | 2/1/2018 | Y | No
AB1-127 | St. Thomas-Guilford 34.5kV | St. Thomas Township Solar Facility | PA | Franklin | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1127_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_127_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_127_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2015 | N/A | N/A | 7/24/2020 |  |  | 8/31/2020 | 8/31/2020 | 8/21/2020 | N | No
AB1-128 | St. Thomas-Mercersburg 34.5kV | St. Thomas Township Solar Facility II | PA | Franklin | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1128_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1128_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_128_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_128_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2015 | N/A | N/A | 8/5/2020 |  |  | 8/31/2020 | 8/31/2020 | 9/8/2020 | N | No
AB1-122 | Kendall-Tazewell & Dresden-Mole Creek | Three Rivers Energy Center | IL | Grundy | In Service | ComEd | 1160 | 1160 | 1150 | 1160 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1122_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1122_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_122_csa.pdf | Document Posted | N/A | N/A | 10/12/2022 | 10/30/2015 | N/A | N/A | 12/30/2022 |  |  | 6/20/2023 | 6/20/2023 | 6/16/2023 | N | No
AB1-138 | Navy 34.5kV | Lakehurst Solar Farm | NJ | Ocean | In Service | JCPL | 9.6 | 9.6 | 3.6 | 9.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1138_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_138_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_138_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/24/2020 |  |  | 8/18/2020 | 8/18/2020 | 3/24/2020 | N | No
AB1-139 | Metuchen 26kV | Nixon Lane Solar | NJ | Middlesex | In Service | PSEG | 6.6 | 6.6 | 2.5 | 6.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1139_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 5/26/2017 | N | No
AB1-141 | Church-Wye Mills 138 kV I | Pondtown Solar 1 | MD | Queen Anne's | In Service | DPL | 19.8 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1141_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1141_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_141_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_141_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 9/28/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB1-142 | Church-Wye Mills 138 kV II | Pondtown Solar 1 | MD | Queen Anne's | In Service | DPL | 39.6 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1142_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1142_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_142_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 9/28/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB1-144 | Shawville 230kV | Shawville Generating Station | PA | Clearfield | In Service | PENELEC | 590 | 590 | 590 | 532 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1144_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_144_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_144_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/21/2017 | 12/21/2017 | 10/24/2016 | N | No
AB1-150 | Grassy Falls 138kV | Beech Ridge Wind Farm | WV | Greenbrier | In Service | APS | 50.6 | 50.6 | 6.7 | 50.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1150_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_150_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_150_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/30/2020 |  |  | 4/30/2020 | 4/30/2020 | 3/14/2020 | N | No
AB1-160 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 90 | 20 | 3.8 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1160_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1160_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_160_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 8/22/2019 |  |  | 10/31/2019 | 10/31/2019 | 11/20/2019 | N | No
AB1-163 | Glidden-Van Hiseville 34.5 kV | Legler Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 2.88 | 2.88 | 0 | 2.88 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1163_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1163_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1163_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 10/30/2021 |  |  | 10/30/2021 | 10/30/2021 | 11/6/2021 | N | No
AB1-180 | Pine View 12kV | Seven Islands Environmental Solutions, LLC | WV | Unknown | In Service | AEP | 3.2 | 3.2 | 2.4 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1180_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab1180_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1180_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 3/7/2017 | N | No
AB1-181 | Cunningham 500kV |  | VA | Fluvanna | In Service | Dominion | 1000 | 28 | 37.3 | 28 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1181_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 2/28/2017 | 2/28/2017 | 3/7/2017 | N | No
AB1-173 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 19.8 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1173_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1173_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_173_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2015 | N/A | N/A | 8/26/2022 |  |  | 4/1/2022 | 4/1/2022 | 9/29/2022 | N | No
AB1-173A | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 39.6 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1173a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1173a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1173a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_173a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_173a_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2015 | N/A | N/A | 8/26/2022 |  |  | 4/1/2022 | 4/1/2022 | 9/29/2022 | N | No
AB1-132 | Thelma 230kV | Gaston Green Acres Solar | NC | Northhampton | In Service | Dominion | 120 | 120 | 84 | 120 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab1132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab1132_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab1132_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab1_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab1_132_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 11/2/2015 | N/A | N/A | 12/21/2023 |  |  | 12/25/2023 | 12/25/2023 | 8/22/2024 | N | No
AB2-001 | Ringoes-US Bronze 34kV | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 0 | 3.8 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2015 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 12/31/2016 | N | No
AB2-014 | Lakewood 230kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 0 | 8.1 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2014_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/15/2015 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 11/16/2016 | N | No
AB2-020 | Roseland-Williams 230kV |  | N/A | N/A | In Service | PSEG | 40 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 62 | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab2020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/ab2020_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/ab2_020_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 11/22/2017 | S | No
AB2-021 | Keeney-Rock Springs 500kV |  | MD | Unknown | In Service | BGE | 100 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 705 | N/A |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-impact-studies/ab2021_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-facilities/ab2021_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/merch-csa/ab2_021_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 10/31/2018 | S | No
AB2-022 | Elizabeth City 34.5kV | Elizabeth City Solar | NC | Camden | In Service | Dominion | 20 | 20 | 13 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2022_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2022_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2022_wmpa.pdf | Not Required | N/A | N/A |  | 2/4/2016 | N/A | N/A | 8/1/2021 |  |  | 6/30/2021 | 6/30/2021 | 10/18/2021 | N | No
AB2-024 | Correctional 34.5kV |  | VA | New Kent | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2024_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2024_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2024_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/27/2017 | N | Yes
AB2-025 | Sapony 34.5kV |  | VA | Sussex | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2025_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2025_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2025_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-026 | Powhatan 34.5kV |  | VA | Powhatan | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2026_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2026_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2026_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-029 | Remington 34.5kV |  | VA | Fauquier | In Service | Dominion | 19.8 | 19.8 | 7.6 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2029_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2029_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2029_wmpa.pdf | Not Required | N/A | N/A |  | 2/11/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 10/1/2017 | N | No
AB2-032 | Church-Wye Mills 138 kV | Pondtown Solar 2 | MD | Queen Anne's | In Service | DPL | 20 | 20 | 13.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2032_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2032_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_032_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_032_csa.pdf | Document Posted | N/A | N/A |  | 2/11/2016 | N/A | N/A | 9/23/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB2-031 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 59.6 | 20 | 13.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2031_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2031_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2031_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_031_csa.pdf | Document Posted | N/A | N/A |  | 2/13/2016 | N/A | N/A | 8/26/2022 |  |  | 4/1/2022 | 4/1/2022 | 9/29/2022 | N | No
AB2-043 | Chase City 115kV | Bluestone Farm Solar | VA | Mecklenburg | In Service | Dominion | 49.9 | 49.9 | 18.9 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2043_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2043_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_043_csa.pdf | Document Posted | N/A | N/A | 3/2/2021 | 2/29/2016 | N/A | N/A | 3/28/2021 |  |  | 4/8/2021 | 4/8/2021 | 4/3/2021 | N | No
AB2-045 | Buckingham 34.5kV |  | VA | Buckingham | In Service | Dominion | 19.8 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2045_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2045_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2045_wmpa.pdf | Not Required | N/A | N/A |  | 2/29/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-047 | Brokaw-Pontiac Midpoint | Blooming Grove WF | IL | McLean | In Service | ComEd | 250 | 250 | 32.5 | 250 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2047_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2047_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_047_csa.pdf | Document Posted | N/A | N/A | 10/20/2020 | 2/29/2016 | N/A | N/A | 10/30/2020 |  |  | 12/30/2020 | 12/30/2020 | 10/30/2020 | N | No
AB2-038 | Frostburg 138kV |  | MD | Allegany | In Service | APS | 139.4 | 0 | 2.9 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_038_csa.pdf | Document Posted | N/A | N/A |  | 3/1/2016 | N/A | N/A | 12/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 9/13/2017 | N | No
AB2-040 | Brink 115kV | Brink Solar Project | VA | Greensville | In Service | Dominion | 80 | 80 | 44 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2040_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2040_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_040_csa.pdf | Document Posted | N/A | N/A | 10/10/2024 | 3/2/2016 | N/A | N/A | 11/11/2024 |  |  | 10/1/2024 | 10/1/2024 | 12/27/2024 | N | No
AB2-049 | Gloucester Township 12kV | GEMS Landfill Solar | NJ | Camden | In Service | AEC | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2049_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2049_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2049_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2049_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2049_wmpa.pdf | Not Required | N/A | N/A |  | 3/4/2016 | N/A | N/A | 3/18/2022 |  |  | 6/30/2022 | 6/30/2022 | 4/14/2022 | N | No
AB2-050 | Four Rivers 230kV | Doswell Complex 5 & 6 | VA | Hanover | In Service | Dominion | 746 | 20 | 20 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2050_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/4/2016 | N/A | N/A |  |  |  | 3/1/2020 | 3/1/2020 | 2/28/2018 | N | No
AB2-057 | Brunswick 26kV | New Road Solar | NJ | Middlesex | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2057_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2057_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2057_wmpa.pdf | Not Required | N/A | N/A |  | 3/24/2016 | N/A | N/A |  |  |  | 3/30/2018 | 3/30/2018 | 6/22/2018 | N | No
AB2-058 | Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 10 | 0 | 3.6 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2058_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/25/2016 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 12/6/2016 | N | No
AB2-059 | Benson-Dunbar 115kV | Moccasin Creek Solar | NC | Edgecombe | In Service | Dominion | 100 | 100 | 66 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_059_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2016 | N/A | N/A | 6/30/2020 |  |  | 6/15/2020 | 6/15/2020 | 10/12/2020 | N | No
AB2-060 | Chase City-Lunenburg 115kV | Chase City Solar | VA | Mecklenburg | In Service | Dominion | 80 | 80 | 54.4 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_060_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2016 | N/A | N/A | 5/15/2020 |  |  | 5/15/2020 | 5/15/2020 | 7/21/2020 | N | No
AB2-067 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 1100 | 1100 | 1100 | 1100 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2067_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2067_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_067_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 3/31/2016 | N/A | N/A | 9/17/2022 |  |  | 12/31/2022 | 12/31/2022 | 4/7/2023 | N | No
AB2-070 | Mt. Pulaski-Brokaw | Alta Farms II | IL | DeWitt | In Service | ComEd | 197 | 197 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2070_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2070_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_070_csa.pdf | Document Posted | N/A | N/A | 4/1/2023 | 3/31/2016 | N/A | N/A | 5/1/2023 |  |  | 5/31/2023 | 5/31/2023 | 5/20/2023 | N | No
AB2-077 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2077_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2077_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_077_csa.pdf | Document Posted | N/A | N/A | 11/7/2023 | 4/14/2016 | N/A | N/A | 4/17/2024 |  |  | 5/31/2024 | 5/31/2024 | 6/18/2024 | N | No
AB2-078 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 40 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2078_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2078_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_078_csa.pdf | Document Posted | N/A | N/A | 11/7/2023 | 4/14/2016 | N/A | N/A | 4/17/2024 |  |  | 5/31/2024 | 5/31/2024 | 6/18/2024 | N | No
AB2-079 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 60 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_079_csa.pdf | Document Posted | N/A | N/A | 11/7/2023 | 4/14/2016 | N/A | N/A | 4/17/2024 |  |  | 5/31/2024 | 5/31/2024 | 6/18/2024 | N | No
AB2-093 | Ormet 138kV | Hannibal Port Power Project | OH | Monroe | In Service | AEP | 485 | 485 | 485 | 485 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2093_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2093_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2093_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_093_csa.pdf | Document Posted | N/A | N/A | 12/15/2020 | 4/26/2016 | N/A | N/A | 5/22/2021 |  |  | 9/13/2021 | 9/13/2021 | 6/1/2021 | N | No
AB2-097 | Antietam 34.5kV | Hagerstown Plant | MD | Washington | In Service | APS | 10 | 10 | 0 | 10 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2097_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2097_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2097_wmpa.pdf | Not Required | N/A | N/A |  | 4/27/2016 | N/A | N/A | 12/31/2022 |  |  | 2/28/2020 | 2/28/2020 | 10/15/2020 | N | No
AB2-100 | Clubhouse-Lakeview 230kV | Sadler Solar | VA | Greensville | In Service | Dominion | 100 | 100 | 67 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_100_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2016 | N/A | N/A | 1/18/2021 |  |  | 12/1/2021 | 12/1/2021 | 1/22/2021 | N | No
AB2-099 | Ahoskie 34.5kV | Colice Hall Solar | NC | Hertford | In Service | Dominion | 5 | 5 | 3.5 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2099_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_099_csa.pdf | Document Posted | N/A | N/A | 3/1/2023 | 4/28/2016 | N/A | N/A | 6/29/2023 |  |  | 7/23/2023 | 7/23/2023 | 7/6/2023 | N | No
AB2-109 | Reusens 34.5kV | Reusens Hydro Electric Generating Plant | VA | City of Lynchburg | In Service | AEP | 12.5 | 12.5 | 4 | 12.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 3/31/2018 | 3/31/2018 | 11/29/2017 | N | No
AB2-112 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 485 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 2/7/2019 | N | No
AB2-134 | Hopewell-Surry 230kV | Colonial Trail West Solar | VA | Surry | In Service | Dominion | 142.4 | 142.4 | 71.8 | 142.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2134_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2134_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_134_csa.pdf | Document Posted | N/A | N/A | 10/3/2019 | 4/29/2016 | N/A | N/A | 11/7/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/7/2019 | N | No
AB2-139 | Raceway Mall 34.5kV | Freemall Fuel Cell Facility | NJ | Monmouth | In Service | JCPL | 0.42 | 0.42 | 0 | 0.42 | Energy | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2139_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2139_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 2/1/2018 | Y | No
AB2-153 | Church-Wye Mills 138 kV | Pondtown Solar 2 | MD | Queen Anne's | In Service | DPL | 40 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2153_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2153_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2153_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_153_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_153_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 9/23/2022 |  |  | 12/31/2023 | 12/31/2023 | 10/18/2022 | N | No
AB2-157 | Prince George's County 12kV | Rollins Avenue Phoenix | MD | Prince George's | In Service | PEPCO | 2.5 | 2.5 | 0.8 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2157_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2157_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2157_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ab2157_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2157_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/19/2019 |  |  | 7/12/2019 | 7/12/2019 | 12/23/2019 | N | No
AB2-158 | Louisa-South Anna 230kV | Belcher Solar | VA | Louisa | In Service | Dominion | 88.2 | 88.2 | 61 | 88.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2158_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2158_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_158_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 5/31/2021 |  |  | 12/1/2020 | 12/1/2020 | 6/30/2021 | N | No
AB2-169 | Pantago-Five Points 115kV | Wilkinson Solar Energy Center | NC | Hyde | In Service | Dominion | 74 | 74 | 39 | 74 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2169_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2169_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2169_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_169_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_169_csa.pdf | Document Posted | N/A | N/A | 10/10/2019 | 4/29/2016 | N/A | N/A | 11/18/2019 |  |  | 6/30/2021 | 6/30/2021 | 11/20/2019 | N | No
AB2-170 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | In Service | AEP | 150 | 130 | 49.4 | 130 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2170_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2170_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2170_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_170_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_170_csa.pdf | Document Posted | N/A | N/A | 8/7/2020 | 4/29/2016 | N/A | N/A | 10/13/2020 |  |  | 6/1/2021 | 6/1/2021 | 10/13/2020 | N | No
AB2-174 | Emporia-Trego 115kV | Greensville County Solar Project | VA | Greensville | In Service | Dominion | 80 | 80 | 42 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_174_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/1/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/1/2020 | N | No
AB2-179 | Townsend 138kV | New Castle Solar | DE | New Castle | In Service | DPL | 50 | 50 | 37.6 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2179_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2179_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_179_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_179_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 11/22/2022 |  |  | 12/16/2022 | 12/16/2022 | 12/30/2022 | N | No
AB2-190 | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | In Service | Dominion | 150 | 150 | 105 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2190_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2190_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_190_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 8/6/2021 |  | Customer Milestone Not Met | 12/1/2021 | 12/1/2021 | 1/19/2022 | N | No
AB2-191 | Mendota Hills | Mendota Hills Wind Farm | IL | Lee | In Service | ComEd | 70.4 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2191_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_191_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 3/1/2019 | 3/1/2019 | 2/11/2019 | N | No
AB2-132 | Haumesser Road | Lee-DeKalb Wind Energy Center | IL | Lee | In Service | ComEd | 240 | 0 | 2.2 | 0 | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2132_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_132_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2016 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/1/2023 | N | No
AB2-172 | Todd 69kV | Richfield Solar and Storage | MD | Dorchester | In Service | DPL | 50 | 50 | 19 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2172_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2172_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_172_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_172_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2016 | N/A | N/A | 1/30/2024 |  |  | 1/10/2024 | 1/10/2024 | 2/9/2024 | N | No
AB2-161 | Waverly #2 DP 115kV | Waverly Solar | VA | Sussex | In Service | Dominion | 50 | 50 | 19 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ab2161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ab2161_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ab2161_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ab2_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ab2_161_csa.pdf | Document Posted | N/A | N/A | 11/2/2023 | 5/2/2016 | N/A | N/A | 12/21/2023 |  |  | 12/29/2023 | 12/29/2023 | 3/14/2024 | N | No
AC1-001 | Delano 138kV | Salt City Solar | OH | Ross | In Service | AEP | 49.9 | 49.9 | 33.93 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1001_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1001_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_001_csa.pdf | Document Posted | N/A | N/A | 6/29/2023 | 5/6/2016 | N/A | N/A | 6/29/2023 |  |  | 8/31/2023 | 8/31/2023 | 8/8/2023 | N | No
AC1-008 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 1799.3 | 15 | 19.2 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1008_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1008_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_008_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 6/9/2016 | N/A | N/A |  |  |  | 1/13/2023 | 1/13/2023 |  | N | No
AC1-017 | Levittown 13 kV | Levittown 13 kV Solar | NJ | Burlington | In Service | PSEG | 3.7 | 3.7 | 1.4 | 3.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1017_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1017_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1017_wmpa.pdf | Not Required | N/A | N/A |  | 7/13/2016 | N/A | N/A | 4/17/2020 |  |  | 3/31/2020 | 3/31/2020 | 5/28/2020 | N | No
AC1-021 | Yukon Hatfield 500kV | Smithton Generation Station | PA | Westmoreland | In Service | APS | 1050 | 110 | 0 | 110 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1021_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_021_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/14/2016 | N/A | N/A |  |  |  | 3/1/2019 |  | 11/18/2018 | N | No
AC1-025 | Dale Summit | State College Pumping Station Battery | PA | Centre | In Service | APS | 1.5 | 1.5 | 0 | 1.5 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1025_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1025_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1025_wmpa.pdf | Not Required | N/A | N/A |  | 7/18/2016 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 2/14/2019 | Y | Yes
AC1-027 | Pendleton 34.5kV | Oceana Solar Facility | VA | City of Virginia Beach | In Service | Dominion | 17.6 | 17.6 | 11.2 | 17.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1027_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1027_wmpa.pdf | Not Required | N/A | N/A |  | 7/26/2016 | N/A | N/A |  |  |  | 1/1/2018 | 1/1/2018 | 12/1/2017 | N | No
AC1-030 | Cinnaminson 13kV | Pennsauken Solar 3 | NJ | Camden | In Service | PSEG | 2.5 | 2.5 | 0.95 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1030_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1030_wmpa.pdf | Not Required | N/A | N/A |  | 8/1/2016 | N/A | N/A |  |  |  | 12/29/2017 | 12/29/2017 | 12/13/2017 | N | Yes
AC1-033 | Kewanee 138 kV | Midland Wind Farm | IL | Henry | In Service | ComEd | 100.8 | 100.8 | 13.1 | 100.8 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_033_csa.pdf | Document Posted | N/A | N/A | 11/17/2023 | 8/14/2016 | N/A | N/A | 11/21/2023 |  |  | 4/15/2024 | 4/15/2024 | 1/31/2024 | N | No
AC1-035 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | In Service | ME | 750 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1035_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_035_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2016 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 3/30/2018 | N | No
AC1-036 | Twittys Creek 34.5kV | Twittys Creek Solar | VA | Charlotte | In Service | Dominion | 13.75 | 13.75 | 5.7 | 13.75 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1036_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1036_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1036_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/8/2020 | N | No
AC1-038 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 293 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1038_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1038_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/30/2016 | N/A | N/A |  |  |  | 10/1/2018 | 10/1/2018 | 5/30/2016 | N | No
AC1-044 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 1650 | 550 | 550 | 550 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1044_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1044_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_044_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 8/31/2016 | N/A | N/A | 9/17/2022 |  |  | 12/31/2022 | 12/31/2022 | 12/7/2022 | N | No
AC1-054 | Kerr Dam–Eatons Ferry 115 kV | Hawtree Creek | NC | Warren | In Service | Dominion | 65 | 65 | 44.5 | 65 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1054_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1054_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_054_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A | 12/1/2021 |  |  | 6/1/2021 | 6/1/2021 | 10/1/2021 | N | No
AC1-042 | Altavista-Mt. Airy 69kV | Sycamore Solar I | VA | Pittsylvania | In Service | Dominion | 42 | 42 | 15.96 | 42 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1042_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1042_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_042_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_042_csa.pdf | Document Posted | N/A | N/A |  | 9/1/2016 | N/A | N/A | 3/23/2023 |  |  | 12/1/2022 | 12/1/2022 | 2/14/2023 | N | No
AC1-060 | Providence Forge 34.5kV | Charles City 1 | VA | Charles City | In Service | Dominion | 24 | 0 | 2.5 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_060_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 6/9/2017 | N | No
AC1-061 | Locks 34.5kV | Dinwiddie 2 | VA | Dinwiddie | In Service | Dominion | 3 | 0 | 0.2 | 0 | Capacity | Generation Interconnection | Diesel; Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_061_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 6/1/2017 | N | No
AC1-062 | Jetersville 34.5kV | Amelia 1 | VA | Amelia | In Service | Dominion | 16 | 0 | 1.9 | 0 | Capacity | Generation Interconnection | Diesel; Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_062_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/24/2018 | N | No
AC1-063 | Shackleford 34.5kV | King & Queen Landfill Facility | VA | King and Queen | In Service | Dominion | 14 | 0 | 2.2 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1063_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_063_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 5/9/2019 | N | No
AC1-064 | Route 16 34.5kV | Route 16 (Mountain View) 345kV (Upton 114) | PA | Franklin | In Service | APS | 15 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_064_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 6/22/2017 | N | No
AC1-068 | Atlanta 69kV I | Pickaway County Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 34 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1068_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1068_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1068_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_068_csa.pdf | Document Posted | N/A | N/A | 10/10/2024 | 9/28/2016 | N/A | N/A | 10/11/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-069 | Atlanta 69kV II | Pickaway County II Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 34 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1069_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1069_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1069_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_069_csa.pdf | Document Posted | N/A | N/A | 10/10/2024 | 9/28/2016 | N/A | N/A | 10/11/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-072 | Segreto (Covert) 345kV | Covert Generating Facility | MI | Van Buren | In Service | ITCI | 1055 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1072_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2016 | N/A | N/A |  |  |  | 6/18/2018 | 6/18/2018 | 5/9/2018 | N | No
AC1-075 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | In Service | Dominion | 60 | 60 | 38.3 | 60 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1075_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_075_csa.pdf | Document Posted | N/A | N/A | 3/3/2021 | 9/29/2016 | N/A | N/A | 3/30/2021 |  |  | 12/31/2021 | 12/31/2021 | 4/1/2021 | N | No
AC1-080 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | In Service | Dominion | 80 | 20 | 12.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1080_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1080_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1080_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_080_csa.pdf | Document Posted | N/A | N/A | 3/3/2021 | 9/30/2016 | N/A | N/A | 3/30/2021 |  |  | 12/31/2021 | 12/31/2021 | 4/1/2021 | N | No
AC1-083 | Smith Mountain-Bearskin 138kV | Maplewood Solar | VA | Pittsylvania | In Service | AEP | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1083_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1083_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1083_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_083_csa.pdf | Document Posted | N/A | N/A | 12/15/2021 | 9/30/2016 | N/A | N/A | 9/2/2022 |  |  | 5/20/2022 | 5/20/2022 | 9/2/2022 | N | No
AC1-078 | Beatty-London 138kV | Big Plain | OH | Madison | In Service | ATSI | 176 | 176 | 66 | 176 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1078_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1078_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_078_csa.pdf | Document Posted | N/A | N/A | 5/5/2023 | 10/1/2016 | N/A | N/A | 6/25/2023 |  |  | 8/31/2023 | 8/31/2023 | 7/25/2023 | N | No
AC1-076 | Locust Grove-Paytes 115kV | Pine Glade Solar | VA | Orange | In Service | Dominion | 62.5 | 62.5 | 23.8 | 62.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1076_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1076_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1076_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_076_csa.pdf | Document Posted | N/A | N/A | 5/30/2024 | 10/2/2016 | N/A | N/A | 7/19/2024 |  |  | 7/15/2024 | 7/15/2024 | 9/13/2024 | N | No
AC1-085 | Stuart-Clinton 345kV | Highland County Solar | OH | Highland | In Service | Dayton | 400 | 400 | 152 | 400 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1085_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1085_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_085_csa.pdf | Document Posted | N/A | N/A |  | 10/2/2016 | N/A | N/A | 10/27/2023 |  |  | 12/31/2023 | 12/31/2023 | 8/21/2024 | N | No
AC1-087 | Siegfried-Hauto 69kV | PA Solar Park | PA | Carbon | In Service | PPL | 20 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1087_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_087_csa.pdf | Document Posted | N/A | N/A |  | 10/11/2016 | N/A | N/A | 12/1/2019 |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AC1-089 | Hillsboro-Wildcat 138kV | Willowbrook Solar | OH | Highland | In Service | AEP | 150 | 150 | 57 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1089_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1089_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1089_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_089_csa.pdf | Document Posted | N/A | N/A | 11/13/2023 | 10/15/2016 | N/A | N/A | 11/13/2023 |  |  | 1/19/2024 | 1/19/2024 | 9/27/2024 | N | No
AC1-100 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 678 | 98 | 43.4 | 98 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1100_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_100_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/10/2017 | N | No
AC1-105 | Halifax-Mt. Laurel 115kV | Sunnybrook Farm Solar | VA | Halifax | In Service | Dominion | 51 | 51 | 34.5 | 51 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1105_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1105_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1105_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_105_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_105_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2016 | N/A | N/A | 12/20/2022 |  |  | 2/9/2023 | 2/9/2023 | 12/28/2022 | N | No
AC1-108 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 1100 | 50 | 100 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1108_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2016 | N/A | N/A | 9/13/2019 |  |  | 3/1/2021 | 3/1/2021 | 9/22/2019 | N | No
AC1-109 | Aurora 345kV | Aurora Generation | IL | Du Page | In Service | ComEd | 980 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 8/27/2020 | N | No
AC1-110 | Aurora 138kV | Aurora Generation | IL | Du Page | In Service | ComEd | 1046 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1110_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1110_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_110_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_110_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 8/28/2023 | 8/28/2023 | 4/30/2023 | N | No
AC1-111 | Aurora 138kV | Aurora Generation | IL | Du Page | In Service | ComEd | 1016 | 36 | 36 | 36 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1111_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_111_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 8/27/2020 | N | No
AC1-112 | Old Church 34.5kV | Hollyfield Solar Facility | VA | King William | In Service | Dominion | 17 | 17 | 10.9 | 17 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1112_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1112_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 8/8/2018 | N | No
AC1-113 | Rockford | Rockford I Energy Center | IL | Winnebago | In Service | ComEd | 320 | 20 | 20 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1113_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 | 6/5/2021 | N | No
AC1-114 | Rockford II | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 173 | 20 | 20 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1114_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 | 8/25/2021 | N | No
AC1-118 | Westmoreland 34.5kV | Montross Solar Facility | VA | Westmoreland | In Service | Dominion | 20 | 20 | 13.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1118_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1118_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1118_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 12/12/2018 | N | No
AC1-122 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | In Service | AEP | 60 | 60 | 40.7 | 60 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1122_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1122_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1122_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_122_csa.pdf | Document Posted | N/A | N/A | 9/30/2020 | 10/27/2016 | N/A | N/A | 10/21/2020 |  |  | 6/1/2021 | 6/1/2021 | 10/21/2020 | N | No
AC1-123 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | In Service | AEP | 80 | 20 | 13.7 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1123_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1123_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_123_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_123_csa.pdf | Document Posted | N/A | N/A | 9/30/2020 | 10/27/2016 | N/A | N/A | 10/15/2020 |  |  | 6/1/2021 | 6/1/2021 | 10/21/2020 | N | No
AC1-134 | Four Rivers 230kV | Doswell Facility (Doswell Complex 5 & 6) | VA | Hanover | In Service | Dominion | 746 | 0 | 50 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1134_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_134_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 9/30/2019 | 9/30/2019 | 2/28/2018 | N | No
AC1-140 | North Longview 500 kV | Longview Power | WV | Monongalia | In Service | APS | 710 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1140_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_140_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_140_csa.pdf | Document Posted | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 6/30/2018 | 6/30/2018 | 5/14/2018 | N | No
AC1-141 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | In Service | AEP | 1085 | 91 | 91 | 91 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1141_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1141_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/24/2021 | 10/28/2016 | N/A | N/A | 12/27/2021 |  |  | 3/15/2022 | 3/15/2022 | 12/27/2021 | N | No
AC1-145 | Gretna DP 69 kV | Whitethorn Solar | VA | Pittsylvania | In Service | Dominion | 50 | 50 | 19 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1145_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1145_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_145_csa.pdf | Document Posted | N/A | N/A | 7/1/2021 | 10/31/2016 | N/A | N/A | 9/1/2021 |  |  | 9/1/2021 | 9/1/2021 | 10/13/2021 | N | No
AC1-147 | Grassfield 34.5kV |  | VA | City of Chesapeake | In Service | Dominion | 20 | 20 | 12.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1147_fea.pdf | Document Posted |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac1147_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1147_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A | 9/30/2022 |  |  | 12/31/2021 | 12/31/2021 | 3/25/2022 | N | Yes
AC1-152 | Lawrenceburg 345kV PB I | Lawrenceburg Generating Plant | IN | Dearborn | In Service | AEP | 1270 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1152_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_152_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/13/2019 | N | No
AC1-158 | Spotsylvania 500kV | Spotsylvania Energy Center | VA | Spotsylvania | In Service | Dominion | 485 | 485 | 337 | 485 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1158_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1158_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1158_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_158_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 10/31/2016 | N/A | N/A | 12/31/2022 |  |  | 12/31/2022 | 12/31/2022 | 9/2/2020 | N | No
AC1-172 | Lawrenceburg 345kV PB II | Lawrenceburg Generating Plant | IN | Dearborn | In Service | AEP | 1320 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1172_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_172_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/13/2019 | N | No
AC1-173 | Logtown 138kV | Timber Road IV Wind Farm (Southern Phase) | OH | Paulding | In Service | AEP | 75.9 | 75.9 | 9.9 | 75.9 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1173_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1173_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_173_csa.pdf | Document Posted | N/A | N/A | 2/5/2020 | 10/31/2016 | N/A | N/A | 2/15/2020 |  |  | 3/31/2020 | 3/31/2020 | 3/27/2020 | N | No
AC1-174 | Losantville 345kV | Riverstart Solar Park | IN | Randolph | In Service | AEP | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1174_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1174_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1174_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_174_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/24/2021 |  |  | 6/1/2022 | 6/1/2022 | 9/24/2021 | N | No
AC1-175 | Losantville 345kV | Riverstart Solar Park | IN | Randolph | In Service | AEP | 200 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1175_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1175_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_175_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/10/2021 |  |  | 6/1/2022 | 6/1/2022 | 9/24/2021 | N | No
AC1-181 | Richland 138kV | Richland Power Plant | OH | Defiance | In Service | ATSI | 428 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1181_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2019 |  | 8/8/2018 | N | No
AC1-185 | Lee County | Lee Energy Facility | IL | Lee | In Service | ComEd | 688 | 48 | 48 | 48 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1185_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1185_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2019 |  | 12/14/2018 | N | No
AC1-204 | Elwood | Jackson Generation | IL | Will | In Service | ComEd | 1200.9 | 1200.9 | 1115.9 | 1200.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1204_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1204_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1204_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_204_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_204_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 11/8/2021 |  |  | 4/1/2022 | 4/1/2022 | 5/3/2022 | N | No
AC1-207 | Monroe 34.5kV | Hoffman Station Road Solar | NJ | Middlesex | In Service | JCPL | 13.1 | 13.1 | 4.9 | 13.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1207_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1207_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_207_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_207_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 6/16/2020 |  |  | 5/26/2020 | 5/26/2020 | 6/25/2020 | N | Yes
AC1-214 | Crescent Ridge | Lone Tree Wind | IL | Bureau | In Service | ComEd | 79.4 | 79.4 | 19 | 79.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1214_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1214_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1214_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_214_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_214_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 11/27/2020 |  |  | 12/30/2020 | 12/30/2020 | 11/20/2020 | N | No
AC1-216 | Hopewell-Surry 230kV | Spring Grove I Solar | VA | Surry | In Service | Dominion | 97.9 | 97.9 | 54.8 | 97.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1216_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1216_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1216_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_216_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_216_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 9/14/2020 |  |  | 12/1/2020 | 12/1/2020 | 10/1/2020 | N | No
AC1-223 | E. Frankfort-University Park North |  | IL | Will | In Service | ComEd | 0 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ac1223_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ac1223_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/ac1223_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 |  | 12/12/2018 | EE | No
AC1-161 | Septa 500kV | Cavalier | VA | Isle of Wight | In Service | Dominion | 240 | 240 | 168.2 | 240 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1161_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1161_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1161_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_161_csa.pdf | Document Posted | N/A | N/A | 6/23/2023 | 11/2/2016 | N/A | N/A | 12/12/2023 |  |  | 1/1/2023 | 1/1/2023 | 12/10/2024 | N | No
AC1-165 | Atlanta 69kV III | Buckeye Plains II Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 33.6 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1165_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1165_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1165_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_165_csa.pdf | Document Posted | N/A | N/A | 9/19/2024 | 11/2/2016 | N/A | N/A | 10/2/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-166 | Atlanta 69kV IV | Buckeye Plains Solar | OH | Pickaway | In Service | Dayton | 99.8 | 49.9 | 33.6 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1166_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1166_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_166_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_166_csa.pdf | Document Posted | N/A | N/A | 9/19/2024 | 11/2/2016 | N/A | N/A | 10/2/2024 |  |  | 1/7/2025 | 1/7/2025 | 1/17/2025 | N | No
AC1-221 | Halifax-Person 230kV | Alton Post Office Solar | VA | Halifax | In Service | Dominion | 29.2 | 29.2 | 14.6 | 29.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1221_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1221_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_221_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_221_csa.pdf | Document Posted | N/A | N/A | 9/26/2024 | 11/2/2016 | N/A | N/A | 10/31/2024 |  |  | 12/31/2024 | 12/31/2024 | 1/9/2025 | N | No
AC1-222 | Crystal Hill-Halifax 115kV | Halifax County Solar | VA | Halifax | In Service | Dominion | 44.7 | 44.7 | 22.9 | 44.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac1222_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac1222_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac1222_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac1_222_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac1_222_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 11/3/2016 | N/A | N/A | 12/7/2023 |  |  | 12/29/2023 | 12/29/2023 | 2/15/2024 | N | No
AC2-009 | Pennington 13 kV | Pennington 13 kV Solar | NJ | Mercer | In Service | PSEG | 0.59 | 0.59 | 0.1 | 0.55 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2009_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2009_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2009_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2016 | N/A | N/A | 6/1/2023 |  |  | 3/2/2018 | 3/2/2018 | 10/19/2017 | N | Yes
AC2-012 | Grassfield-Great Bridge 115kV | Shillelagh Solar | VA | City of Chesapeake | In Service | Dominion | 118 | 118 | 44.8 | 118 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2012_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2012_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2012_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_012_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2016 | N/A | N/A | 11/8/2023 |  |  | 12/31/2023 | 12/31/2023 | 12/20/2023 | N | No
AC2-016 | Stemple 345kV | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 748 | 6 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2016_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_016_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/3/2017 | N/A | N/A |  |  |  | 9/1/2019 | 9/1/2019 | 2/14/2020 | N | No
AC2-017 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 1810.4 | 11.1 | 11.1 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2017_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_017_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 1/4/2017 | N/A | N/A |  |  |  | 1/13/2023 | 1/13/2023 |  | N | No
AC2-018 | Rock Springs 500kV | Rock Springs Units #3 & #4 | MD | Cecil | In Service | Essential Power | 390 | 60 | 8 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2018_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2018_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/19/2017 | N/A | N/A |  |  |  | 6/1/2017 |  | 10/1/2017 | N | No
AC2-059 | Biers Run-Circleville 138kV | Yellowbud Solar | OH | Ross | In Service | AEP | 127 | 127 | 62.5 | 127 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_059_csa.pdf | Document Posted | N/A | N/A | 10/24/2022 | 2/16/2017 | N/A | N/A | 12/21/2022 |  |  | 12/15/2022 | 12/15/2022 | 12/21/2022 | N | No
AC2-060 | Buckskin 69kV | Ross County Solar | OH | Ross | In Service | AEP | 100 | 100 | 64 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_060_csa.pdf | Document Posted | N/A | N/A | 8/16/2024 | 2/18/2017 | N/A | N/A | 9/17/2024 |  |  | 6/1/2024 | 6/1/2024 | 2/19/2025 | N | No
AC2-066 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | In Service | DEOK | 200 | 75 | 28.5 | 75 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2066_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2066_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_066_csa.pdf | Document Posted | N/A | N/A | 8/19/2020 | 2/24/2017 | N/A | N/A | 11/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/18/2020 | N | No
AC2-088 | S. Bethel-Brown 69kV | Nestlewood Solar | OH | Clermont | In Service | DEOK | 70 | 70 | 38.4 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2088_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2088_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2088_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_088_csa.pdf | Document Posted | N/A | N/A | 12/7/2023 | 3/1/2017 | N/A | N/A | 12/20/2023 |  |  | 3/31/2024 | 3/31/2024 | 12/27/2023 | N | No
AC2-092 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1105 | 55 | 65 | 55 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2092_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2092_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_092_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/1/2017 | N/A | N/A | 6/1/2023 |  |  | 6/1/2022 | 6/1/2022 | 1/26/2023 | N | No
AC2-090 | Losantville 345kV | Riverstart Solar Park III | IN | Randolph | In Service | AEP | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_090_csa.pdf | Document Posted | N/A | N/A | 3/26/2024 | 3/7/2017 | N/A | N/A | 8/21/2024 |  | Customer Milestone Not Met | 12/31/2024 | 12/31/2024 | 12/18/2024 | N | No
AC2-100 | Halifax-Person 230kV | Powells Creek Solar | VA | Halifax | In Service | Dominion | 50 | 50 | 33.6 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_100_csa.pdf | Document Posted | N/A | N/A | 7/26/2023 | 3/12/2017 | N/A | N/A | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 | 8/23/2023 | N | No
AC2-115 | Rockford | Rockford I Energy Center | IL | Winnebago | In Service | ComEd | 360 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2115_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_115_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 | 8/27/2021 | N | No
AC2-116 | Rockford II | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 180 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2116_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_116_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 | 8/25/2021 | N | No
AC2-117 | University Park North | University Park North Energy Center | IL | Will | In Service | ComEd | 606 | 46 | 46 | 46 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2117_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2117_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_117_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 5/31/2021 | 5/31/2021 | 11/6/2023 | N | No
AC2-120 | Ripley 69kV | Ripley Solar | MD | Charles | In Service | SMECO | 27.5 | 27.5 | 10.45 | 10.45 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2120_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2120_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2120_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2120_wmpa.pdf | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 2/28/2023 |  |  | 7/13/2022 | 7/13/2022 | 6/23/2023 | N | No
AC2-125 | Ladysmith 230 kV I | Ladysmith Combustion Turbines Unit 1 | VA | Caroline | In Service | Dominion | 209 | 19 | 14.9 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2125_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_125_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 6/1/2021 |  |  | 6/1/2020 | 6/1/2020 | 5/17/2019 | N | No
AC2-126 | Ladysmith 230 kV II | Ladysmith Combustion Turbines Unit 2 | VA | Caroline | In Service | Dominion | 209 | 19 | 15 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2126_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_126_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 6/1/2021 |  |  | 6/1/2020 | 6/1/2020 | 5/17/2019 | N | No
AC2-133 | Warren County 500kV | Warren County Power Station | VA | Warren | In Service | Dominion | 1484 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2133_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_133_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 | 9/4/2018 | N | No
AC2-137 | Elko 34.5kV | Briel Farm Solar | VA | Henrico | In Service | Dominion | 18.8 | 18.8 | 11.4 | 18.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2137_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2137_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2137_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2137_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 | 12/30/2020 | 12/21/2020 | N | No
AC2-138 | Northern Neck 34.5kV | Gardy's Mill Solar | VA | Westmoreland | In Service | Dominion | 10.8 | 10.8 | 4.8 | 10.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2138_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2138_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2138_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 | 12/30/2020 | 12/21/2020 | N | No
AC2-140 | DC Cook Unit 2 | DC Cook Generating Plant Unit No. 2 | MI | Berrien | In Service | AEP | 1220 | 28 | 38 | 28 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2140_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_140_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 1/14/2017 | N | No
AC2-142 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 664.7 | 129.7 | 129.7 | 129.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2142_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_142_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A | 3/16/2021 |  |  | 5/9/2021 | 5/9/2021 | 4/1/2021 | N | No
AC2-168 | Clinton 23kV | Gaucho Solar | PA | Washington | In Service | DL | 11.7 | 11.7 | 4.4 | 11.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2168_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2168_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2168_wmpa.pdf | Not Required | N/A | N/A | 3/21/2023 | 3/30/2017 | N/A | N/A | 3/21/2023 |  |  | 6/1/2023 | 6/1/2023 | 6/29/2023 | N | Yes
AC2-172 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 310 | 17 | 12 | 17 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2172_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ac2_172_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2017 | N/A | N/A |  |  |  | 10/1/2018 | 10/1/2018 | 5/30/2016 | N | No
AC2-175 | Berkshire Solar 12 kV | Berkshire Solar | NJ | Morris | In Service | JCPL | 1.6 | 1.6 | 0 | 1.6 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ac2175_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2175_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A | 9/30/2021 |  |  | 9/30/2021 | 9/30/2021 | 11/6/2021 | N | Yes
AC2-176 | Jay 138 kV | Bitter Ridge Wind Farm | IN | Jay | In Service | AEP | 130 | 130 | 16.9 | 130 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ac2176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ac2176_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ac2176_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ac2_176_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ac2_176_csa.pdf | Document Posted | N/A | N/A | 9/2/2020 | 3/31/2017 | N/A | N/A | 9/5/2020 |  |  | 10/31/2020 | 10/31/2020 | 9/5/2020 | N | No
AD1-017 | Smith Mountain-Bearskin 138 kV | Maplewood Solar | VA | Pittsylvania | In Service | AEP | 120 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1017_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1017_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1017_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_017_csa.pdf | Document Posted | N/A | N/A | 12/17/2021 | 5/11/2017 | N/A | N/A | 12/28/2021 |  |  | 12/1/2022 | 12/1/2022 | 9/2/2022 | N | No
AD1-020 | Hunterstown-Lincoln 115 kV | Adams Solar LLC | PA | Adams | In Service | ME | 80 | 80 | 53.6 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1020_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1020_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1020_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_020_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_020_csa.pdf | Document Posted | N/A | N/A | 12/22/2023 | 6/9/2017 | N/A | N/A | 12/27/2023 |  |  | 2/25/2024 | 2/25/2024 | 3/21/2024 | N | No
AD1-026 | Shenango-Hoytdale 345 kV | Hickory Run Energy Station | PA | Lawrence | In Service | ATSI | 1000 | 0 | 130 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1026_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/22/2019 | 6/28/2017 | N/A | N/A |  |  |  | 3/30/2020 | 3/30/2020 | 4/28/2020 | N | No
AD1-033 | Fentress-Landstown 230 kV | Bedford Solar Center | VA | City of Chesapeake | In Service | Dominion | 70 | 70 | 42 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1033_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1033_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1033_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_033_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2017 | N/A | N/A | 12/31/2021 |  |  | 12/1/2021 | 12/1/2021 | 11/23/2021 | N | No
AD1-037 | Martins Creek 230 kV | Lower Mount Bethel | PA | Northampton | In Service | PPL | 651.6 | 51.6 | 86.6 | 51.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1037_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1037_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/28/2017 | N/A | N/A | 8/16/2022 |  |  | 9/29/2019 | 9/29/2019 | 7/10/2019 | N | No
AD1-041 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | In Service | Dominion | 50 | 50 | 30 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1041_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1041_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_041_csa.pdf | Document Posted | N/A | N/A | 4/4/2024 | 8/3/2017 | N/A | N/A | 7/17/2024 |  |  | 6/28/2024 | 6/28/2024 | 8/22/2024 | N | No
AD1-052 | Freemont Energy Center | Freemont Energy Center | OH | Sandusky | In Service | ATSI | 745 | 38 | 26.3 | 38 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1052_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_052_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/10/2017 | N/A | N/A | 10/1/2020 |  |  | 10/1/2020 | 10/1/2020 | 2/24/2021 | N | No
AD1-054 | Bergen 13 kV | Bergen 13kV | NJ | Bergen | In Service | PSEG | 1.5 | 1.5 | 0 | 1.5 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1054_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1054_wmpa.pdf | Not Required | N/A | N/A |  | 8/11/2017 | N/A | N/A | 12/20/2019 |  |  | 10/15/2019 | 10/15/2019 | 12/31/2019 | Y | Yes
AD1-055 | Crystal Hill-Halifax 115 kV | Halifax County Solar | VA | Halifax | In Service | Dominion | 64.7 | 20 | 15.9 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1055_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1055_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1055_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_055_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_055_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 8/16/2017 | N/A | N/A | 12/7/2023 |  |  | 12/29/2023 | 12/29/2023 | 2/15/2024 | N | No
AD1-058 | Halifax-Person 230 kV | Alton Post Office Solar | VA | Halifax | In Service | Dominion | 75.1 | 45.9 | 36.6 | 45.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1058_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1058_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_058_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_058_csa.pdf | Document Posted | N/A | N/A | 9/26/2024 | 8/16/2017 | N/A | N/A | 10/31/2024 |  |  | 12/31/2024 | 12/31/2024 | 1/9/2025 | N | No
AD1-059 | Lakewood 230 kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 0 | 14.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1059_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_059_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/17/2017 | N/A | N/A |  |  |  | 9/30/2019 | 9/30/2019 | 5/7/2018 | N | No
AD1-060 | Mercersburg-Milnor 34.5 kV | Upton Solar | PA | Franklin | In Service | APS | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_060_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2017 | N/A | N/A | 9/1/2021 |  |  | 9/1/2021 | 9/1/2021 | 12/17/2020 | N | No
AD1-061 | McConnelsburg-Mercersburg 34 kV |  | PA | Franklin | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1061_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1061_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_061_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2017 | N/A | N/A |  |  |  | 3/31/2022 | 3/31/2022 | 5/6/2022 | N | No
AD1-063 | Harmony Village 34.5 kV | Puller Solar | VA | Middlesex | In Service | Dominion | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1063_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1063_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2017 | N/A | N/A | 10/8/2018 |  |  | 12/1/2018 | 12/1/2018 | 10/8/2018 | N | No
AD1-067 | Mendota Hills | Mendota Hills Wind Farm | IL | Lee | In Service | ComEd | 76.13 | 5.725 | 1.1 | 5.725 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1067_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 11/30/2018 |  | 10/19/2020 | N | No
AD1-072 | Biers Run-Circleville 138 kV | Yellowbud Solar | OH | Ross | In Service | AEP | 147 | 20 | 13.7 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1072_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_072_csa.pdf | Document Posted | N/A | N/A | 10/24/2022 | 8/31/2017 | N/A | N/A | 12/21/2022 |  |  | 12/15/2022 | 12/15/2022 | 12/21/2022 | N | No
AD1-073 | Buckskin 69 kV | Ross County Solar | OH | Ross | In Service | AEP | 120 | 20 | 13.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1073_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1073_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_073_csa.pdf | Document Posted | N/A | N/A | 8/16/2024 | 9/2/2017 | N/A | N/A | 9/17/2024 |  |  | 6/1/2024 | 6/1/2024 | 2/19/2025 | N | No
AD1-081 | Beatty-London 138 kV | Big Plain 2 | OH | Madison | In Service | ATSI | 196 | 20 | 13.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1081_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1081_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_081_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/22/2023 | 9/6/2017 | N/A | N/A | 6/25/2023 |  |  | 8/31/2023 | 8/31/2023 | 7/25/2023 | N | No
AD1-082 | Bakers Pond-Ivor 115kV | Waverly Solar | VA | Sussex | In Service | Dominion | 68 | 68 | 43.3 | 68 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1082_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1082_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1082_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_082_csa.pdf | Document Posted | N/A | N/A | 10/26/2023 | 9/8/2017 | N/A | N/A | 12/28/2023 |  |  | 2/16/2024 | 2/16/2024 | 3/14/2024 | N | No
AD1-084 | Cushaw 115 kV | Cushaw Hydropower Station | VA | Bedford | In Service | Dominion | 7.5 | 5.5 | 5.5 | 5.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1084_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1084_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1084_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/12/2017 | N/A | N/A |  |  |  | 1/15/2019 | 1/15/2019 | 11/12/2018 | N | No
AD1-087 | Clover-Sedge Hill 230 kV | Foxhound Solar | VA | Halifax | In Service | Dominion | 64.2 | 64.2 | 43.7 | 64.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1087_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1087_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1087_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_087_csa.pdf | Document Posted | N/A | N/A | 2/1/2024 | 9/16/2017 | N/A | N/A | 2/15/2024 |  |  | 5/31/2024 | 5/31/2024 | 4/24/2024 | N | No
AD1-097 | Linwood 230 kV II | Phillips Island CT1, CT2, CT3, and ST4 | PA | Delaware | In Service | PECO | 919 | 67 | 34.8 | 67 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_097_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_097_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2017 | N/A | N/A |  |  |  | 7/30/2021 | 7/30/2021 | 6/9/2020 | N | No
AD1-099 | South Bend 500 kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 720 | 0 | 70 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1099_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1099_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_099_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2017 | N/A | N/A |  |  |  | 9/1/2019 | 9/1/2019 | 9/20/2018 | N | No
AD1-101 | Continental 69 kV | Blue Harvest Solar Park | OH | Putnam | In Service | AEP | 49.9 | 49.9 | 18.96 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1101_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_101_csa.pdf | Document Posted | N/A | N/A | 12/17/2022 | 9/21/2017 | N/A | N/A | 8/22/2023 |  |  | 6/30/2023 | 6/30/2023 | 11/22/2023 | N | No
AD1-108 | Grover 34 kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 9/17/2018 | 9/17/2018 | 7/16/2018 | N | No
AD1-109 | Canton 34.5 kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 21 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 7/9/2018 | 7/9/2018 | 5/10/2018 | N | No
AD1-110 | North Meshoppen 34.5 kV | Roundtop Energy Projects | PA | Susquehanna | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 8/9/2018 | 8/9/2018 | 6/22/2018 | N | No
AD1-114 | Kelson Ridge 230kV | CPV Maryland | MD | Charles | In Service | PEPCO | 820 | 75 | 75 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1114_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2017 | N/A | N/A |  |  |  | 5/31/2021 | 5/31/2021 | 3/28/2019 | N | No
AD1-118 | Lemoyne | Troy Energy | OH | Wood | In Service | ATSI | 700 | 60 | 60 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1118_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1118_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_118_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/27/2017 | N/A | N/A |  |  |  | 8/1/2022 | 8/1/2022 | 8/17/2022 | N | No
AD1-119 | Payne 69 kV | Timber Road Solar Park | OH | Paulding | In Service | AEP | 49.9 | 49.9 | 18.96 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1119_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1119_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1119_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_119_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_119_csa.pdf | Document Posted | N/A | N/A | 12/15/2022 | 9/28/2017 | N/A | N/A | 6/29/2023 |  |  | 11/30/2023 | 11/30/2023 | 9/12/2024 | N | No
AD1-135 | Clinton 23 kV II | Gaucho Solar | PA | Washington | In Service | DL | 20 | 8.3 | 3.15 | 8.3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1135_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1135_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1135_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1135_wmpa.pdf | Not Required | N/A | N/A | 3/21/2023 | 9/29/2017 | N/A | N/A | 3/21/2023 |  |  | 6/1/2023 | 6/1/2023 | 6/29/2023 | N | No
AD1-142 | Milan 34.5 kV | Milan Energy | PA | Bradford | In Service | PENELEC | 21 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1142_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_142_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 7/9/2018 | 7/9/2018 | 4/24/2018 | N | No
AD1-131 | Sedge Hill-Person 230 kV | Powells Creek Solar | VA | Halifax | In Service | Dominion | 70 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1131_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1131_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1131_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_131_csa.pdf | Document Posted | N/A | N/A | 7/26/2023 | 9/30/2017 | N/A | N/A | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 | 8/23/2023 | N | No
AD1-136 | South Bethel-Brown 69 kV | Nestlewood Solar | OH | Clermont | In Service | DEOK | 80 | 10 | 5.4 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1136_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1136_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1136_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_136_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_136_csa.pdf | Document Posted | N/A | N/A | 12/7/2023 | 9/30/2017 | N/A | N/A | 12/20/2023 |  |  | 3/31/2024 | 3/31/2024 | 12/27/2023 | N | No
AD1-144 | Kings Fork 34.5 kV | TWE Myrtle Solar Project | VA | City of Suffolk | In Service | Dominion | 15 | 15 | 9.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1144_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad1144_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1144_wmpa.pdf | Not Required | N/A | N/A | 4/15/2020 | 9/30/2017 | N/A | N/A | 5/5/2020 |  |  | 6/1/2020 | 6/1/2020 | 6/29/2020 | N | No
AD1-148 | Brokaw-Lanesville | HillTopper Wind Farm | IL | Logan | In Service | ComEd | 185 | 0 | 36.3 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1148_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_148_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/1/2017 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 9/1/2022 | N | No
AD1-152 | Clover-Sedge Hill 230 kV | Piney Creek Solar | VA | Halifax | In Service | Dominion | 80 | 80 | 48 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1152_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1152_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1152_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_152_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_152_csa.pdf | Document Posted | N/A | N/A |  | 10/1/2017 | N/A | N/A | 6/19/2023 |  |  | 12/1/2023 | 12/1/2023 | 8/15/2023 | N | No
AD1-130 | Hardin Switch 345 kV | Hardin Energy Center – Phase 2 | OH | Hardin | In Service | AEP | 150 | 150 | 101.47 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1130_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1130_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1130_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_130_csa.pdf | Document Posted | N/A | N/A | 5/22/2024 | 10/2/2017 | N/A | N/A | 8/7/2024 |  |  | 12/31/2024 | 12/31/2024 | 12/3/2024 | N | No
AD1-155 | Meadow Brook-Strasburg 138 kV | Foxglove Solar | VA | Frederick | In Service | APS | 75 | 75 | 37.2 | 75 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad1155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad1155_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad1155_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad1_155_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad1_155_csa.pdf | Document Posted | N/A | N/A | 9/11/2024 | 10/2/2017 | N/A | N/A | 9/23/2024 |  |  | 6/30/2024 | 6/30/2024 | 10/19/2024 | N | No
AD2-001 | Grangston 138 kV | Big Sandy Peaker Plant | WV | Wayne | In Service | AEP | 318 | 18 | 18 | 18 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/2/2017 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 10/2/2020 | N | No
AD2-009 | McConnellsburg 138 kV | Great Cover Solar LLC | PA | Fulton | In Service | APS | 70 | 70 | 48.1 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2009_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2009_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2009_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_009_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_009_csa.pdf | Document Posted | N/A | N/A | 11/21/2023 | 11/7/2017 | N/A | N/A | 12/8/2023 |  |  | 3/31/2024 | 3/31/2024 | 4/16/2024 | N | No
AD2-018 | Roseland-Cedar Grove 230kV |  | NJ | Unknown | In Service | PSEG | 0 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ad2018_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ad2018_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/ad2_018_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 | 3/12/2021 | EE | No
AD2-019 | Williams-Cedar Grove 230kV |  | NJ | Unknown | In Service | PSEG | 0 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-impact-studies/ad2019_arr-imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-facilities-studies/ad2019_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/arr-csa-studies/ad2_019_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 | 3/12/2021 | EE | No
AD2-016 | Biers Run-Circleville 138 kV | Yellowbud Solar | OH | Ross | In Service | AEP | 274 | 127 | 62.5 | 127 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2016_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2016_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2016_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_016_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_016_csa.pdf | Document Posted | N/A | N/A | 10/24/2022 | 11/16/2017 | N/A | N/A | 12/21/2022 |  |  | 12/15/2022 | 12/15/2022 | 12/21/2022 | N | No
AD2-021 | Elko 34.5 kV | Briel Farm Solar | VA | Henrico | In Service | Dominion | 20 | 1.2 | 1.3 | 1.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2021_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2021_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2021_wmpa.pdf | Not Required | N/A | N/A |  | 11/29/2017 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 | 12/30/2020 | 12/21/2020 | N | No
AD2-026 | East Flemington-Frenchtown 34.5 kV II | Quakertown Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2026_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_026_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2017 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 5/3/2019 | N | No
AD2-027 | Camden Switch 26 kV | Taylors Lane Solar | NJ | Burlington | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2027_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2027_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2027_wmpa.pdf | Not Required | N/A | N/A |  | 12/7/2017 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 3/22/2019 | N | No
AD2-030 | Wan 34.5 kV | Gloucester Solar | VA | Gloucester | In Service | Dominion | 19.8 | 19.8 | 13.1 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2030_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2030_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2030_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2030_wmpa.pdf | Not Required | N/A | N/A |  | 12/13/2017 | N/A | N/A |  |  |  | 5/21/2019 | 5/21/2019 | 3/22/2019 | N | No
AD2-035 | Ontelaunee 230 kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 630 | 38.9 | 14 | 38.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2035_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ad2_035_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/2018 | N/A | N/A |  |  |  | 12/1/2019 |  | 12/1/2019 | N | No
AD2-042 | Camden Switch 26 kV II | Pennsauken Solar II | NJ | Camden | In Service | PSEG | 13.2 | 13.2 | 5 | 13.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2042_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2042_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2042_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2042_wmpa.pdf | Not Required | N/A | N/A |  | 1/29/2018 | N/A | N/A | 10/4/2019 |  |  | 9/10/2019 | 9/10/2019 | 10/4/2019 | N | No
AD2-044 | Northern Neck 34.5 kV | Gardy's Mill Solar | VA | Westmoreland | In Service | Dominion | 14 | 3.2 | 1.5 | 3.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2044_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2044_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2044_wmpa.pdf | Not Required | N/A | N/A |  | 1/29/2018 | N/A | N/A | 10/15/2020 |  |  | 12/30/2020 |  | 12/21/2020 | N | No
AD2-058 | St. Barnabas 13 kV | Spectrum Solar | MD | Prince George's | In Service | PEPCO | 5.6 | 5.6 | 2.38 | 5.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2058_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2058_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2058_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2058_wmpa.pdf | Not Required | N/A | N/A |  | 2/21/2018 | N/A | N/A | 12/30/2023 |  |  | 6/3/2022 | 6/3/2022 | 1/2/2024 | N | No
AD2-065 | Atco 12 kV | Kettle Run | NJ | Burlington | In Service | AEC | 2.57 | 2.57 | 1.08 | 2.57 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2065_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2065_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2065_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2065_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2018 | N/A | N/A | 9/30/2022 |  |  | 5/20/2022 | 5/20/2022 | 3/24/2023 | N | No
AD2-070 | Gilbert-Morris Park 34.5kV | Milford Solar Farm | NJ | Hunterdon | In Service | JCPL | 7.5 | 7.5 | 3.2 | 7.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2070_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2070_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_070_csa.pdf | Document Posted | N/A | N/A |  | 3/12/2018 | N/A | N/A | 9/18/2019 |  |  | 6/1/2020 | 6/1/2020 | 9/18/2019 | N | No
AD2-073 | Sanders DP 230 kV | Woodbine Road Solar | VA | Westmoreland | In Service | Dominion | 19.92 | 19.92 | 13.32 | 19.92 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2073_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2073_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2073_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ad2073_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2073_wmpa.pdf | Not Required | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 9/2/2021 | N | No
AD2-079 | Capitol Ave 34.5kV | St. Joseph County, Indiana | IN | St. Joseph | In Service | AEP | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2079_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2079_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2079_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_079_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2018 | N/A | N/A |  |  |  | 3/31/2021 | 3/31/2021 | 3/16/2021 | N | No
AD2-086 | Hardin Switch 345 kV | Hardin Energy Center – Phase 3 | OH | Hardin | In Service | AEP | 230 | 230 | 138 | 230 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2086_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2086_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_086_csa.pdf | Document Posted | N/A | N/A | 10/25/2024 | 3/21/2018 | N/A | N/A | 12/7/2024 |  |  | 12/31/2025 | 12/31/2025 | 2/21/2025 | N | No
AD2-097 | Spruance NUG 230kV | Spruance Operating Services LLC | VA | Henrico | In Service | Dominion | 66 | 66 | 11 | 66 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2097_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2097_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_097_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2018 | N/A | N/A | 8/1/2019 |  |  | 5/1/2019 | 5/1/2019 | 10/1/2019 | N | No
AD2-108 | Springdale CT II 138kV | Springdale | PA | Allegheny | In Service | APS | 96 | 0 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2108_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2108_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/ad2_108_gia.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_108_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 | 7/10/2019 | N | No
AD2-110 | Guilford 138kV | Chambersburg Energy, LLC | PA | Franklin | In Service | APS | 100 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2110_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 9/30/2022 | 9/30/2022 | 9/14/2020 | N | No
AD2-112 | Springdale CC II 138kV | Springdale | PA | Allegheny | In Service | APS | 610 | 20 | 50.4 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2112_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2112_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 | 11/21/2023 | N | No
AD2-113 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 788.1 | 68.1 | 60.6 | 70 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2113_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2113_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_113_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2018 | N/A | N/A | 6/1/2023 |  |  | 6/1/2023 | 6/1/2023 | 4/27/2022 | N | No
AD2-115 | Lyons-Moselem 69kV | Lyons Solar | PA | Berks | In Service | ME | 20 | 20 | 13 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2115_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2115_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_115_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_115_csa.pdf | Document Posted | N/A | N/A | 8/25/2023 | 3/24/2018 | N/A | N/A | 11/29/2023 |  |  | 8/31/2023 | 8/31/2023 | 12/1/2023 | N | No
AD2-116 | Hokes-Grantley 69 kV | Cottontail Solar 2 | PA | York | In Service | ME | 20 | 20 | 13 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2116_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2116_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2116_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_116_csa.pdf | Document Posted | N/A | N/A | 3/23/2023 | 3/24/2018 | N/A | N/A | 12/1/2023 |  |  | 12/31/2023 | 12/31/2023 | 3/1/2024 | N | No
AD2-133 | Eagle Valley 115kV | Sandy Ridge | PA | Centre | In Service | PENELEC | 135.4 | 85.4 | 15.3 | 135.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_133_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2018 | N/A | N/A | 7/1/2023 |  |  | 7/31/2023 | 7/31/2023 | 9/16/2023 | N | No
AD2-160 | Hickory-Moyock 230kV | Oak Trail Solar | NC | Currituck | In Service | Dominion | 50 | 50 | 32.8 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2160_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2160_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2160_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_160_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_160_csa.pdf | Document Posted | N/A | N/A |  | 3/26/2018 | N/A | N/A | 6/9/2023 |  |  | 7/1/2023 | 7/1/2023 | 7/5/2023 | N | No
AD2-163 | Broadview-Tangy 138 kV | Madison Fields Solar Project | OH | Madison | In Service | ATSI | 180 | 180 | 120.7 | 180 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2163_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2163_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2163_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_163_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_163_csa.pdf | Document Posted | N/A | N/A | 10/26/2023 | 3/27/2018 | N/A | N/A | 10/30/2023 |  |  | 12/31/2023 | 12/31/2023 | 1/23/2024 | N | No
AD2-166 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | In Service | ME | 825 | 75 | 89.8 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2166_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2166_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_166_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2018 | N/A | N/A |  |  |  | 4/30/2022 | 4/30/2022 | 4/28/2022 | N | No
AD2-167 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 1090 | 90 | 52 | 90 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2167_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2167_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_167_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2018 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 | 7/27/2017 | N | No
AD2-172 | Lena 138kV | High Point Solar | IL | Stephenson | In Service | ComEd | 50 | 50 | 21 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2172_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2172_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2172_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_172_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_172_csa.pdf | Document Posted | N/A | N/A | 5/1/2022 | 3/29/2018 | N/A | N/A |  |  |  | 2/28/2024 | 2/28/2024 | 11/30/2023 | N | No
AD2-180 | Elk Garden-Parr Run 138kV | Black Rock Wind | WV | Mineral | In Service | APS | 110 | 110 | 15.08 | 110 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2180_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2180_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_180_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_180_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2018 | N/A | N/A |  |  |  | 12/15/2021 | 12/15/2021 | 10/25/2021 | N | No
AD2-189 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 1875 | 225 | 186 | 225 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2189_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_189_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_189_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 3/30/2018 | N/A | N/A | 9/17/2022 |  |  | 12/31/2022 | 12/31/2022 | 2/27/2023 | N | No
AD2-202 | Clover-Sedge Hill 230kV | Foxhound Solar | VA | Halifax | In Service | Dominion | 83 | 18.8 | 12.8 | 18.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2202_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2202_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2202_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_202_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_202_csa.pdf | Document Posted | N/A | N/A | 2/1/2024 | 3/31/2018 | N/A | N/A | 2/15/2024 |  |  | 5/31/2024 | 5/31/2024 | 4/24/2024 | N | No
AD2-213 | East Flemington-Lebanon 34.5 kV | Justin Court Energy Storage | NJ | Hunterdon | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2213_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2213_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ad2213_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_213_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ad2_213_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 4/1/2018 | N/A | N/A | 12/18/2023 |  |  | 7/14/2023 | 7/14/2023 | 2/15/2024 | N | No
AE1-001 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 1820.8 | 28.1 | 7.1 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1001_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_001_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 4/2/2018 | N/A | N/A |  |  |  | 1/13/2023 | 1/13/2023 |  | N | No
AD2-205 | Byllesby 69 kV | Buck & Byllesby Hydro Project | VA | Carroll | In Service | AEP | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ad2205_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ad2205_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ad2_205_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/13/2018 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 1/31/2019 | N | No
AE1-021 | Gavin #2 765 kV | Gavin Unit No. 2 | OH | Gallia | In Service | AEP | 1367 | 11 | 11 | 11 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1021_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_021_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/24/2018 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 | 6/19/2021 | N | No
AE1-035 | Earleys 230 kV | Aulander Holloman Solar Park | NC | Hertford | In Service | Dominion | 99.9 | 19.9 | 13.4 | 19.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1035_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_035_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/8/2018 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 2/24/2020 | N | No
AE1-036 | Red Oak 230 kV | Red Oak | NJ | Middlesex | In Service | JCPL | 776 | 0 | 9 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1036_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_036_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/13/2018 | N/A | N/A |  |  |  | 7/1/2018 |  | 2/8/2019 | N | No
AE1-039 | West Street (Orchard Hills) 12.47 kV | Orchard Hills Sanitary Landfill | MI | Berrien | In Service | AEP | 4 | 0.8 | 0.8 | 0.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/22/2018 | N/A | N/A |  |  |  | 9/30/2020 | 9/30/2020 | 10/1/2019 | N | No
AE1-041 | Edison 4kV | Highland Park | NJ | Middlesex | In Service | PSEG | 1.1 | 1.1 | 0.2 | 0.6 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1041_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1041_wmpa.pdf | Not Required | N/A | N/A |  | 6/25/2018 | N/A | N/A | 12/19/2019 |  |  | 1/31/2020 | 1/31/2020 | 12/30/2019 | N | No
AE1-040 | Greenfield 69 kV | Fayette Solar | OH | Fayette | In Service | Dayton | 48 | 48 | 31.6 | 48 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1040_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1040_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1040_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_040_csa.pdf | Document Posted | N/A | N/A | 10/18/2024 | 6/26/2018 | N/A | N/A | 11/23/2024 |  |  | 5/31/2024 | 5/31/2024 | 1/2/2025 | N | No
AE1-060 | Kittatinny-Newton 34.5 kV | VESI – Andover Energy Storage | NJ | Sussex | In Service | JCPL | 19.8 | 19.8 | 0 | 19.8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_060_csa.pdf | Document Posted | N/A | N/A | 9/16/2022 | 7/26/2018 | N/A | N/A | 10/3/2022 |  |  | 9/30/2022 | 9/30/2022 | 6/17/2023 | N | No
AE1-071 | Shade Gap-Roxbury 115 kV | Aspen Road Solar | PA | Franklin | In Service | PENELEC | 100.1 | 100.1 | 62.1 | 100.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1071_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1071_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_071_csa.pdf | Document Posted | N/A | N/A | 12/20/2024 | 7/31/2018 | N/A | N/A | 2/18/2025 |  |  | 3/8/2025 | 3/8/2025 | 2/28/2025 | N | No
AE1-075 | Powhatan 34.5 kV | Powhatan Solar I, LLC | VA | Powhatan | In Service | Dominion | 18 | 18 | 12 | 18 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1075_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1075_wmpa.pdf | Not Required | N/A | N/A | 1/19/2024 | 8/2/2018 | N/A | N/A | 12/4/2024 |  |  | 10/31/2024 | 10/31/2024 | 1/31/2025 | N | No
AE1-081 | Landing 12.47 kV | Durban Ave Solar | NJ | Sussex | In Service | JCPL | 1.25 | 1.25 | 0.52 | 1.25 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1081_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1081_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1081_wmpa.pdf | Not Required | N/A | N/A |  | 8/27/2018 | N/A | N/A | 6/30/2020 |  |  | 6/30/2021 | 6/30/2021 | 9/25/2020 | N | No
AE1-086 | Grassy Falls 138 kV | Beech Ridge Wind Farm | WV | Greenbrier | In Service | APS | 55.6 | 5 | 0.6 | 5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1086_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1086_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_086_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2018 | N/A | N/A | 5/31/2020 |  |  | 5/31/2020 | 5/31/2020 | 3/14/2020 | N | No
AE1-090 | Hardin Switch 345 kV | Hardin Energy Center - Phase 3 | OH | Hardin | In Service | AEP | 250 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1090_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1090_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1090_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_090_csa.pdf | Document Posted | N/A | N/A | 10/25/2024 | 9/1/2018 | N/A | N/A | 12/7/2024 |  |  | 12/31/2025 | 12/31/2025 | 2/21/2025 | N | No
AE1-101 | McConnellsburg-Texas Eastern 138 kV | Great Cove Solar II | PA | Franklin | In Service | APS | 150 | 150 | 100.5 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1101_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1101_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1101_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_101_csa.pdf | Document Posted | N/A | N/A | 12/10/2023 | 9/2/2018 | N/A | N/A | 12/13/2023 |  |  | 3/31/2024 | 3/31/2024 | 6/6/2024 | N | No
AE1-100 | Axton 138 kV | Caden Energix Axton | VA | Henry | In Service | AEP | 66 | 66 | 41.9 | 66 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1100_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1100_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1100_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_100_csa.pdf | Document Posted | N/A | N/A | 7/1/2023 | 9/3/2018 | N/A | N/A | 12/26/2023 |  |  | 12/31/2023 | 12/31/2023 | 2/22/2024 | N | No
AE1-109 | Frenchs Mill 34 kV | Capon Bridge Solar | WV | Hampshire | In Service | APS | 20 | 20 | 8.7 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1109_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1109_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1109_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1109_wmpa.pdf | Not Required | N/A | N/A | 6/20/2024 | 9/15/2018 | N/A | N/A | 7/10/2024 |  |  | 7/31/2024 | 7/31/2024 | 7/25/2024 | N | No
AE1-120 | Hillcrest 138 kV | Hillcrest Solar I | OH | Brown | In Service | DEOK | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1120_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_120_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/19/2020 | 9/17/2018 | N/A | N/A | 11/15/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/18/2020 | N | No
AE1-123 | Emlenton 34.5 kV | Clarion Boards | PA | Clarion | In Service | PENELEC | 18 | 18 | 18 | 18 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1123_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1123_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1123_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1123_wmpa.pdf | Not Required | N/A | N/A |  | 9/20/2018 | N/A | N/A | 10/2/2023 |  |  | 11/10/2023 | 11/10/2023 | 11/3/2023 | N | No
AE1-134 | Nelson 345 kV | Nelson Energy Center | IL | Lee | In Service | ComEd | 609 | 9 | 24.4 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_134_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/30/2023 | 6/30/2023 | 5/12/2023 | N | No
AE1-142 | Manitou-Pleasant Plains 34.5 kV | Toms River Solar | NJ | Ocean | In Service | JCPL | 20 | 20 | 8.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1142_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1142_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_142_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A | 2/15/2021 |  |  | 2/28/2021 | 2/28/2021 | 3/12/2021 | N | No
AE1-162 | Smithfield 34.5 kV | Solidago Solar | VA | Isle of Wight | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1162_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1162_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1162_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1162_wmpa.pdf | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A | 6/20/2023 |  |  | 12/31/2023 | 12/31/2023 | 8/1/2023 | N | No
AE1-175 | Light Foot 34.5 kV | Lightfoot 34.5 kV II | VA | James City | In Service | Dominion | 19.9 | 19.9 | 13.3 | 19.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1175_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae1175_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1175_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 11/15/2021 | 11/15/2021 | 5/10/2022 | N | No
AE1-176 | Roanoke-Vinton 12 kV (Niagara Hydro) | Niagara Power Plant Dam | VA | Roanoke | In Service | AEP | 2.4 | 2.4 | 2.4 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1176_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1176_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_176_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 5/23/2020 | N | No
AE1-178 | Wolf Hills 138 kV | Wolf Hills Energy Plant | VA | Washington | In Service | AEP | 294 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_178_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 12/21/2021 | 12/21/2021 | 5/25/2021 | N | No
AE1-155 | Garner-Northern Neck 115 kV | Bookers Mill Solar | VA | City of Richmond | In Service | Dominion | 127 | 127 | 76.2 | 127 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1155_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1155_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_155_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_155_csa.pdf | Document Posted | N/A | N/A | 10/6/2023 | 9/26/2018 | N/A | N/A | 3/12/2024 |  |  | 5/14/2024 | 5/14/2024 | 12/18/2024 | N | No
AE1-196 | Hokes-Jackson 69 kV II | Cottontail Solar 8 | PA | York | In Service | ME | 20 | 20 | 12.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1196_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1196_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_196_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_196_csa.pdf | Document Posted | N/A | N/A | 3/9/2023 | 9/28/2018 | N/A | N/A | 2/29/2024 |  |  | 12/31/2023 | 12/31/2023 | 4/24/2024 | N | No
AE1-221 | North Wales 34.5 kV | West Point Cogeneration Facility | PA | Montgomery | In Service | PECO | 38 | 0 | 14 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1221_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1221_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_221_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 | 4/21/2020 | N | No
AE1-185 | Hokes-Jackson 69 kV | Cottontail Solar 1 | PA | York | In Service | ME | 20 | 20 | 12.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae1185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae1185_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae1185_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae1_185_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae1_185_csa.pdf | Document Posted | N/A | N/A | 3/9/2023 | 9/30/2018 | N/A | N/A | 7/22/2024 |  |  | 7/31/2024 | 7/31/2024 | 8/12/2024 | N | No
AE2-006 | Twittys Creek 34.5 kV | Twittys Creek Solar | VA | Charlotte | In Service | Dominion | 13.75 | 0 | 2.9 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2006_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2006_wmpa.pdf | Not Required | N/A | N/A |  | 10/8/2018 | N/A | N/A | 12/8/2020 |  |  | 12/31/2020 | 12/31/2020 | 12/8/2020 | N | No
AE2-010 | Paper Tap 69 kV | Jericho | PA | Delaware | In Service | PECO | 29 | 29 | 3 | 29 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2010_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2018 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 8/12/2020 | N | No
AE2-035 | Lena 138 kV | High Point II Solar | IL | Stephenson | In Service | ComEd | 100 | 50 | 21 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2035_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2035_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2035_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_035_csa.pdf | Document Posted | N/A | N/A | 5/1/2022 | 1/16/2019 | N/A | N/A |  |  |  | 2/28/2024 | 2/28/2024 | 11/30/2023 | N | No
AE2-054 | Warfordsburg 34 kV | Blairs Valley | PA | Franklin | In Service | APS | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2054_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2054_wmpa.pdf | Not Required | N/A | N/A | 10/21/2024 | 2/2/2019 | N/A | N/A | 12/12/2024 |  |  | 11/30/2024 | 11/30/2024 | 1/30/2025 | N | No
AE2-061 | Rock Springs 500 kV | Rock Springs Unit #1 and Unit #2 | MD | Cecil | In Service | Essential Power | 394 | 0 | 7 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2061_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_061_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/4/2019 | N/A | N/A |  |  |  | 8/23/2019 | 8/23/2019 | 8/12/2019 | N | No
AE2-062 | Romeoville 12 kV | Magid Glove & Safety Mfg. Co | IL | Will | In Service | ComEd | 0.98 | 0.98 | 0 | 0.98 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2062_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2062_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2062_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2062_wmpa.pdf | Not Required | N/A | N/A |  | 2/5/2019 | N/A | N/A | 3/31/2021 |  |  | 3/31/2021 | 3/31/2021 | 4/8/2021 | Y | No
AE2-065 | Romeoville 12 kV | Kinsley 2 Deptford Solar | NJ | Gloucester | In Service | PSEG | 6.8 | 1.8 | 0.76 | 1.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2065_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_065_csa.pdf | Document Posted | N/A | N/A |  | 2/6/2019 | N/A | N/A | 6/1/2023 |  |  | 8/31/2020 | 8/31/2020 | 9/19/2020 | N | No
AE2-059 | Derry Tap-Derry Bus 69 kV | Cottontail Solar 4 aka East Chilli Solar | PA | Northumberland | In Service | PPL | 20 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2059_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2059_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2059_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_059_csa.pdf | Document Posted | N/A | N/A | 2/2/2024 | 2/7/2019 | N/A | N/A | 8/11/2024 |  |  | 5/31/2024 | 5/31/2024 | 8/20/2024 | N | No
AE2-060 | Mifflintown Bus-Mifflintown Tap 69 kV | Cottontail Solar 5 aka Walker Solar | PA | Juniata | In Service | PPL | 20 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2060_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2060_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2060_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_060_csa.pdf | Document Posted | N/A | N/A | 10/26/2023 | 2/7/2019 | N/A | N/A | 12/8/2023 |  |  | 12/1/2023 | 12/1/2023 | 12/12/2023 | N | No
AE2-064 | Beaverbrook 13 kV | Kinsley 2 Beaverbrook Solar | NJ | Gloucester | In Service | PSEG | 5.8 | 2 | 0.85 | 5.13 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2064_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_064_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2019 | N/A | N/A | 1/30/2024 |  |  | 8/31/2020 | 8/31/2020 |  | N | No
AE2-072 | East Leipsic-Richland 138 kV | Powell Creek Solar | OH | Putnam | In Service | AEP | 150 | 150 | 90 | 150 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2072_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2072_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2072_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_072_csa.pdf | Document Posted | N/A | N/A | 1/23/2025 | 2/15/2019 | N/A | N/A | 3/17/2025 |  |  | 6/2/2025 | 6/2/2025 | 4/30/2025 | N | No
AE2-071 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | In Service | EKPC | 35 | 35 | 21 | 35 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2071_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2071_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2071_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_071_csa.pdf | Document Posted | N/A | N/A | 4/1/2024 | 2/19/2019 | N/A | N/A | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 | 6/7/2024 | N | No
AE2-148 | Beatty-Greene 345 kV | Fox Squirrel Solar | OH | Madison | In Service | AEP | 577 | 577 | 397.3 | 577 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2148_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2148_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_148_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_148_csa.pdf | Document Posted | N/A | N/A |  | 2/22/2019 | N/A | N/A | 11/14/2023 |  |  | 11/1/2023 | 11/1/2023 | 11/1/2024 | N | No
AE2-114 | Midland 23 kV I | BE-PINE 1 Cain Road | PA | Beaver | In Service | DL | 17.1 | 17.1 | 10.26 | 17.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2114_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2114_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2114_wmpa.pdf | Not Required | N/A | N/A |  | 3/1/2019 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 | 11/20/2023 | N | No
AE2-115 | Midland 23 kV II | BE-PINE 2 Dam Road | PA | Beaver | In Service | DL | 17.1 | 17.1 | 10.26 | 17.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2115_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2115_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2115_wmpa.pdf | Not Required | N/A | N/A |  | 3/1/2019 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 | 11/5/2023 | N | No
AE2-126 | Dubois-Curwensville 34.5 kV | CL-Viaduct | PA | Clearfield | In Service | PENELEC | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2126_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_126_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_126_csa.pdf | Document Posted | N/A | N/A | 9/1/2022 | 3/1/2019 | N/A | N/A | 3/1/2023 |  |  | 5/31/2023 | 5/31/2023 | 3/23/2023 | N | No
AE2-129 | Philipsburg-Clarence 34.5 kV | Philipsburg-Clarence 34.5 kV | PA | Clearfield | In Service | PENELEC | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2129_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2129_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2129_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2129_wmpa.pdf | Not Required | N/A | N/A | 11/1/2022 | 3/1/2019 | N/A | N/A | 3/1/2023 |  |  | 11/1/2022 | 11/1/2022 | 1/28/2023 | N | No
AE2-132 | Remington CT 230 kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 190 | 0 | 17.7 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2132_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2132_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_132_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/1/2019 | N/A | N/A |  |  |  | 5/31/2020 |  | 10/17/2019 | N | No
AE2-125 | Stahlstown-Ligonier 25 kV | Stahlstown-Ligonier 25 kV | PA | Westmoreland | In Service | APS | 13.8 | 13.8 | 8.28 | 13.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2125_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2125_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2125_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2125_wmpa.pdf | Not Required | N/A | N/A | 10/15/2024 | 3/2/2019 | N/A | N/A | 11/21/2024 |  |  | 11/15/2024 | 11/15/2024 | 12/4/2024 | N | No
AE2-133 | Penns Tap-Richfield Tie 69 kV | Penn Solar (Cottontail 6) | PA | Snyder | In Service | PPL | 20 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2133_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2133_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2133_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_133_csa.pdf | Document Posted | N/A | N/A | 1/26/2024 | 3/6/2019 | N/A | N/A | 3/22/2024 |  |  | 12/1/2023 | 12/1/2023 | 5/8/2024 | N | No
AE2-134 | Locust Grove-Paytes 115 kV | Pine Glade Solar | VA | Orange | In Service | Dominion | 62.5 | 0 | 16.5 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_134_csa.pdf | Document Posted | N/A | N/A | 5/30/2024 | 3/6/2019 | N/A | N/A | 7/19/2024 |  |  | 7/15/2024 | 7/15/2024 | 9/13/2024 | N | No
AE2-155 | Old Church 34.5 kV | Hanover Solar | VA | Hanover | In Service | Dominion | 25 | 5 | 3.5 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2155_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2155_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_155_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/15/2019 | N/A | N/A | 8/20/2020 |  |  | 12/1/2020 | 12/1/2020 | 9/23/2020 | N | No
AE2-183 | Rogers Road 500 kV | Greensville Power Station | VA | Greensville | In Service | Dominion | 1756 | 75 | 0 | 75 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2183_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_183_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 8/15/2023 | 8/15/2023 | 8/30/2023 | N | No
AE2-184 | Warren County 500 kV | Warren County Power Station | VA | Warren | In Service | Dominion | 1499 | 15 | 0 | 15 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_184_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 4/30/2021 | 4/30/2021 | 8/11/2020 | N | No
AE2-206 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | In Service | Dayton | 99 | 99 | 41.58 | 99 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2206_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2206_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2206_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_206_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_206_csa.pdf | Document Posted | N/A | N/A | 10/28/2024 | 3/20/2019 | N/A | N/A | 12/19/2024 |  |  | 1/31/2025 | 1/31/2025 | 2/5/2025 | N | No
AE2-297 | Madison-Tanners Creek 138 kV | Bellflower Solar 1 | IN | Henry | In Service | AEP | 152.5 | 152.5 | 91.5 | 152.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2297_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2297_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2297_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_297_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_297_csa.pdf | Document Posted | N/A | N/A | 11/18/2022 | 3/22/2019 | N/A | N/A | 12/2/2023 |  |  | 12/31/2024 | 12/31/2024 | 12/6/2022 | N | No
AE2-224 | Bearrock-Johnstown 230 kV | CPV Maple Hill Solar | PA | Cambria | In Service | PENELEC | 100 | 100 | 60 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2224_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2224_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2224_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_224_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_224_csa.pdf | Document Posted | N/A | N/A | 3/24/2023 | 3/23/2019 | N/A | N/A | 10/12/2023 |  |  | 11/17/2023 | 11/17/2023 | 11/28/2023 | N | No
AE2-230 | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 70 | 70 | 42 | 70 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2230_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2230_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2230_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_230_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_230_csa.pdf | Document Posted | N/A | N/A | 10/20/2024 | 3/24/2019 | N/A | N/A | 11/17/2024 |  |  | 7/1/2024 | 7/1/2024 | 12/27/2024 | N | No
AE2-253 | Hickory-Moyock 230 kV | Oak Trail Solar | NC | Currituck | In Service | Dominion | 100 | 50 | 34.5 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2253_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2253_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2253_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_253_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_253_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2019 | N/A | N/A | 6/9/2023 |  |  | 7/15/2023 | 7/15/2023 | 7/5/2023 | N | No
AE2-254 | Garrard County-Tommy-Gooch 69 kV | Turkey Creek Solar | KY | Garrard | In Service | EKPC | 50 | 50 | 30 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2254_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2254_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2254_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_254_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_254_csa.pdf | Document Posted | N/A | N/A | 9/22/2020 | 3/26/2019 | N/A | N/A | 9/23/2022 |  |  | 12/31/2022 |  | 10/28/2022 | N | No
AE2-272 | Woodstown 12 kV | Pilesgrove Solar | NJ | Salem | In Service | AEC | 19.9 |  | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2272_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2272_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_272_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 | 9/17/2019 | N | No
AE2-273 | Siegfried-Hauto 69KV | PA Solar Park | PA | Carbon | In Service | PPL | 20 | 0 | 0.4 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2273_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2273_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_273_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_273_csa.pdf | Document Posted | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AE2-274 | Siegfried-Hauto 69 kV | PA Solar Park | PA | Carbon | In Service | PPL | 20 | 0 | 0.8 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2274_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2274_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_274_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_274_csa.pdf | Document Posted | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AE2-315 | Yankee Tap 69 kV | Yankee 1-7 | OH | Montgomery | In Service | Dayton | 124 | 23.5 | 23.5 | 23.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2315_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2315_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2315_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_315_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_315_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 11/30/2022 | 11/30/2022 | 4/19/2022 | N | No
AE2-346 | Ahoskie 34.5 kV | Colice Hall Solar | NC | Hertford | In Service | Dominion | 17 | 12 | 8.4 | 12 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2346_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2346_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_346_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_346_csa.pdf | Document Posted | N/A | N/A | 6/29/2023 | 3/29/2019 | N/A | N/A | 3/1/2023 |  |  | 9/15/2023 | 9/15/2023 | 7/6/2023 | N | No
AE2-282 | East Fayette 138 kV | Arche Energy Project | OH | Fulton | In Service | ATSI | 67 | 67 | 43.9 | 67 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2282_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2282_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/ae2282_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ae2_282_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2_282_csa.pdf | Document Posted | N/A | N/A | 9/7/2023 | 3/31/2019 | N/A | N/A | 10/11/2023 |  |  | 12/31/2023 | 12/31/2023 | 1/17/2024 | N | No
AE2-309 | Carlos Junction-Lonaconing 34.5 kV | Jade Meadow | MD | Allegany | In Service | APS | 19.84 | 19.84 | 11.9 | 19.84 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ae2309_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ae2309_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ae2309_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ae2309_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2019 | N/A | N/A | 1/16/2024 |  |  | 3/22/2024 | 3/22/2024 | 3/26/2024 | N | No
AF1-006 | Fairview East 34.5 kV | Erie Solar | PA | Erie | In Service | PENELEC | 20 | 20 | 12.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1006_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1006_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1006_wmpa.pdf | Not Required | N/A | N/A | 11/25/2024 | 4/2/2019 | N/A | N/A | 1/9/2025 |  |  | 12/31/2024 | 12/31/2024 | 1/29/2025 | N | No
AF1-019 | Branchville-Holiday Lakes 34.5 kV | Viridity Energy Solutions Montague Storage | NJ | Sussex | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1019_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1019_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1019_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_019_csa.pdf | Document Posted | N/A | N/A | 10/18/2024 | 4/6/2019 | N/A | N/A | 10/22/2024 |  |  | 1/31/2025 | 1/31/2025 | 12/20/2024 | N | No
AF1-021 | Bethelboro-Connellsville #1 25 kV | Dunbar Solar | PA | Fayette | In Service | APS | 14 | 14 | 8.4 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1021_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1021_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1021_wmpa.pdf | Not Required | N/A | N/A | 8/20/2024 | 4/17/2019 | N/A | N/A | 10/8/2024 |  |  | 11/29/2024 | 11/29/2024 | 10/18/2024 | N | No
AF1-022 | Lake Lynn-Uniontown 25 kV | Gans Solar Farm | PA | Fayette | In Service | APS | 14 | 14 | 8.4 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1022_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1022_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1022_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1022_wmpa.pdf | Not Required | N/A | N/A | 10/21/2024 | 4/17/2019 | N/A | N/A | 10/31/2024 |  |  | 11/29/2024 | 11/29/2024 | 12/3/2024 | N | No
AF1-023 | Atlantic-Red Bank 34 kV II | Hamilton Road Solar | NJ | Monmouth | In Service | JCPL | 20 | 0 | 8.4 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1023_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1023_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_023_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/18/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 8/6/2020 | N | No
AF1-026 | Edge Road Battery Storage (CIRs) | Alpha Battery Storage Facility | NJ | Warren | In Service | JCPL | 20 | 0 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1026_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/6/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/21/2020 | N | No
AF1-027 | Plumsted 537 Energy Storage (CIRs) | Plumsted Energy Storage Facility | NJ | Ocean | In Service | JCPL | 20 | 0 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1027_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/6/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/21/2020 | N | No
AF1-032 | Suffolk 34.5 kV | Stratford Solar Center | VA | City of Suffolk | In Service | Dominion | 15 | 15 | 9.8 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1032_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1032_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1032_wmpa.pdf | Not Required | N/A | N/A |  | 5/18/2019 | N/A | N/A | 2/28/2023 |  |  | 2/28/2023 | 2/28/2023 | 1/4/2023 | N | No
AF1-039 | Listonburg-Highpoint 24.9 kV | Listonburg Solar | PA | Somerset | In Service | PENELEC | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1039_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1039_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1039_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1039_wmpa.pdf | Not Required | N/A | N/A | 10/17/2024 | 6/7/2019 | N/A | N/A | 12/9/2024 |  |  | 10/31/2024 | 10/31/2024 | 12/26/2024 | N | No
AF1-041 | Absecon 12.47 kV | Pear Street Solar | NJ | Atlantic | In Service | AEC | 2.4 | 2.4 | 0 | 2.4 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1041_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1041_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1041_wmpa.pdf | Not Required | N/A | N/A |  | 6/18/2019 | N/A | N/A |  |  |  | 3/3/2022 | 3/3/2022 | 5/8/2020 | N | No
AF1-058 | Welco 34.5 kV | Watlington Solar | VA | Halifax | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1058_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1058_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1058_wmpa.pdf | Not Required | N/A | N/A |  | 8/1/2019 | N/A | N/A | 3/31/2023 |  |  | 11/30/2022 | 11/30/2022 | 3/8/2023 | N | No
AF1-078 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | In Service | Dayton | 144 | 45 | 18.9 | 43 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1078_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1078_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/28/2024 | 8/27/2019 | N/A | N/A | 12/19/2024 |  |  | 1/31/2025 | 1/31/2025 | 2/5/2025 | N | No
AF1-120 | East Fayette 2 138 kV | Arche Energy Project | OH | Fulton | In Service | ATSI | 107 | 40 | 26.6 | 40 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1120_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1120_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_120_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_120_csa.pdf | Document Posted | N/A | N/A | 9/7/2023 | 8/31/2019 | N/A | N/A | 10/11/2023 |  |  | 12/31/2023 | 12/31/2023 | 1/17/2024 | N | No
AF1-102 | Gans 138 kV II | Gans CT | PA | Fayette | In Service | APS | 96 | 0 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1102_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_102_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/6/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 3/11/2021 | N | No
AF1-150 | Midfield 22.9 kV | Pittsburgh International Airport | PA | Allegheny | In Service | DL | 14.4 | 14.4 | 4.28 | 14.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1150_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1150_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1150_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1150_wmpa.pdf | Not Required | N/A | N/A | 4/1/2021 | 9/19/2019 | N/A | N/A | 4/1/2021 |  |  | 9/1/2021 | 9/1/2021 | 10/28/2021 | N | No
AF1-177 | Warren 115 kV | Warren Generating Station | PA | Warren | In Service | PENELEC | 62 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1177_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1177_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_177_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 7/1/2020 | N | No
AF1-178 | Tolna 2 115 kV | Tolna Unit 2 | PA | York | In Service | ME | 21.5 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_178_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-179 | Tolna 1 115 kV | Tolna Unit 1 | PA | York | In Service | ME | 21 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1179_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_179_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-180 | Titus 4 & 5 69 kV | Titus Generating Station (Titus CT 4 and Titus CT 5) | PA | Berks | In Service | ME | 38.7 | 2 | 2 | 2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1180_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_180_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-181 | Shawville 3 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 593 | 3 | 3 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1181_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1181_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-182 | Shawville 4 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 597 | 4 | 4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1182_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1182_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_182_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-183 | Shawville 1 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 598 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1183_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1183_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_183_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-184 | Shawnee 1 34.5 kv | Shawnee Generating Station (CT 1) | PA | Monroe | In Service | ME | 21 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_184_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-185 | Sayreville 1-2-3 230 kV | Sayreville Facility (Raritan River) | NJ | Middlesex | In Service | JCPL | 171.7 | 0 | 5.5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-186 | Portland 5 230 kV | Portland Station Unit 5 | PA | Northampton | In Service | ME | 147.5 | 6.5 | 6.5 | 6.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1186_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1186_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_186_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-187 | Portland 3 & 4 115 kV | Portland Station Unit 3 and Unit 4 | PA | Northampton | In Service | ME | 39.8 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1187_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1187_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_187_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-188 | Orrtanna 115 kV | Orrtanna Station Unit C1 | PA | Adams | In Service | ME | 27 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1188_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1188_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af1_188_gia.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-189 | Niles CT A 23 kV | Niles A CT | OH | Trumbull | In Service | ATSI | 26.1 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1189_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1189_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_189_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-190 | New Castle 4 69 kV | New Castle Generating Station | PA | Lawrence | In Service | ATSI | 93 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1190_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1190_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_190_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-191 | New Castle 5 138 kV | New Castle Generating Station | PA | Lawrence | In Service | ATSI | 145 | 4 | 4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1191_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1191_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_191_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-192 | Mountain 2 115 kV | Mountain Station Unit C2 | PA | Cumberland | In Service | ME | 28 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1192_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1192_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_192_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-193 | Hunterstown 115 kV | Hunterstown CT Facility | PA | Adams | In Service | ME | 65 | 4 | 4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1193_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1193_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_193_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-194 | Hamilton CT1 115 kV | Hamilton Station | PA | York | In Service | ME | 27 | 1 | 1 | 1 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1194_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1194_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_194_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-195 | Gilbert CT9 230 kV | Gilbert Station Unit 9 | NJ | Hunterdon | In Service | JCPL | 168 | 0 | 1 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1195_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1195_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_195_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-196 | Gilbert CT 5-6-7 230 kV | Gilbert Station 4x1 Combined Cycle (Unit 4, Unit 5, Unit 6, Unit 7, and Unit 8) | NJ | Hunterdon | In Service | JCPL | 302.5 | 0 | 14.5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1196_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1196_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_196_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-198 | Blossburg #1 CT 34.5 kV | Blossburg Station Unit 1 | PA | Tioga | In Service | PENELEC | 22.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1198_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1198_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_198_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2019 | N/A | N/A | 7/24/2023 |  |  | 9/30/2023 | 9/30/2023 | 7/1/2020 | N | No
AF1-215 | Olive-Reynolds 345 kV | Mammoth North Solar Project | IN | Starke | In Service | AEP | 300 | 300 | 180 | 300 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1215_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1215_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1215_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_215_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_215_csa.pdf | Document Posted | N/A | N/A | 8/20/2024 | 9/28/2019 | N/A | N/A | 10/14/2024 |  |  | 7/31/2024 | 7/31/2024 | 11/8/2024 | N | No
AF1-203 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | In Service | EKPC | 55 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1203_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1203_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1203_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_203_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_203_csa.pdf | Document Posted | N/A | N/A | 4/15/2024 | 9/30/2019 | N/A | N/A | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 | 6/7/2024 | N | No
AF1-227 | Marysville – Gunn Road 345 kV | Union Solar | OH | Union | In Service | AEP | 325 | 325 | 195 | 325 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1227_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1227_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1227_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_227_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_227_csa.pdf | Document Posted | N/A | N/A | 4/9/2024 | 9/30/2019 | N/A | N/A | 5/14/2024 |  |  | 12/31/2024 | 12/31/2024 | 11/15/2024 | N | No
AF1-248 | Northern Neck 34.5 kV | Gardy’s Mill Solar | VA | Westmoreland | In Service | Dominion | 14 | 0 | 2.1 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1248_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1248_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1248_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1248_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A | 6/1/2023 |  |  | 12/30/2020 | 12/30/2020 | 6/1/2023 | N | No
AF1-257 | Hawks 2 12 kV |  | NJ | Hunterdon | In Service | JCPL | 3 | 0 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1257_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1257_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_257_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 5/10/2021 | N | No
AF1-258 | Rockawalkin 69 kV | Hebron Solar | MD | Wicomico | In Service | DPL | 15 | 0 | 3.2 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1258_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1258_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1258_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1258_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 11/5/2020 | N | No
AF1-259 | Price 25 kV | Church Hill Solar | MD | Queen Anne's | In Service | DPL | 6 | 0 | 0.8 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1259_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1259_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_259_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/10/2020 | N | No
AF1-260 | Allenwood-Larrabee 2 34.5 kV | Lakewood-Farmingdale Road Solar Farm | NJ | Monmouth | In Service | JCPL | 7 | 0 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1260_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1260_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_260_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/8/2020 | N | No
AF1-261 | Burlington 26 kV | North American Solar | NJ | Burlington | In Service | PSEG | 7 | 0 | 0.9 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1261_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1261_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_261_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 6/1/2021 | N | No
AF1-262 | Upper Pittsgrove 12 kV | Pittsgrove Solar | NJ | Salem | In Service | AEC | 2 | 0 | 0.9 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1262_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1262_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_262_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 9/15/2022 | N | No
AF1-264 | Runnemede 13 kV | Owens Corning Solar | NJ | Gloucester | In Service | PSEG | 3 | 0 | 1.3 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1264_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1264_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_264_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/1/2021 | 9/30/2019 | N/A | N/A | 5/15/2021 |  |  | 9/30/2023 | 9/30/2023 | 6/1/2021 | N | No
AF1-299 | Otter Point 34.5 kV I | Fairview Farms II | MD | Harford | In Service | BGE | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1299_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1299_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1299_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1299_wmpa.pdf | Not Required | N/A | N/A | 12/11/2024 | 9/30/2019 | N/A | N/A | 2/13/2025 |  |  | 12/30/2024 | 12/30/2024 | 5/1/2025 | N | No
AF1-291A | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 80 | 10 | 6 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1291a_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1291a_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1291a_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_291a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_291a_csa.pdf | Document Posted | N/A | N/A | 10/20/2024 | 10/1/2019 | N/A | N/A | 11/17/2024 |  |  | 7/1/2024 | 7/1/2024 | 12/27/2024 | N | No
AF1-249 | Nickel 12.47 kV | Nickel Solar | OH | Warren | In Service | DEOK | 19.92 | 19.92 | 14 | 19.92 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1249_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1249_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af1249_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1249_wmpa.pdf | Not Required | N/A | N/A | 10/28/2024 | 10/2/2019 | N/A | N/A | 10/28/2024 |  |  | 10/18/2024 | 10/18/2024 | 12/5/2024 | N | No
AF1-290 | Feagans Mill-Millville 138 kV | Blake Solar | WV | Jefferson | In Service | APS | 80 | 80 | 40.4 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af1290_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af1290_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af1290_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af1_290_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af1_290_csa.pdf | Document Posted | N/A | N/A | 11/17/2023 | 10/5/2019 | N/A | N/A | 11/28/2023 |  |  | 4/15/2024 | 4/15/2024 | 3/6/2024 | N | No
AF2-044 | Highland-Sammis and Highland-Mansfield 345 kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 940 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/10/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 10/20/2020 | N | No
AF2-043 | Suffolk 34.5 kV | Pleasant Hill Solar | VA | City of Suffolk | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2043_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2043_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2043_wmpa.pdf | Not Required | N/A | N/A |  | 12/11/2019 | N/A | N/A | 3/31/2023 |  |  | 12/31/2022 | 12/31/2022 | 6/20/2023 | N | No
AF2-054 | Wan 34.5 kV | Camellia Solar | VA | Gloucester | In Service | Dominion | 19.9 | 19.9 | 11.94 | 19.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2054_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2054_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2054_wmpa.pdf | Not Required | N/A | N/A | 12/2/2024 | 1/11/2020 | N/A | N/A | 4/15/2025 |  |  | 8/29/2027 | 8/29/2027 | 4/12/2025 | N | No
AF2-075 | Bartonsville-Meadow Brook 138 kV III | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 130 | 50 | 30 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2075_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2075_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2075_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_075_csa.pdf | Document Posted | N/A | N/A | 10/20/2024 | 2/1/2020 | N/A | N/A | 11/17/2024 |  |  | 7/1/2024 | 7/1/2024 | 12/27/2024 | N | No
AF2-077 | White Marsh 34.5 kV | Winterberry Solar | VA | Gloucester | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2077_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2077_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2077_wmpa.pdf | Not Required | N/A | N/A |  | 2/1/2020 | N/A | N/A | 6/26/2024 |  |  | 8/14/2024 | 8/14/2024 | 6/4/2024 | N | No
AF2-085 | Midlothian 34.5 kV | Dry Bridge Energy Center | VA | Chesterfield | In Service | Dominion | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2085_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2085_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2085_wmpa.pdf | Not Required | N/A | N/A |  | 2/4/2020 | N/A | N/A | 8/29/2023 |  |  | 12/31/2023 | 12/31/2023 | 11/21/2023 | N | No
AF2-134 | Olive-Reynolds #2 345 kV | Mammoth North Solar Project | IN | Starke | In Service | AEP | 400 | 100 | 60 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2134_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2134_imp.htm | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2134_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_134_csa.pdf | Document Posted | N/A | N/A | 8/20/2024 | 3/7/2020 | N/A | N/A | 10/14/2024 |  |  | 6/30/2024 | 6/30/2024 | 10/21/2024 | N | No
AF2-138 | Flanders-West Wharton 34.5 kV | Mount Olive Solar Farm | NJ | Morris | In Service | JCPL | 19.8 | 19.8 | 8.32 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2138_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2138_imp.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/facilities/af2138_fac.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_138_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_138_csa.pdf | Document Posted | N/A | N/A | 11/1/2022 | 3/10/2020 | N/A | N/A | 11/1/2022 |  |  | 5/31/2023 | 5/31/2023 | 3/15/2023 | N | No
AF2-139 | Gilbert-Warren Glen 34.5 kV | Holland Solar Farm | NJ | Hunterdon | In Service | JCPL | 16.3 | 8.8 | 3.7 | 16 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2139_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2139_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_139_csa.pdf | Document Posted | N/A | N/A |  | 3/10/2020 | N/A | N/A |  |  |  | 8/31/2022 | 8/31/2022 | 7/28/2022 | N | No
AF2-140 | Saegers 230 kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 907 | 0 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2140_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2140_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/gia/af2_140_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 9/1/2024 | 9/1/2024 |  | N | No
AF2-144 | Powhatan 34.5 kV | Scott 1 BESS | VA | Powhatan | In Service | Dominion | 17 | 17 | 10.2 | 17 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2144_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2144_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2144_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2144_wmpa.pdf | Not Required | N/A | N/A |  | 3/12/2020 | N/A | N/A | 5/31/2023 |  |  | 6/1/2023 | 6/1/2023 | 6/1/2023 | N | No
AF2-154 | Dickerson H2 CT 230 kV | Dickerson HCT1, HCT2, DCT1 | MD | Montgomery | In Service | PEPCO | 173 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2154_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2154_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_154_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 4/1/2023 | 4/1/2023 | 5/31/2023 | N | No
AF2-156 | Chalk Point CT2 69 kV | Chalk Point CT 2 | MD | Prince George's | In Service | PEPCO | 30 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2156_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2156_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_156_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 6/22/2023 | 6/22/2023 | 5/31/2023 | N | No
AF2-168 | Princeton University 69 kV | Princeton University Generating Facility | NJ | Mercer | In Service | PSEG | 5 | 5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas; Solar; Other |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2168_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2168_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_168_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_168_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2020 | N/A | N/A |  |  |  | 4/27/2023 | 4/27/2023 | 3/2/2022 | N | No
AF2-178 | Roxbury 23 kV II | Whitetail Solar 1 | PA | Franklin | In Service | PENELEC | 13.5 | 0 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2178_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_178_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 1/12/2021 | N | No
AF2-179 | St. Thomas-Mercersburg 34.5 kV II | Whitetail Solar 2 | PA | Franklin | In Service | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2179_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2179_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_179_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 1/12/2021 | N | No
AF2-180 | St. Thomas-Guilford 34.5 kV II | St Thomas Township Solar Facility | PA | Franklin | In Service | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2180_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2180_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_180_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 | 1/12/2021 | N | No
AF2-184 | McConnelsburg-Mercersburg 34 kV II |  | PA | Franklin | In Service | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2184_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_184_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_184_csa.pdf | Document Posted | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 10/7/2020 |  | 5/1/2023 | N | No
AF2-185 | Mercersburg-Milnor 34.5 kV II | Elk Hill Solar 2 | PA | Franklin | In Service | APS | 15 | 0 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2185_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 1/4/2021 | N | No
AF2-247 | Bustleton 13.2 kV | FLR Florence Landfill | NJ | Burlington | In Service | PSEG | 5 | 5 | 2.1 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2247_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2247_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_247_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_247_csa.pdf | Document Posted | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 6/30/2022 | 6/30/2022 | 3/2/2022 | N | No
AF2-250 | Edgewood 12 kV III | Kumquat Solar | MD | Wicomico | In Service | DPL | 1.95 | 1.95 | 1.1 | 1.95 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2250_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2250_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/af2250_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2250_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/31/2022 | 7/31/2022 | 10/19/2022 | N | No
AF2-305 | Brokaw-Lanesville 345 kV | Alta Farms II | IL | DeWitt | In Service | ComEd | 197 | 0 | 9.2 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2305_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2305_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_305_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/2/2024 | 9/2/2024 | 5/20/2023 | N | No
AF2-317 | Hill Topper 345 kV | Whitney Hill Wind Farm | IL | Logan | In Service | ComEd | 65 | 0 | 15.68 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2317_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2317_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_317_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2022 | 9/1/2022 | 9/1/2022 | N | No
AF2-395 | Flatlick 765 kV | Rolling Hills Generating | OH | Vinton | In Service | AEP | 1045 | 51.1 | 89.6 | 51.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2395_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2395_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_395_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_395_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 4/1/2023 | 4/1/2023 | 2/7/2023 | N | No
AF2-436 | Wyalusing 34.5 kV II | Wyalusing 34.5 kV | PA | Bradford | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2436_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2436_imp.pdf | Document Posted |  |  | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_436_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_436_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 3/18/2021 | N | No
AF2-437 | Oxbow 34.5 kV III | Oxbow Creek Energy | PA | Wyoming | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/af2437_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/af2437_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/af2_437_isa.pdf | Document Posted | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/af2_437_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 | 1/11/2021 | N | No
AG1-044 | Whiteside County | Rock River ESS | IL | Whiteside | In Service | ComEd | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1044_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1044_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1044_wmpa.pdf | Not Required | N/A | N/A |  | 7/1/2020 | N/A | N/A | 4/30/2021 |  |  | 7/30/2021 | 7/30/2021 | 12/27/2021 | Y | No
AG1-063 | Fairhaven 13,8 kV | Fairhaven Battery Energy Storage System | MD | Anne Arundel | In Service | BGE | 2.5 | 2.5 | 0.7 | 2.5 | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1063_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1063_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1063_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2020 | N/A | N/A | 9/19/2024 |  |  | 9/30/2024 | 9/30/2024 | 9/19/2024 | N | No
AG1-145 | Lightfoot 34.5 kV | Norge Solar | VA | James City | In Service | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1145_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1145_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1145_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1145_wmpa.pdf | Not Required | N/A | N/A |  | 9/10/2020 | N/A | N/A | 10/20/2023 |  |  | 10/1/2023 | 10/1/2023 | 11/30/2023 | N | No
AG1-148 | McCarter 26.4 kV | Rutgers Generation | NJ | Essex | In Service | PSEG | 5 | 5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1148_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1148_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1148_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1148_wmpa.pdf | Not Required | N/A | N/A |  | 9/12/2020 | N/A | N/A | 3/21/2024 |  |  | 1/12/2024 | 1/12/2024 |  | N | No
AG1-398 | Brokaw-Lanesville 345 kV | Alta Farms II | IL | Fulton | In Service | ComEd | 197 | 0 | 7.33 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1398_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1398_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_398_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/2/2024 | 9/2/2024 | 5/20/2023 | N | No
AG1-563 | Bennett-Farmingdale 2 34.5 kV | AG1-563 | NJ | Monmouth | In Service | JCPL | 2 | 0 | 0.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1563_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1563_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pjmfiles/pub/planning/project-queues/isa/ag1_563_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2020 |  | 7/16/2021 | N | No
AG1-360 | Costen 25 kV | Costen Solar | MD | Somerset | In Service | DPL | 8.75 | 8.75 | 0 | 8.75 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag1360_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag1360_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag1360_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag1360_wmpa.pdf | Not Required | N/A | N/A | 9/30/2024 | 10/1/2020 | N/A | N/A | 9/30/2024 |  |  | 8/30/2024 | 8/30/2024 | 10/7/2024 | N | No
AG2-050 | Randle Cliff 13.8 kV | CHESAPEAKE BEACH BESS | MD | Calvert | In Service | BGE | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pjmfiles/pub/planning/project-queues/feas_docs/ag2050_fea.pdf | Document Posted | https://www.pjm.com/pjmfiles/pub/planning/project-queues/impact_studies/ag2050_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pjmfiles/pub/planning/project-queues/wmpa/ag2050_wmpa.pdf | https://www.pjm.com/pjmfiles/pub/planning/project-queues/csa/ag2050_wmpa.pdf | Not Required | N/A | N/A |  | 11/25/2020 | N/A | N/A | 5/1/2023 |  |  | 5/1/2023 | 5/1/2023 | 5/9/2023 | Y | No

## Definitions-Mapping
Column Names from Data Tab
Project ID | Project/OASIS ID
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection request process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Generation Interconnection Agreement | After the project’s required study work is completed, PJM will tender a Generation Interconnection Agreement (“GIA”) to be executed by the Project Developer, the Transmission Owner, and PJM.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Submitted Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Project
Sliding Project